## Summary
SO No | Item Code | Item Name | Ordered Qty | SO Delivery Date | Expected Completion | Days Late | Working (days) | Waiting: machine (days) | Waiting: off-hours (days) | Waiting: crew (days) | Why
26-27SO84 | 2109801 | PIPE FOR LKHSP 25 TANK PIPE LENGTH 39.4 MM | 50 | 16-07-2026 | 14-08-2026 | 29 | 0.1 | 0.9 | 3 | 1.5 | 29 days late — 0.9d machines busy (higher-priority orders), 3.0d off-hours, 1.5d waiting for operators
26-27SO113 | 9611416360 | AIR CYLINDER BOTTOM FOR LKLA 304 | 500 | 22-07-2026 | 15-08-2026 | 24 | 4.3 | 1.5 | 0.2 | 0.6 | 24 days late — 1.5d machines busy (higher-priority orders), 0.2d off-hours, 0.6d waiting for operators
26-27SO113 | 9612193501 | END CAP W/O PIN LKLA-T | 1000 | 30-07-2026 | 18-08-2026 | 19 | 9.1 | 0 | 0.1 | 0.5 | 19 days late — 0.1d off-hours, 0.5d waiting for operators
26-27SO131 | 8010005735 | HUB SMALL END MACHINED,NX910 PART ID; 8010005735 | 15 | 24-08-2026 | 12-09-2026 | 19 | 10.2 | 22.3 | 1.5 | 0.6 | 19 days late — 22.3d machines busy (higher-priority orders), 1.5d off-hours, 0.6d waiting for operators
26-27SO68 | 61241992-01 | GREASE DEFLECTOR | 15 | 01-08-2026 | 16-08-2026 | 15 | 2.9 | 3.2 | 0.4 | 1.2 | 15 days late — 3.2d machines busy (higher-priority orders), 0.4d off-hours, 1.2d waiting for operators
26-27SO98 | 61239701-01 | COVER 8 KNM DD GEAR- | 15 | 17-08-2026 | 01-09-2026 | 15 | 5 | 8.7 | 2.2 | 7.7 | 15 days late — 8.7d machines busy (higher-priority orders), 2.2d off-hours, 7.7d waiting for operators
26-27SO75 | 61235943-01 | COVER 3.5 KNM DD GEAR | 10 | 20-08-2026 | 04-09-2026 | 15 | 4.5 | 19.9 | 1.6 | 0.5 | 15 days late — 19.9d machines busy (higher-priority orders), 1.6d off-hours, 0.5d waiting for operators
26-27SO94 | 6003009 | PIPE BLANK F122/110L/2 THK FOR LKGG 101.6 SS304 | 20 | 08-08-2026 | 21-08-2026 | 13 | 0 | 4.4 | 5.6 | 2.3 | 13 days late — 4.4d machines busy (higher-priority orders), 5.6d off-hours, 2.3d waiting for operators
26-27SO96 | 6003009 | PIPE BLANK F122/110L/2 THK FOR LKGG 101.6 SS304 | 20 | 08-08-2026 | 21-08-2026 | 13 | 0 | 4.4 | 5.6 | 2.3 | 13 days late — 4.4d machines busy (higher-priority orders), 5.6d off-hours, 2.3d waiting for operators
26-27SO95 | 61248811-01 | COVER NX 4450 | 10 | 02-08-2026 | 14-08-2026 | 12 | 1.1 | 3.1 | 0.2 | 1.1 | 12 days late — 3.1d machines busy (higher-priority orders), 0.2d off-hours, 1.1d waiting for operators
26-27SO117 | 00531569-01 | COVER,2.5KNM GEAR BOX | 25 | 17-08-2026 | 29-08-2026 | 12 | 8.3 | 11.4 | 0.4 | 0.5 | 12 days late — 11.4d machines busy (higher-priority orders), 0.4d off-hours, 0.5d waiting for operators
26-27SO93 | 61249330-80 | HUB SMALL END BOWL NX 5040 | 6 | 08-09-2026 | 20-09-2026 | 12 | 9.4 | 19.8 | 2.9 | 10.4 | 12 days late — 19.8d machines busy (higher-priority orders), 2.9d off-hours, 10.4d waiting for operators
26-27SO128 | 61249396-01 | LABYRINTH RING NX5040 | 20 | 20-08-2026 | 30-08-2026 | 10 | 2.5 | 13.1 | 2 | 4 | 10 days late — 13.1d machines busy (higher-priority orders), 2.0d off-hours, 4.0d waiting for operators
26-27SO130 | 61249330-80 | HUB SMALL END BOWL NX 5040 | 5 | 17-08-2026 | 26-08-2026 | 9 | 8.1 | 5.8 | 1.8 | 2 | 9 days late — 5.8d machines busy (higher-priority orders), 1.8d off-hours, 2.0d waiting for operators
26-27SO69 | 8010009209 | RETAINING RING NX 4450 | 10 | 10-08-2026 | 18-08-2026 | 8 | 4.7 | 4.2 | 0.2 | 0.5 | 8 days late — 4.2d machines busy (higher-priority orders), 0.2d off-hours, 0.5d waiting for operators
26-27SO134 | 9612220708 P | NRV CONE FSHD 38 316L 3A POLISH | 135 | 22-08-2026 | 30-08-2026 | 8 | 0.4 | 15.9 | 4.2 | 1.2 | 8 days late — 15.9d machines busy (higher-priority orders), 4.2d off-hours, 1.2d waiting for operators
26-27SO135 | 9612220704-P | NRV CONE 63 316L | 400 | 22-08-2026 | 30-08-2026 | 8 | 1.5 | 14.4 | 4.3 | 1.4 | 8 days late — 14.4d machines busy (higher-priority orders), 4.3d off-hours, 1.4d waiting for operators
26-27SO136 | 9612220704-P | NRV CONE 63 316L | 23 | 22-08-2026 | 30-08-2026 | 8 | 1.5 | 14.4 | 4.3 | 1.4 | 8 days late — 14.4d machines busy (higher-priority orders), 4.3d off-hours, 1.4d waiting for operators
26-27SO95 | 8010009209 | RETAINING RING NX 4450 | 10 | 10-08-2026 | 18-08-2026 | 8 | 4.7 | 4.2 | 0.2 | 0.5 | 8 days late — 4.2d machines busy (higher-priority orders), 0.2d off-hours, 0.5d waiting for operators
26-27SO139 | 9611443241 | BFV BODY FSHD 63 316L | 100 | 22-08-2026 | 30-08-2026 | 8 | 8.2 | 9.9 | 2.5 | 1 | 8 days late — 9.9d machines busy (higher-priority orders), 2.5d off-hours, 1.0d waiting for operators
26-27SO140 | 9611443241 | BFV BODY FSHD 63 316L | 400 | 22-08-2026 | 30-08-2026 | 8 | 8.2 | 9.9 | 2.5 | 1 | 8 days late — 9.9d machines busy (higher-priority orders), 2.5d off-hours, 1.0d waiting for operators
26-27SO132 | 61239819-81 | HUB SMALL END NX904 | 8 | 14-08-2026 | 22-08-2026 | 8 | 5.1 | 7.3 | 0.5 | 0.5 | 8 days late — 7.3d machines busy (higher-priority orders), 0.5d off-hours, 0.5d waiting for operators
26-27SO104 | 61249522-01 | SEAL RING NX4450 | 15 | 10-08-2026 | 17-08-2026 | 7 | 3.1 | 4 | 0.5 | 1.2 | 7 days late — 4.0d machines busy (higher-priority orders), 0.5d off-hours, 1.2d waiting for operators
26-27SO146 | 61240401-01 | COVER 1.5KNM GEAR | 20 | 01-09-2026 | 08-09-2026 | 7 | 6.3 | 11.3 | 2.8 | 10.3 | 7 days late — 11.3d machines busy (higher-priority orders), 2.8d off-hours, 10.3d waiting for operators
26-27SO126 | 971-571126-03 | SLIDING BOWL BOTTOM | 15 | 05-08-2026 | 11-08-2026 | 6 | 2.2 | 0 | 0.1 | 0.5 | 6 days late — 0.1d off-hours, 0.5d waiting for operators
26-27SO137 | 9612220701-P | NRV CONE 25 316L | 119 | 22-08-2026 | 28-08-2026 | 6 | 0.9 | 13.7 | 3.9 | 1 | 6 days late — 13.7d machines busy (higher-priority orders), 3.9d off-hours, 1.0d waiting for operators
26-27SO138 | 9612220701-P | NRV CONE 25 316L | 219 | 22-08-2026 | 28-08-2026 | 6 | 0.9 | 13.7 | 3.9 | 1 | 6 days late — 13.7d machines busy (higher-priority orders), 3.9d off-hours, 1.0d waiting for operators
26-27SO120 | 9611443240 | BFV BODY FSHD 63 304L | 254 | 19-08-2026 | 24-08-2026 | 5 | 8.8 | 4.7 | 1.4 | 0.8 | 5 days late — 4.7d machines busy (higher-priority orders), 1.4d off-hours, 0.8d waiting for operators
26-27SO122 | 9611443240 | BFV BODY FSHD 63 304L | 281 | 19-08-2026 | 24-08-2026 | 5 | 8.8 | 4.7 | 1.4 | 0.8 | 5 days late — 4.7d machines busy (higher-priority orders), 1.4d off-hours, 0.8d waiting for operators
26-27SO111 | 61241989-01 | THURST RING TRACE | 15 | 10-08-2026 | 15-08-2026 | 5 | 2.3 | 2.2 | 0.9 | 1.2 | 5 days late — 2.2d machines busy (higher-priority orders), 0.9d off-hours, 1.2d waiting for operators
26-27SO117 | 61239857-01 | RING NX 904 | 30 | 17-08-2026 | 21-08-2026 | 4 | 4.5 | 5.4 | 0.9 | 1.5 | 4 days late — 5.4d machines busy (higher-priority orders), 0.9d off-hours, 1.5d waiting for operators
26-27SO118 | 61239614-01 | GEARBOX ADAPTOR NX910 | 10 | 22-08-2026 | 26-08-2026 | 4 | 2.2 | 9.3 | 3.1 | 2.8 | 4 days late — 9.3d machines busy (higher-priority orders), 3.1d off-hours, 2.8d waiting for operators
26-27SO134 | 9612220705-P | NRV CONE 76 316L | 232 | 19-08-2026 | 22-08-2026 | 3 | 1.2 | 8.9 | 2.5 | 1 | 3 days late — 8.9d machines busy (higher-priority orders), 2.5d off-hours, 1.0d waiting for operators
26-27SO129 | 9612139601 | IMPELLER SCREW M8 LKH SS 316L | 400 | 06-08-2026 | 09-08-2026 | 3 | 0 | 0 | 0 | 0 | 3 days late
26-27SO149 | 9611443651 | BFV BODY FSHD 25 316L | 120 | 29-08-2026 | 01-09-2026 | 3 | 4.5 | 14.9 | 1.3 | 3.1 | 3 days late — 14.9d machines busy (higher-priority orders), 1.3d off-hours, 3.1d waiting for operators
26-27SO150 | 9611443651 | BFV BODY FSHD 25 316L | 180 | 29-08-2026 | 01-09-2026 | 3 | 4.5 | 14.9 | 1.3 | 3.1 | 3 days late — 14.9d machines busy (higher-priority orders), 1.3d off-hours, 3.1d waiting for operators
26-27SO105 | 9612220703-P | NRV CONE 51 316L | 300 | 15-08-2026 | 17-08-2026 | 2 | 2.8 | 3.5 | 1.4 | 0.8 | 2 days late — 3.5d machines busy (higher-priority orders), 1.4d off-hours, 0.8d waiting for operators
26-27SO134 | 9612220703-P | NRV CONE 51 316L | 445 | 15-08-2026 | 17-08-2026 | 2 | 2.8 | 3.5 | 1.4 | 0.8 | 2 days late — 3.5d machines busy (higher-priority orders), 1.4d off-hours, 0.8d waiting for operators
26-27SO134 | 9612220704-P | NRV CONE 63 316L | 377 | 15-08-2026 | 17-08-2026 | 2 | 1.2 | 5.3 | 1.4 | 0.8 | 2 days late — 5.3d machines busy (higher-priority orders), 1.4d off-hours, 0.8d waiting for operators
26-27SO148 | 9612220703-P | NRV CONE 51 316L | 355 | 29-08-2026 | 31-08-2026 | 2 | 1.7 | 15.9 | 3.8 | 1.2 | 2 days late — 15.9d machines busy (higher-priority orders), 3.8d off-hours, 1.2d waiting for operators
26-27SO148 | 9612220705-P | NRV CONE 76 316L | 144 | 29-08-2026 | 31-08-2026 | 2 | 0.8 | 16.9 | 3.8 | 1.2 | 2 days late — 16.9d machines busy (higher-priority orders), 3.8d off-hours, 1.2d waiting for operators
26-27SO143 | 61240222-01 | COVER GEARBOX NX 904 | 20 | 14-09-2026 | 16-09-2026 | 2 | 3 | 24.2 | 2.9 | 8.6 | 2 days late — 24.2d machines busy (higher-priority orders), 2.9d off-hours, 8.6d waiting for operators
26-27SO143 | 61240190-01 | GEARBOX COVER SPINE NX 904 | 20 | 14-09-2026 | 15-09-2026 | 1 | 2.8 | 32.3 | 1.9 | 0.8 | 1 days late — 32.3d machines busy (higher-priority orders), 1.9d off-hours, 0.8d waiting for operators
26-27SO134 | 9612220701-P | NRV CONE 25 316L | 280 | 15-08-2026 | 15-08-2026 | 0 | 2.9 | 2.5 | 0.2 | 0.8 | On time.
26-27SO117 | 61240807-01 | RING NX910 REV 002 TRACE | 20 | 17-08-2026 | 17-08-2026 | 0 | 1.3 | 4.4 | 1.2 | 1.4 | On time.
26-27SO143 | 61239701-01 | COVER 8 KNM DD GEAR- | 15 | 14-09-2026 | 14-09-2026 | 0 | 6.5 | 27.6 | 1.6 | 0.8 | On time.
26-27SO133 | 9611443650 | BFV BODY FSHD 25 304L | 490 | 19-08-2026 | 18-08-2026 | -1 | 2.8 | 4.4 | 1.2 | 1.1 | On time.
26-27SO108 | 61240341-80 | HUB LARGE END NX910 316 | 15 | 24-08-2026 | 23-08-2026 | -1 | 9 | 1 | 1.6 | 3 | On time.
26-27SO137 | 9611340324-P | FERRULE W.G14AC 76 316L FOR USA | 100 | 12-08-2026 | 10-08-2026 | -2 | 0.6 | 0 | 0.3 | 0.5 | On time.
26-27SO144 | 9612358901 | PIPE COOLING (HEX) | 250 | 19-08-2026 | 16-08-2026 | -3 | 0.8 | 1 | 3.5 | 2 | On time.
26-27SO147 | 8010009209 | RETAINING RING NX 4450 | 10 | 22-09-2026 | 19-09-2026 | -3 | 2.4 | 34.3 | 2.8 | 2.1 | On time.
26-27SO105 | 9612220702-P | NRV CONE 38 316L | 100 | 15-08-2026 | 10-08-2026 | -5 | 0.3 | 0.5 | 0.2 | 0.6 | On time.
26-27SO142 | 8010009209 | RETAINING RING NX 4450 | 10 | 25-09-2026 | 20-09-2026 | -5 | 3.7 | 36.2 | 1.8 | 1 | On time.
26-27SO134 | 9612220710 P | NRV CONE FSHD 63 316L | 147 | 22-08-2026 | 16-08-2026 | -6 | 0.5 | 3.8 | 1.9 | 1.2 | On time.
26-27SO98 | 61239614-01 | GEARBOX ADAPTOR NX910 | 18 | 08-10-2026 | 29-09-2026 | -9 | 3.9 | 37.6 | 6.4 | 3.7 | On time.
26-27SO145 | 61249396-01 | LABYRINTH RING NX5040 | 24 | 11-09-2026 | 02-09-2026 | -9 | 3 | 9.9 | 3.5 | 8.2 | On time.
26-27SO88 | 61249330-80 | HUB SMALL END BOWL NX 5040 | 6 | 08-10-2026 | 28-09-2026 | -10 | 8.1 | 28.5 | 3 | 10.9 | On time.
26-27SO143 | 61249291-01 | END PIECE CONVEYOR NX 5040 | 11 | 14-09-2026 | 04-09-2026 | -10 | 0.4 | 12.7 | 5 | 8.4 | On time.

## Detail
SO No | Item Code | State | Process | Machine | Operator | From | To | Hours | Why
26-27SO84 | 2109801 | WAITING (off-hours) |  |  |  | 09-08-2026 00:00 | 09-08-2026 08:00 | 8 | Outside working hours (night / weekly off / holiday)
26-27SO84 | 2109801 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 18:46 | 10.77 | Machine free — waiting for a free qualified operator
26-27SO84 | 2109801 | WAITING (machine busy) |  | MD2 |  | 09-08-2026 18:46 | 10-08-2026 15:56 | 21.17 | MD2 busy with 26-27SO133 / 9611443650 — DEBURING (higher priority)
26-27SO84 | 2109801 | WAITING (crew) |  |  |  | 10-08-2026 15:56 | 10-08-2026 19:00 | 3.06 | Machine free — waiting for a free qualified operator
26-27SO84 | 2109801 | WAITING (off-hours) |  |  |  | 10-08-2026 19:00 | 11-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO84 | 2109801 | WAITING (crew) |  |  |  | 11-08-2026 08:00 | 11-08-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO84 | 2109801 | WAITING (off-hours) |  |  |  | 11-08-2026 19:00 | 12-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO84 | 2109801 | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO84 | 2109801 | WAITING (off-hours) |  |  |  | 12-08-2026 19:00 | 14-08-2026 08:00 | 37 | Outside working hours (night / weekly off / holiday)
26-27SO84 | 2109801 | RUNNING | 3. DEBURING | MD2 | Sanjay | 14-08-2026 08:00 | 14-08-2026 08:50 | 0.83
26-27SO84 | 2109801 | RUNNING | 4. PACKING | MD2 | Sanjay | 14-08-2026 08:50 | 14-08-2026 09:40 | 0.83
26-27SO113 | 9611416360 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO113 | 9611416360 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO113 | 9611416360 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO113 | 9611416360 | WAITING (machine busy) |  | CNC5 |  | 09-08-2026 14:00 | 11-08-2026 02:22 | 36.38 | CNC5 busy with 26-27SO113 / 9612193501 — CNC FIRST SIDE
26-27SO113 | 9611416360 | WAITING (crew) |  |  |  | 11-08-2026 02:22 | 11-08-2026 05:00 | 2.62 | Machine free — waiting for a free qualified operator
26-27SO113 | 9611416360 | WAITING (off-hours) |  |  |  | 11-08-2026 05:00 | 11-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO113 | 9611416360 | RUNNING | 2. CNC FIRST SIDE | CNC5 | Rajiv Kumar → Anil Kumar | 11-08-2026 08:00 | 11-08-2026 20:56 | 12.94
26-27SO113 | 9611416360 | RUNNING | 3. CNC SECOND SIDE | CNC4 | Sandeep Kumar → Murali → Anil Kumar | 11-08-2026 16:19 | 12-08-2026 22:22 | 30.06
26-27SO113 | 9611416360 | RUNNING | 4. VMC FIRST SIDE | VMC2 | Saif → Rupesh Pawar | 11-08-2026 20:31 | 14-08-2026 18:07 | 69.6
26-27SO113 | 9611416360 | RUNNING | 5. DEBURING | MD1 | Anturam | 14-08-2026 12:37 | 14-08-2026 18:07 | 5.5
26-27SO113 | 9611416360 | RUNNING | 6. INSP | MI1 | Nitin Khade | 14-08-2026 13:10 | 15-08-2026 13:10 | 24
26-27SO113 | 9611416360 | RUNNING | 7. WASHING | MW2 | HP2 → Sanjay | 14-08-2026 15:50 | 15-08-2026 13:10 | 21.33
26-27SO113 | 9611416360 | RUNNING | 8. PACKING | MPK2 | HP2 | 15-08-2026 10:33 | 15-08-2026 14:43 | 4.17
26-27SO113 | 9612193501 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO113 | 9612193501 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO113 | 9612193501 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO113 | 9612193501 | RUNNING | 2. CNC FIRST SIDE | CNC5 | Swapnil → Anil Kumar | 09-08-2026 14:00 | 11-08-2026 02:22 | 36.38
26-27SO113 | 9612193501 | RUNNING | 3. CNC SECOND SIDE | CNC4 | Sandeep Kumar → Murali | 09-08-2026 18:50 | 11-08-2026 16:19 | 45.48
26-27SO113 | 9612193501 | RUNNING | 4. VMC FIRST SIDE | VMC1 | Rupesh Pawar → Saif → Mahesh → Ankush Jadhav | 10-08-2026 15:56 | 12-08-2026 15:26 | 47.5
26-27SO113 | 9612193501 | RUNNING | 5. CHAMFER | DTC2 | Anturam | 11-08-2026 09:46 | 12-08-2026 15:26 | 29.67
26-27SO113 | 9612193501 | RUNNING | 6. RETAPP | DTC2 | Anturam | 12-08-2026 15:26 | 14-08-2026 08:36 | 41.17
26-27SO113 | 9612193501 | RUNNING | 7. WASHING | MW1 | HP1 | 12-08-2026 15:51 | 15-08-2026 10:31 | 66.67
26-27SO113 | 9612193501 | RUNNING | 8. INSPECTION | MI3 | Sidhanath | 14-08-2026 11:31 | 18-08-2026 17:31 | 102
26-27SO113 | 9612193501 | RUNNING | 9. PACKING | MPK1 | HP1 | 18-08-2026 13:21 | 18-08-2026 17:31 | 4.17
26-27SO131 | 8010005735 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO131 | 8010005735 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO131 | 8010005735 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO131 | 8010005735 | WAITING (machine busy) |  | CNC3 |  | 09-08-2026 14:00 | 10-08-2026 13:48 | 23.8 | CNC3 busy with 26-27SO126 / 971-571126-03 — CNC FORTH SIDE (higher priority)
26-27SO131 | 8010005735 | WAITING (machine busy) |  | CNC3 |  | 10-08-2026 13:48 | 12-08-2026 19:18 | 53.5 | CNC3 busy with 26-27SO108 / 61240341-80 — CNC SECOND SIDE (higher priority)
26-27SO131 | 8010005735 | WAITING (machine busy) |  | CNC3 |  | 12-08-2026 19:18 | 14-08-2026 17:48 | 46.5 | CNC3 busy with 26-27SO69 / 8010009209 — CNC SECOND SIDE (higher priority)
26-27SO131 | 8010005735 | WAITING (machine busy) |  | CNC3 |  | 14-08-2026 17:48 | 16-08-2026 03:30 | 33.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC FIRST SIDE (higher priority)
26-27SO131 | 8010005735 | WAITING (crew) |  |  |  | 16-08-2026 03:30 | 16-08-2026 05:00 | 1.5 | Machine free — waiting for a free qualified operator
26-27SO131 | 8010005735 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO131 | 8010005735 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 08:00 | 16-08-2026 23:54 | 15.9 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC SECOND SIDE (higher priority)
26-27SO131 | 8010005735 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 23:54 | 17-08-2026 05:00 | 5.1 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC FIRST SIDE (higher priority)
26-27SO131 | 8010005735 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO131 | 8010005735 | WAITING (machine busy) |  | CNC3 |  | 17-08-2026 08:00 | 17-08-2026 17:30 | 9.5 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC SECOND SIDE (higher priority)
26-27SO131 | 8010005735 | WAITING (machine busy) |  | CNC3 |  | 17-08-2026 17:30 | 18-08-2026 14:00 | 20.5 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC THIRD SIDE (higher priority)
26-27SO131 | 8010005735 | WAITING (machine busy) |  | CNC3 |  | 18-08-2026 14:00 | 19-08-2026 11:42 | 21.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC THIRD SIDE (higher priority)
26-27SO131 | 8010005735 | WAITING (machine busy) |  | CNC3 |  | 19-08-2026 11:42 | 23-08-2026 10:12 | 94.5 | CNC3 busy with 26-27SO117 / 00531569-01 — CNC FIRST SIDE (higher priority)
26-27SO131 | 8010005735 | RUNNING | 1. CNC FIRST SIDE | CNC3 | Rohan Chakane → Khansab Mulla | 23-08-2026 10:12 | 25-08-2026 08:42 | 46.5
26-27SO131 | 8010005735 | WAITING (machine busy) |  | CNC3 |  | 25-08-2026 08:42 | 28-08-2026 18:12 | 81.5 | CNC3 busy with 26-27SO117 / 00531569-01 — CNC SECOND SIDE (higher priority)
26-27SO131 | 8010005735 | WAITING (machine busy) |  | CNC3 |  | 28-08-2026 18:12 | 31-08-2026 11:42 | 65.5 | CNC3 busy with 26-27SO75 / 61235943-01 — CNC FIRST SIDE (higher priority)
26-27SO131 | 8010005735 | WAITING (machine busy) |  | CNC3 |  | 31-08-2026 11:42 | 01-09-2026 12:42 | 25 | CNC3 busy with 26-27SO98 / 61239701-01 — CNC THIRD SIDE (higher priority)
26-27SO131 | 8010005735 | WAITING (machine busy) |  | CNC3 |  | 01-09-2026 12:42 | 03-09-2026 03:12 | 38.5 | CNC3 busy with 26-27SO75 / 61235943-01 — CNC SECOND SIDE (higher priority)
26-27SO131 | 8010005735 | WAITING (crew) |  |  |  | 03-09-2026 03:12 | 03-09-2026 05:00 | 1.8 | Machine free — waiting for a free qualified operator
26-27SO131 | 8010005735 | WAITING (off-hours) |  |  |  | 03-09-2026 05:00 | 04-09-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO131 | 8010005735 | RUNNING | 2. CNC SECOND SIDE | CNC3 | Sidhu Singe → Khansab Mulla → Rohan Chakane | 04-09-2026 08:00 | 06-09-2026 16:30 | 56.5
26-27SO131 | 8010005735 | RUNNING | 3. VMC FIRST SIDE | VMC3 | Rupesh Pawar → Mahesh → Ankush Jadhav → Saif | 04-09-2026 13:24 | 08-09-2026 08:54 | 91.5
26-27SO131 | 8010005735 | RUNNING | 4. VMC SECOND SIDE | VMC3 | Ankush Jadhav → Saif → Rupesh Pawar | 08-09-2026 08:54 | 09-09-2026 22:24 | 37.5
26-27SO131 | 8010005735 | RUNNING | 5. CNC THIRD SIDE | CNC6 | Khansab Mulla → Sidhu Singe | 08-09-2026 23:54 | 09-09-2026 22:24 | 22.5
26-27SO131 | 8010005735 | RUNNING | 6. CNC FORTH SIDE | CNC6 | Khansab Mulla → Rohan Chakane | 09-09-2026 22:24 | 11-09-2026 20:54 | 46.5
26-27SO131 | 8010005735 | RUNNING | 7. CHAMFER | DTC2 | Anturam | 11-09-2026 08:00 | 12-09-2026 12:00 | 28
26-27SO131 | 8010005735 | RUNNING | 8. CMM | CMM | Kiran Mohite | 11-09-2026 09:30 | 12-09-2026 13:30 | 28
26-27SO131 | 8010005735 | RUNNING | 9. WASHING | MW1 | HP1 | 12-09-2026 12:15 | 12-09-2026 13:30 | 1.25
26-27SO131 | 8010005735 | RUNNING | 10. PACKING | MPK1 | HP2 | 12-09-2026 12:22 | 12-09-2026 13:37 | 1.25
26-27SO68 | 61241992-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO68 | 61241992-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO68 | 61241992-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 10-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO68 | 61241992-01 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO68 | 61241992-01 | WAITING (machine busy) |  | CNC7 |  | 10-08-2026 08:00 | 10-08-2026 13:30 | 5.5 | CNC7 busy with 26-27SO95 / 61248811-01 — CNC FIRST SIDE (higher priority)
26-27SO68 | 61241992-01 | WAITING (machine busy) |  | CNC7 |  | 10-08-2026 13:30 | 11-08-2026 03:00 | 13.5 | CNC7 busy with 26-27SO95 / 61248811-01 — CNC SECOND SIDE (higher priority)
26-27SO68 | 61241992-01 | WAITING (crew) |  |  |  | 11-08-2026 03:00 | 11-08-2026 05:00 | 2 | Machine free — waiting for a free qualified operator
26-27SO68 | 61241992-01 | WAITING (off-hours) |  |  |  | 11-08-2026 05:00 | 11-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO68 | 61241992-01 | RUNNING | 1. CNC FIRST SIDE | CNC7 | Sidhu Singe | 11-08-2026 08:00 | 12-08-2026 12:00 | 28
26-27SO68 | 61241992-01 | WAITING (machine busy) |  | VMC2 |  | 12-08-2026 12:00 | 14-08-2026 18:07 | 54.12 | VMC2 busy with 26-27SO113 / 9611416360 — VMC FIRST SIDE (higher priority)
26-27SO68 | 61241992-01 | RUNNING | 2. VMC FIRST SIDE | VMC2 | Rupesh Pawar → Saif | 14-08-2026 18:07 | 15-08-2026 04:37 | 10.5
26-27SO68 | 61241992-01 | RUNNING | 3. CNC SECOND SIDE | CNC7 | Khansab Mulla → Rohan Chakane | 14-08-2026 21:36 | 15-08-2026 15:00 | 17.4
26-27SO68 | 61241992-01 | RUNNING | 4. CHAMFER | DTC2 | Anturam | 15-08-2026 12:30 | 15-08-2026 15:00 | 2.5
26-27SO68 | 61241992-01 | WAITING (crew) |  |  |  | 15-08-2026 15:00 | 15-08-2026 15:20 | 0.33 | Machine free — waiting for a free qualified operator
26-27SO68 | 61241992-01 | WAITING (machine busy) |  | CMM |  | 15-08-2026 15:20 | 15-08-2026 18:40 | 3.33 | CMM busy with 26-27SO117 / 61240807-01 — CMM
26-27SO68 | 61241992-01 | RUNNING | 5. CMM | CMM | Kiran Mohite | 15-08-2026 18:40 | 16-08-2026 11:25 | 16.75
26-27SO68 | 61241992-01 | RUNNING | 6. INSPECTION | MI1 | Nitin Khade | 16-08-2026 10:27 | 16-08-2026 14:12 | 3.75
26-27SO68 | 61241992-01 | RUNNING | 7. WASHING | MW1 | HP1 | 16-08-2026 13:27 | 16-08-2026 14:12 | 0.75
26-27SO68 | 61241992-01 | RUNNING | 8. PACKING | MPK2 | HP2 | 16-08-2026 13:42 | 16-08-2026 14:12 | 0.5
26-27SO98 | 61239701-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239701-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239701-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239701-01 | WAITING (machine busy) |  | CNC6 |  | 09-08-2026 14:00 | 10-08-2026 00:00 | 10 | CNC6 busy with 26-27SO130 / 61249330-80 — CNC SECOND SIDE (higher priority)
26-27SO98 | 61239701-01 | WAITING (crew) |  |  |  | 10-08-2026 00:00 | 10-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239701-01 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239701-01 | WAITING (crew) |  |  |  | 10-08-2026 08:00 | 11-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239701-01 | WAITING (off-hours) |  |  |  | 11-08-2026 05:00 | 11-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239701-01 | WAITING (crew) |  |  |  | 11-08-2026 08:00 | 12-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239701-01 | WAITING (off-hours) |  |  |  | 12-08-2026 05:00 | 12-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239701-01 | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 13-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239701-01 | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239701-01 | WAITING (crew) |  |  |  | 14-08-2026 08:00 | 15-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239701-01 | WAITING (off-hours) |  |  |  | 15-08-2026 05:00 | 15-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239701-01 | WAITING (crew) |  |  |  | 15-08-2026 08:00 | 16-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239701-01 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239701-01 | WAITING (crew) |  |  |  | 16-08-2026 08:00 | 17-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239701-01 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239701-01 | WAITING (crew) |  |  |  | 17-08-2026 08:00 | 18-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239701-01 | WAITING (off-hours) |  |  |  | 18-08-2026 05:00 | 18-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239701-01 | WAITING (crew) |  |  |  | 18-08-2026 08:00 | 19-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239701-01 | WAITING (off-hours) |  |  |  | 19-08-2026 05:00 | 19-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239701-01 | WAITING (machine busy) |  | CNC6 |  | 19-08-2026 08:00 | 21-08-2026 09:30 | 49.5 | CNC6 busy with 26-27SO108 / 61240341-80 — CNC THIRD SIDE (higher priority)
26-27SO98 | 61239701-01 | WAITING (machine busy) |  | CNC6 |  | 21-08-2026 09:30 | 21-08-2026 14:12 | 4.7 | CNC6 busy with 26-27SO132 / 61239819-81 — CNC FORTH SIDE (higher priority)
26-27SO98 | 61239701-01 | RUNNING | 2. CNC FIRST SIDE | CNC6 | Rohan Chakane → Sidhu Singe | 21-08-2026 14:12 | 23-08-2026 08:42 | 42.5
26-27SO98 | 61239701-01 | WAITING (machine busy) |  | VMC3 |  | 23-08-2026 08:42 | 23-08-2026 21:00 | 12.3 | VMC3 busy with 26-27SO130 / 61249330-80 — VMC SECOND SIDE (higher priority)
26-27SO98 | 61239701-01 | RUNNING | 3. VMC FIRST SIDE | VMC3 | Mahesh → Rupesh Pawar | 23-08-2026 21:00 | 24-08-2026 12:00 | 15
26-27SO98 | 61239701-01 | RUNNING | 4. VMC SECOND SIDE | VMC2 | Ankush Jadhav | 24-08-2026 08:00 | 24-08-2026 15:30 | 7.5
26-27SO98 | 61239701-01 | WAITING (machine busy) |  | CNC6 |  | 24-08-2026 15:30 | 25-08-2026 09:02 | 17.53 | CNC6 busy with 26-27SO130 / 61249330-80 — CNC THIRD SIDE (higher priority)
26-27SO98 | 61239701-01 | WAITING (machine busy) |  | CNC6 |  | 25-08-2026 09:02 | 26-08-2026 12:52 | 27.83 | CNC6 busy with 26-27SO130 / 61249330-80 — CNC FORTH SIDE (higher priority)
26-27SO98 | 61239701-01 | WAITING (machine busy) |  | CNC6 |  | 26-08-2026 12:52 | 28-08-2026 20:52 | 56 | CNC6 busy with 26-27SO117 / 00531569-01 — CNC THIRD SIDE (higher priority)
26-27SO98 | 61239701-01 | RUNNING | 5. CNC SECOND SIDE | CNC6 | Khansab Mulla → Rohan Chakane | 28-08-2026 20:52 | 30-08-2026 04:22 | 31.5
26-27SO98 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 30-08-2026 04:22 | 31-08-2026 11:42 | 31.33 | CNC3 busy with 26-27SO75 / 61235943-01 — CNC FIRST SIDE
26-27SO98 | 61239701-01 | RUNNING | 6. CNC THIRD SIDE | CNC3 | Rohan Chakane → Sidhu Singe | 31-08-2026 11:42 | 01-09-2026 12:42 | 25
26-27SO98 | 61239701-01 | RUNNING | 7. CHAMFER | DTC2 | Anturam | 01-09-2026 11:27 | 01-09-2026 12:42 | 1.25
26-27SO98 | 61239701-01 | RUNNING | 8. CMM | CMM | Kiran Mohite | 01-09-2026 11:34 | 01-09-2026 15:19 | 3.75
26-27SO98 | 61239701-01 | RUNNING | 9. INSPECTION | MI1 | Nitin Khade | 01-09-2026 11:57 | 01-09-2026 15:42 | 3.75
26-27SO98 | 61239701-01 | RUNNING | 10. PACKING | MPK1 | HP1 | 01-09-2026 14:27 | 01-09-2026 15:42 | 1.25
26-27SO75 | 61235943-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO75 | 61235943-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO75 | 61235943-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO75 | 61235943-01 | WAITING (machine busy) |  | CNC3 |  | 09-08-2026 14:00 | 10-08-2026 13:48 | 23.8 | CNC3 busy with 26-27SO126 / 971-571126-03 — CNC FORTH SIDE (higher priority)
26-27SO75 | 61235943-01 | WAITING (machine busy) |  | CNC3 |  | 10-08-2026 13:48 | 12-08-2026 19:18 | 53.5 | CNC3 busy with 26-27SO108 / 61240341-80 — CNC SECOND SIDE (higher priority)
26-27SO75 | 61235943-01 | WAITING (machine busy) |  | CNC3 |  | 12-08-2026 19:18 | 14-08-2026 17:48 | 46.5 | CNC3 busy with 26-27SO69 / 8010009209 — CNC SECOND SIDE (higher priority)
26-27SO75 | 61235943-01 | WAITING (machine busy) |  | CNC3 |  | 14-08-2026 17:48 | 16-08-2026 03:30 | 33.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC FIRST SIDE (higher priority)
26-27SO75 | 61235943-01 | WAITING (crew) |  |  |  | 16-08-2026 03:30 | 16-08-2026 05:00 | 1.5 | Machine free — waiting for a free qualified operator
26-27SO75 | 61235943-01 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO75 | 61235943-01 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 08:00 | 16-08-2026 23:54 | 15.9 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC SECOND SIDE (higher priority)
26-27SO75 | 61235943-01 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 23:54 | 17-08-2026 05:00 | 5.1 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC FIRST SIDE (higher priority)
26-27SO75 | 61235943-01 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO75 | 61235943-01 | WAITING (machine busy) |  | CNC3 |  | 17-08-2026 08:00 | 17-08-2026 17:30 | 9.5 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC SECOND SIDE (higher priority)
26-27SO75 | 61235943-01 | WAITING (machine busy) |  | CNC3 |  | 17-08-2026 17:30 | 18-08-2026 14:00 | 20.5 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC THIRD SIDE (higher priority)
26-27SO75 | 61235943-01 | WAITING (machine busy) |  | CNC3 |  | 18-08-2026 14:00 | 19-08-2026 11:42 | 21.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC THIRD SIDE (higher priority)
26-27SO75 | 61235943-01 | WAITING (machine busy) |  | CNC3 |  | 19-08-2026 11:42 | 23-08-2026 10:12 | 94.5 | CNC3 busy with 26-27SO117 / 00531569-01 — CNC FIRST SIDE (higher priority)
26-27SO75 | 61235943-01 | WAITING (machine busy) |  | CNC3 |  | 23-08-2026 10:12 | 25-08-2026 08:42 | 46.5 | CNC3 busy with 26-27SO131 / 8010005735 — CNC FIRST SIDE
26-27SO75 | 61235943-01 | WAITING (machine busy) |  | CNC3 |  | 25-08-2026 08:42 | 28-08-2026 18:12 | 81.5 | CNC3 busy with 26-27SO117 / 00531569-01 — CNC SECOND SIDE (higher priority)
26-27SO75 | 61235943-01 | RUNNING | 2. CNC FIRST SIDE | CNC3 | Rohan Chakane → Sidhu Singe → Khansab Mulla | 28-08-2026 18:12 | 31-08-2026 11:42 | 65.5
26-27SO75 | 61235943-01 | RUNNING | 3. VMC FIRST SIDE | VMC2 | Saif → Rupesh Pawar | 30-08-2026 19:12 | 31-08-2026 11:42 | 16.5
26-27SO75 | 61235943-01 | WAITING (machine busy) |  | CNC3 |  | 31-08-2026 11:42 | 01-09-2026 12:42 | 25 | CNC3 busy with 26-27SO98 / 61239701-01 — CNC THIRD SIDE (higher priority)
26-27SO75 | 61235943-01 | RUNNING | 4. CNC SECOND SIDE | CNC3 | Sidhu Singe → Rohan Chakane → Khansab Mulla | 01-09-2026 12:42 | 03-09-2026 03:12 | 38.5
26-27SO75 | 61235943-01 | WAITING (off-hours) |  |  |  | 03-09-2026 03:12 | 04-09-2026 08:00 | 28.8 | Outside working hours (night / weekly off / holiday)
26-27SO75 | 61235943-01 | RUNNING | 5. CHAMFER | DTC2 | Anturam | 04-09-2026 08:00 | 04-09-2026 08:50 | 0.83
26-27SO75 | 61235943-01 | RUNNING | 6. CMM | CMM | Kiran Mohite | 04-09-2026 08:05 | 04-09-2026 10:35 | 2.5
26-27SO75 | 61235943-01 | RUNNING | 7. INSPECTION | MI1 | Nitin Khade | 04-09-2026 08:20 | 04-09-2026 11:40 | 3.33
26-27SO75 | 61235943-01 | RUNNING | 8. PACKING | MPK1 | HP1 | 04-09-2026 10:50 | 04-09-2026 11:40 | 0.83
26-27SO94 | 6003009 | WAITING (off-hours) |  |  |  | 09-08-2026 00:00 | 09-08-2026 08:00 | 8 | Outside working hours (night / weekly off / holiday)
26-27SO94 | 6003009 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO94 | 6003009 | WAITING (off-hours) |  |  |  | 09-08-2026 19:00 | 10-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO94 | 6003009 | WAITING (crew) |  |  |  | 10-08-2026 08:00 | 10-08-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO94 | 6003009 | WAITING (off-hours) |  |  |  | 10-08-2026 19:00 | 11-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO94 | 6003009 | WAITING (crew) |  |  |  | 11-08-2026 08:00 | 11-08-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO94 | 6003009 | WAITING (off-hours) |  |  |  | 11-08-2026 19:00 | 12-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO94 | 6003009 | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO94 | 6003009 | WAITING (off-hours) |  |  |  | 12-08-2026 19:00 | 14-08-2026 08:00 | 37 | Outside working hours (night / weekly off / holiday)
26-27SO94 | 6003009 | WAITING (crew) |  |  |  | 14-08-2026 08:00 | 14-08-2026 13:10 | 5.17 | Machine free — waiting for a free qualified operator
26-27SO94 | 6003009 | WAITING (machine busy) |  | MI1 |  | 14-08-2026 13:10 | 15-08-2026 13:10 | 24 | MI1 busy with 26-27SO113 / 9611416360 — INSP (higher priority)
26-27SO94 | 6003009 | WAITING (machine busy) |  | MI1 |  | 15-08-2026 13:10 | 15-08-2026 17:20 | 4.17 | MI1 busy with 26-27SO144 / 9612358901 — INSPECTION
26-27SO94 | 6003009 | WAITING (crew) |  |  |  | 15-08-2026 17:20 | 15-08-2026 19:00 | 1.66 | Machine free — waiting for a free qualified operator
26-27SO94 | 6003009 | WAITING (off-hours) |  |  |  | 15-08-2026 19:00 | 16-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO94 | 6003009 | WAITING (crew) |  |  |  | 16-08-2026 08:00 | 16-08-2026 09:50 | 1.84 | Machine free — waiting for a free qualified operator
26-27SO94 | 6003009 | WAITING (machine busy) |  | MI1 |  | 16-08-2026 09:50 | 16-08-2026 10:27 | 0.61 | MI1 busy with 26-27SO134 / 9612220710 P — INSPECTION
26-27SO94 | 6003009 | WAITING (machine busy) |  | MI1 |  | 16-08-2026 10:27 | 16-08-2026 14:12 | 3.75 | MI1 busy with 26-27SO68 / 61241992-01 — INSPECTION (higher priority)
26-27SO94 | 6003009 | WAITING (machine busy) |  | MI1 |  | 16-08-2026 14:12 | 17-08-2026 09:52 | 19.67 | MI1 busy with 26-27SO117 / 61240807-01 — INSPECTION
26-27SO94 | 6003009 | WAITING (machine busy) |  | MI1 |  | 17-08-2026 09:52 | 17-08-2026 12:58 | 3.1 | MI1 busy with 26-27SO105 / 9612220703-P — INSPECTION
26-27SO94 | 6003009 | WAITING (machine busy) |  | MI1 |  | 17-08-2026 12:58 | 17-08-2026 16:43 | 3.75 | MI1 busy with 26-27SO104 / 61249522-01 — INSPECTION
26-27SO94 | 6003009 | WAITING (machine busy) |  | MI1 |  | 17-08-2026 16:43 | 18-08-2026 13:53 | 21.17 | MI1 busy with 26-27SO133 / 9611443650 — INSPECTION
26-27SO94 | 6003009 | WAITING (crew) |  |  |  | 18-08-2026 13:53 | 18-08-2026 14:32 | 0.65 | Machine free — waiting for a free qualified operator
26-27SO94 | 6003009 | WAITING (machine busy) |  | MI1 |  | 18-08-2026 14:32 | 18-08-2026 16:12 | 1.67 | MI1 busy with 26-27SO69 / 8010009209 — INSPECTION
26-27SO94 | 6003009 | WAITING (crew) |  |  |  | 18-08-2026 16:12 | 18-08-2026 16:27 | 0.25 | Machine free — waiting for a free qualified operator
26-27SO94 | 6003009 | WAITING (machine busy) |  | MI1 |  | 18-08-2026 16:27 | 19-08-2026 08:47 | 16.33 | MI1 busy with 26-27SO118 / 61239614-01 — INSPECTION
26-27SO94 | 6003009 | WAITING (crew) |  |  |  | 19-08-2026 08:47 | 19-08-2026 10:12 | 1.42 | Machine free — waiting for a free qualified operator
26-27SO94 | 6003009 | WAITING (machine busy) |  | MI1 |  | 19-08-2026 10:12 | 19-08-2026 17:42 | 7.5 | MI1 busy with 26-27SO117 / 61239857-01 — INSPECTION
26-27SO94 | 6003009 | WAITING (crew) |  |  |  | 19-08-2026 17:42 | 19-08-2026 19:00 | 1.3 | Machine free — waiting for a free qualified operator
26-27SO94 | 6003009 | WAITING (off-hours) |  |  |  | 19-08-2026 19:00 | 21-08-2026 08:00 | 37 | Outside working hours (night / weekly off / holiday)
26-27SO94 | 6003009 | RUNNING | 5. INSPECTION | MI1 | Nitin Khade | 21-08-2026 08:00 | 21-08-2026 09:00 | 1
26-27SO94 | 6003009 | RUNNING | 6. WASHING | MW1 | HP1 | 21-08-2026 08:40 | 21-08-2026 09:00 | 0.33
26-27SO94 | 6003009 | RUNNING | 7. PACKING | MPK1 | HP2 | 21-08-2026 08:42 | 21-08-2026 09:02 | 0.33
26-27SO96 | 6003009 | WAITING (off-hours) |  |  |  | 09-08-2026 00:00 | 09-08-2026 08:00 | 8 | Outside working hours (night / weekly off / holiday)
26-27SO96 | 6003009 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO96 | 6003009 | WAITING (off-hours) |  |  |  | 09-08-2026 19:00 | 10-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO96 | 6003009 | WAITING (crew) |  |  |  | 10-08-2026 08:00 | 10-08-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO96 | 6003009 | WAITING (off-hours) |  |  |  | 10-08-2026 19:00 | 11-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO96 | 6003009 | WAITING (crew) |  |  |  | 11-08-2026 08:00 | 11-08-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO96 | 6003009 | WAITING (off-hours) |  |  |  | 11-08-2026 19:00 | 12-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO96 | 6003009 | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO96 | 6003009 | WAITING (off-hours) |  |  |  | 12-08-2026 19:00 | 14-08-2026 08:00 | 37 | Outside working hours (night / weekly off / holiday)
26-27SO96 | 6003009 | WAITING (crew) |  |  |  | 14-08-2026 08:00 | 14-08-2026 13:10 | 5.17 | Machine free — waiting for a free qualified operator
26-27SO96 | 6003009 | WAITING (machine busy) |  | MI1 |  | 14-08-2026 13:10 | 15-08-2026 13:10 | 24 | MI1 busy with 26-27SO113 / 9611416360 — INSP (higher priority)
26-27SO96 | 6003009 | WAITING (machine busy) |  | MI1 |  | 15-08-2026 13:10 | 15-08-2026 17:20 | 4.17 | MI1 busy with 26-27SO144 / 9612358901 — INSPECTION
26-27SO96 | 6003009 | WAITING (crew) |  |  |  | 15-08-2026 17:20 | 15-08-2026 19:00 | 1.66 | Machine free — waiting for a free qualified operator
26-27SO96 | 6003009 | WAITING (off-hours) |  |  |  | 15-08-2026 19:00 | 16-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO96 | 6003009 | WAITING (crew) |  |  |  | 16-08-2026 08:00 | 16-08-2026 09:50 | 1.84 | Machine free — waiting for a free qualified operator
26-27SO96 | 6003009 | WAITING (machine busy) |  | MI1 |  | 16-08-2026 09:50 | 16-08-2026 10:27 | 0.61 | MI1 busy with 26-27SO134 / 9612220710 P — INSPECTION
26-27SO96 | 6003009 | WAITING (machine busy) |  | MI1 |  | 16-08-2026 10:27 | 16-08-2026 14:12 | 3.75 | MI1 busy with 26-27SO68 / 61241992-01 — INSPECTION (higher priority)
26-27SO96 | 6003009 | WAITING (machine busy) |  | MI1 |  | 16-08-2026 14:12 | 17-08-2026 09:52 | 19.67 | MI1 busy with 26-27SO117 / 61240807-01 — INSPECTION
26-27SO96 | 6003009 | WAITING (machine busy) |  | MI1 |  | 17-08-2026 09:52 | 17-08-2026 12:58 | 3.1 | MI1 busy with 26-27SO105 / 9612220703-P — INSPECTION
26-27SO96 | 6003009 | WAITING (machine busy) |  | MI1 |  | 17-08-2026 12:58 | 17-08-2026 16:43 | 3.75 | MI1 busy with 26-27SO104 / 61249522-01 — INSPECTION
26-27SO96 | 6003009 | WAITING (machine busy) |  | MI1 |  | 17-08-2026 16:43 | 18-08-2026 13:53 | 21.17 | MI1 busy with 26-27SO133 / 9611443650 — INSPECTION
26-27SO96 | 6003009 | WAITING (crew) |  |  |  | 18-08-2026 13:53 | 18-08-2026 14:32 | 0.65 | Machine free — waiting for a free qualified operator
26-27SO96 | 6003009 | WAITING (machine busy) |  | MI1 |  | 18-08-2026 14:32 | 18-08-2026 16:12 | 1.67 | MI1 busy with 26-27SO69 / 8010009209 — INSPECTION
26-27SO96 | 6003009 | WAITING (crew) |  |  |  | 18-08-2026 16:12 | 18-08-2026 16:27 | 0.25 | Machine free — waiting for a free qualified operator
26-27SO96 | 6003009 | WAITING (machine busy) |  | MI1 |  | 18-08-2026 16:27 | 19-08-2026 08:47 | 16.33 | MI1 busy with 26-27SO118 / 61239614-01 — INSPECTION
26-27SO96 | 6003009 | WAITING (crew) |  |  |  | 19-08-2026 08:47 | 19-08-2026 10:12 | 1.42 | Machine free — waiting for a free qualified operator
26-27SO96 | 6003009 | WAITING (machine busy) |  | MI1 |  | 19-08-2026 10:12 | 19-08-2026 17:42 | 7.5 | MI1 busy with 26-27SO117 / 61239857-01 — INSPECTION
26-27SO96 | 6003009 | WAITING (crew) |  |  |  | 19-08-2026 17:42 | 19-08-2026 19:00 | 1.3 | Machine free — waiting for a free qualified operator
26-27SO96 | 6003009 | WAITING (off-hours) |  |  |  | 19-08-2026 19:00 | 21-08-2026 08:00 | 37 | Outside working hours (night / weekly off / holiday)
26-27SO96 | 6003009 | RUNNING | 5. INSPECTION | MI1 | Nitin Khade | 21-08-2026 08:00 | 21-08-2026 09:00 | 1
26-27SO96 | 6003009 | RUNNING | 6. WASHING | MW1 | HP1 | 21-08-2026 08:40 | 21-08-2026 09:00 | 0.33
26-27SO96 | 6003009 | RUNNING | 7. PACKING | MPK1 | HP2 | 21-08-2026 08:42 | 21-08-2026 09:02 | 0.33
26-27SO95 | 61248811-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO95 | 61248811-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO95 | 61248811-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 10-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO95 | 61248811-01 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO95 | 61248811-01 | RUNNING | 1. CNC FIRST SIDE | CNC7 | Sidhu Singe | 10-08-2026 08:00 | 10-08-2026 13:30 | 5.5
26-27SO95 | 61248811-01 | RUNNING | 2. CNC SECOND SIDE | CNC7 | Sidhu Singe → Khansab Mulla | 10-08-2026 13:30 | 11-08-2026 03:00 | 13.5
26-27SO95 | 61248811-01 | WAITING (machine busy) |  | VMC1 |  | 11-08-2026 03:00 | 12-08-2026 15:26 | 36.44 | VMC1 busy with 26-27SO113 / 9612193501 — VMC FIRST SIDE (higher priority)
26-27SO95 | 61248811-01 | RUNNING | 3. VMC FIRST SIDE | VMC1 | Ankush Jadhav | 12-08-2026 15:26 | 12-08-2026 18:56 | 3.5
26-27SO95 | 61248811-01 | WAITING (machine busy) |  | DTC2 |  | 12-08-2026 18:56 | 14-08-2026 08:36 | 37.67 | DTC2 busy with 26-27SO113 / 9612193501 — RETAPP (higher priority)
26-27SO95 | 61248811-01 | RUNNING | 4. CHAMFER | DTC2 | Anturam | 14-08-2026 08:36 | 14-08-2026 10:16 | 1.67
26-27SO95 | 61248811-01 | RUNNING | 5. CMM | CMM | Kiran Mohite | 14-08-2026 08:46 | 14-08-2026 11:16 | 2.5
26-27SO95 | 61248811-01 | RUNNING | 6. INSPECTION | MI3 | Sidhanath | 14-08-2026 09:01 | 14-08-2026 11:31 | 2.5
26-27SO95 | 61248811-01 | RUNNING | 7. WASHING | MW2 | HP2 | 14-08-2026 11:21 | 14-08-2026 11:31 | 0.17
26-27SO95 | 61248811-01 | RUNNING | 8. PACKING | MPK1 | Anturam | 14-08-2026 11:22 | 14-08-2026 11:42 | 0.33
26-27SO117 | 00531569-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO117 | 00531569-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO117 | 00531569-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO117 | 00531569-01 | WAITING (machine busy) |  | CNC3 |  | 09-08-2026 14:00 | 10-08-2026 13:48 | 23.8 | CNC3 busy with 26-27SO126 / 971-571126-03 — CNC FORTH SIDE (higher priority)
26-27SO117 | 00531569-01 | WAITING (machine busy) |  | CNC3 |  | 10-08-2026 13:48 | 12-08-2026 19:18 | 53.5 | CNC3 busy with 26-27SO108 / 61240341-80 — CNC SECOND SIDE (higher priority)
26-27SO117 | 00531569-01 | WAITING (machine busy) |  | CNC3 |  | 12-08-2026 19:18 | 14-08-2026 17:48 | 46.5 | CNC3 busy with 26-27SO69 / 8010009209 — CNC SECOND SIDE (higher priority)
26-27SO117 | 00531569-01 | WAITING (machine busy) |  | CNC3 |  | 14-08-2026 17:48 | 16-08-2026 03:30 | 33.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC FIRST SIDE (higher priority)
26-27SO117 | 00531569-01 | WAITING (crew) |  |  |  | 16-08-2026 03:30 | 16-08-2026 05:00 | 1.5 | Machine free — waiting for a free qualified operator
26-27SO117 | 00531569-01 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO117 | 00531569-01 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 08:00 | 16-08-2026 23:54 | 15.9 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC SECOND SIDE (higher priority)
26-27SO117 | 00531569-01 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 23:54 | 17-08-2026 05:00 | 5.1 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC FIRST SIDE (higher priority)
26-27SO117 | 00531569-01 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO117 | 00531569-01 | WAITING (machine busy) |  | CNC3 |  | 17-08-2026 08:00 | 17-08-2026 17:30 | 9.5 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC SECOND SIDE (higher priority)
26-27SO117 | 00531569-01 | WAITING (machine busy) |  | CNC3 |  | 17-08-2026 17:30 | 18-08-2026 14:00 | 20.5 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC THIRD SIDE (higher priority)
26-27SO117 | 00531569-01 | WAITING (machine busy) |  | CNC3 |  | 18-08-2026 14:00 | 19-08-2026 11:42 | 21.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC THIRD SIDE (higher priority)
26-27SO117 | 00531569-01 | RUNNING | 1. CNC FIRST SIDE | CNC3 | Rohan Chakane → Sidhu Singe → Khansab Mulla | 19-08-2026 11:42 | 23-08-2026 10:12 | 94.5
26-27SO117 | 00531569-01 | RUNNING | 2. VMC FIRST SIDE | VMC2 | Swapnil → Ankush Jadhav → Mahesh | 21-08-2026 16:12 | 23-08-2026 13:12 | 45
26-27SO117 | 00531569-01 | WAITING (machine busy) |  | CNC3 |  | 23-08-2026 13:12 | 25-08-2026 08:42 | 43.5 | CNC3 busy with 26-27SO131 / 8010005735 — CNC FIRST SIDE
26-27SO117 | 00531569-01 | RUNNING | 3. CNC SECOND SIDE | CNC3 | Rohan Chakane → Khansab Mulla | 25-08-2026 08:42 | 28-08-2026 18:12 | 81.5
26-27SO117 | 00531569-01 | RUNNING | 4. CNC THIRD SIDE | CNC6 | Sidhu Singe → Khansab Mulla | 26-08-2026 12:52 | 28-08-2026 20:52 | 56
26-27SO117 | 00531569-01 | RUNNING | 5. CHAMFER | DTC2 | Sanjay | 28-08-2026 18:47 | 29-08-2026 09:52 | 15.08
26-27SO117 | 00531569-01 | RUNNING | 6. CMM | CMM | Kiran Mohite | 28-08-2026 18:59 | 29-08-2026 14:14 | 19.25
26-27SO117 | 00531569-01 | RUNNING | 7. INSPECTION | MI1 | Nitin Khade | 29-08-2026 08:00 | 29-08-2026 14:15 | 6.25
26-27SO117 | 00531569-01 | RUNNING | 8. PACKING | MPK1 | HP1 | 29-08-2026 12:10 | 29-08-2026 14:15 | 2.08
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 09-08-2026 14:00 | 10-08-2026 00:00 | 10 | CNC6 busy with 26-27SO130 / 61249330-80 — CNC SECOND SIDE (higher priority)
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 10-08-2026 00:00 | 10-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 10-08-2026 08:00 | 11-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (off-hours) |  |  |  | 11-08-2026 05:00 | 11-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 11-08-2026 08:00 | 12-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (off-hours) |  |  |  | 12-08-2026 05:00 | 12-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 13-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 14-08-2026 08:00 | 15-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (off-hours) |  |  |  | 15-08-2026 05:00 | 15-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 15-08-2026 08:00 | 16-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 16-08-2026 08:00 | 17-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 17-08-2026 08:00 | 18-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (off-hours) |  |  |  | 18-08-2026 05:00 | 18-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 18-08-2026 08:00 | 19-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (off-hours) |  |  |  | 19-08-2026 05:00 | 19-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO93 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 19-08-2026 08:00 | 21-08-2026 09:30 | 49.5 | CNC6 busy with 26-27SO108 / 61240341-80 — CNC THIRD SIDE (higher priority)
26-27SO93 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 21-08-2026 09:30 | 21-08-2026 14:12 | 4.7 | CNC6 busy with 26-27SO132 / 61239819-81 — CNC FORTH SIDE (higher priority)
26-27SO93 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 21-08-2026 14:12 | 23-08-2026 08:42 | 42.5 | CNC6 busy with 26-27SO98 / 61239701-01 — CNC FIRST SIDE (higher priority)
26-27SO93 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 23-08-2026 08:42 | 25-08-2026 09:02 | 48.33 | CNC6 busy with 26-27SO130 / 61249330-80 — CNC THIRD SIDE (higher priority)
26-27SO93 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 25-08-2026 09:02 | 26-08-2026 12:52 | 27.83 | CNC6 busy with 26-27SO130 / 61249330-80 — CNC FORTH SIDE (higher priority)
26-27SO93 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 26-08-2026 12:52 | 28-08-2026 20:52 | 56 | CNC6 busy with 26-27SO117 / 00531569-01 — CNC THIRD SIDE (higher priority)
26-27SO93 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 28-08-2026 20:52 | 30-08-2026 04:22 | 31.5 | CNC6 busy with 26-27SO98 / 61239701-01 — CNC SECOND SIDE (higher priority)
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 30-08-2026 04:22 | 30-08-2026 05:00 | 0.63 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (off-hours) |  |  |  | 30-08-2026 05:00 | 30-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 30-08-2026 08:00 | 31-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (off-hours) |  |  |  | 31-08-2026 05:00 | 31-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 31-08-2026 08:00 | 01-09-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (off-hours) |  |  |  | 01-09-2026 05:00 | 01-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 01-09-2026 08:00 | 02-09-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (off-hours) |  |  |  | 02-09-2026 05:00 | 02-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO93 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 02-09-2026 08:00 | 05-09-2026 17:30 | 81.5 | CNC6 busy with 26-27SO146 / 61240401-01 — CNC FIRST SIDE (higher priority)
26-27SO93 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 05-09-2026 17:30 | 07-09-2026 23:00 | 53.5 | CNC6 busy with 26-27SO146 / 61240401-01 — CNC SECOND SIDE (higher priority)
26-27SO93 | 61249330-80 | RUNNING | 1. CNC FIRST SIDE | CNC6 | Khansab Mulla → Sidhu Singe | 07-09-2026 23:00 | 08-09-2026 22:30 | 23.5
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 08-09-2026 22:30 | 08-09-2026 23:54 | 1.4 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 08-09-2026 23:54 | 09-09-2026 22:24 | 22.5 | CNC6 busy with 26-27SO131 / 8010005735 — CNC THIRD SIDE (higher priority)
26-27SO93 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 09-09-2026 22:24 | 11-09-2026 20:54 | 46.5 | CNC6 busy with 26-27SO131 / 8010005735 — CNC FORTH SIDE (higher priority)
26-27SO93 | 61249330-80 | RUNNING | 2. CNC SECOND SIDE | CNC6 | Khansab Mulla → Sidhu Singe → Rohan Chakane | 11-09-2026 20:54 | 13-09-2026 10:24 | 37.5
26-27SO93 | 61249330-80 | RUNNING | 3. VMC FIRST SIDE | VMC3 | Rupesh Pawar → Saif → Ankush Jadhav → Mahesh | 12-09-2026 08:00 | 15-09-2026 03:30 | 67.5
26-27SO93 | 61249330-80 | WAITING (crew) |  |  |  | 15-09-2026 03:30 | 15-09-2026 05:00 | 1.5 | Machine free — waiting for a free qualified operator
26-27SO93 | 61249330-80 | WAITING (off-hours) |  |  |  | 15-09-2026 05:00 | 15-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO93 | 61249330-80 | RUNNING | 4. VMC SECOND SIDE | VMC3 | Ankush Jadhav → Mahesh → Rupesh Pawar | 15-09-2026 08:00 | 16-09-2026 15:30 | 31.5
26-27SO93 | 61249330-80 | RUNNING | 5. CNC THIRD SIDE | CNC6 | Sidhu Singe → Khansab Mulla → Rohan Chakane | 15-09-2026 18:30 | 18-09-2026 13:00 | 66.5
26-27SO93 | 61249330-80 | RUNNING | 6. CNC FORTH SIDE | CNC6 | Rohan Chakane → Sidhu Singe → Khansab Mulla | 18-09-2026 13:00 | 19-09-2026 19:30 | 30.5
26-27SO93 | 61249330-80 | RUNNING | 7. CHAMFER | DTC2 | Anturam | 19-09-2026 15:30 | 20-09-2026 08:30 | 17
26-27SO93 | 61249330-80 | RUNNING | 8. INSPECTION | MI1 | Nitin Khade | 19-09-2026 15:54 | 20-09-2026 08:54 | 17
26-27SO93 | 61249330-80 | RUNNING | 9. CMM | CMM | Kiran Mohite | 19-09-2026 16:18 | 20-09-2026 11:18 | 19
26-27SO93 | 61249330-80 | RUNNING | 10. WASHING | MW1 | HP1 | 20-09-2026 10:48 | 20-09-2026 11:18 | 0.5
26-27SO128 | 61249396-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO128 | 61249396-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO128 | 61249396-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 10-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO128 | 61249396-01 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO128 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 10-08-2026 08:00 | 10-08-2026 13:30 | 5.5 | CNC7 busy with 26-27SO95 / 61248811-01 — CNC FIRST SIDE (higher priority)
26-27SO128 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 10-08-2026 13:30 | 11-08-2026 03:00 | 13.5 | CNC7 busy with 26-27SO95 / 61248811-01 — CNC SECOND SIDE (higher priority)
26-27SO128 | 61249396-01 | WAITING (crew) |  |  |  | 11-08-2026 03:00 | 11-08-2026 05:00 | 2 | Machine free — waiting for a free qualified operator
26-27SO128 | 61249396-01 | WAITING (off-hours) |  |  |  | 11-08-2026 05:00 | 11-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO128 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 11-08-2026 08:00 | 12-08-2026 12:00 | 28 | CNC7 busy with 26-27SO68 / 61241992-01 — CNC FIRST SIDE (higher priority)
26-27SO128 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 12-08-2026 12:00 | 12-08-2026 15:18 | 3.3 | CNC7 busy with 26-27SO111 / 61241989-01 — CNC FIRST SIDE (higher priority)
26-27SO128 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 12-08-2026 15:18 | 14-08-2026 11:48 | 44.5 | CNC7 busy with 26-27SO104 / 61249522-01 — CNC SECOND SIDE (higher priority)
26-27SO128 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 14-08-2026 11:48 | 14-08-2026 16:54 | 5.1 | CNC7 busy with 26-27SO111 / 61241989-01 — CNC THIRD SIDE (higher priority)
26-27SO128 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 14-08-2026 16:54 | 14-08-2026 21:36 | 4.7 | CNC7 busy with 26-27SO117 / 61240807-01 — CNC FIRST SIDE (higher priority)
26-27SO128 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 14-08-2026 21:36 | 15-08-2026 15:00 | 17.4 | CNC7 busy with 26-27SO68 / 61241992-01 — CNC SECOND SIDE (higher priority)
26-27SO128 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 15-08-2026 15:00 | 16-08-2026 09:42 | 18.7 | CNC7 busy with 26-27SO117 / 61239857-01 — CNC FIRST SIDE (higher priority)
26-27SO128 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 16-08-2026 09:42 | 16-08-2026 14:12 | 4.5 | CNC7 busy with 26-27SO117 / 61239857-01 — CNC SECOND SIDE (higher priority)
26-27SO128 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 16-08-2026 14:12 | 17-08-2026 11:54 | 21.7 | CNC7 busy with 26-27SO117 / 61239857-01 — CNC THIRD SIDE (higher priority)
26-27SO128 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 17-08-2026 11:54 | 18-08-2026 12:24 | 24.5 | CNC7 busy with 26-27SO69 / 8010009209 — CNC THIRD SIDE (higher priority)
26-27SO128 | 61249396-01 | RUNNING | 1. CNC FIRST SIDE | CNC7 | Rohan Chakane → Khansab Mulla | 18-08-2026 12:24 | 19-08-2026 04:42 | 16.3
26-27SO128 | 61249396-01 | WAITING (machine busy) |  | VMC3 |  | 19-08-2026 04:42 | 22-08-2026 04:36 | 71.9 | VMC3 busy with 26-27SO130 / 61249330-80 — VMC FIRST SIDE (higher priority)
26-27SO128 | 61249396-01 | WAITING (crew) |  |  |  | 22-08-2026 04:36 | 22-08-2026 05:00 | 0.4 | Machine free — waiting for a free qualified operator
26-27SO128 | 61249396-01 | WAITING (off-hours) |  |  |  | 22-08-2026 05:00 | 22-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO128 | 61249396-01 | WAITING (machine busy) |  | VMC3 |  | 22-08-2026 08:00 | 23-08-2026 21:00 | 37 | VMC3 busy with 26-27SO130 / 61249330-80 — VMC SECOND SIDE (higher priority)
26-27SO128 | 61249396-01 | WAITING (machine busy) |  | VMC3 |  | 23-08-2026 21:00 | 24-08-2026 12:00 | 15 | VMC3 busy with 26-27SO98 / 61239701-01 — VMC FIRST SIDE (higher priority)
26-27SO128 | 61249396-01 | RUNNING | 2. VMC FIRST SIDE | VMC3 | Rupesh Pawar → Saif | 24-08-2026 12:00 | 25-08-2026 00:42 | 12.7
26-27SO128 | 61249396-01 | WAITING (crew) |  |  |  | 25-08-2026 00:42 | 25-08-2026 05:00 | 4.3 | Machine free — waiting for a free qualified operator
26-27SO128 | 61249396-01 | WAITING (off-hours) |  |  |  | 25-08-2026 05:00 | 25-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO128 | 61249396-01 | WAITING (crew) |  |  |  | 25-08-2026 08:00 | 26-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO128 | 61249396-01 | WAITING (off-hours) |  |  |  | 26-08-2026 05:00 | 26-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO128 | 61249396-01 | WAITING (crew) |  |  |  | 26-08-2026 08:00 | 27-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO128 | 61249396-01 | WAITING (off-hours) |  |  |  | 27-08-2026 05:00 | 28-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO128 | 61249396-01 | WAITING (crew) |  |  |  | 28-08-2026 08:00 | 29-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO128 | 61249396-01 | WAITING (off-hours) |  |  |  | 29-08-2026 05:00 | 29-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO128 | 61249396-01 | RUNNING | 3. CNC SECOND SIDE | CNC7 | Sidhu Singe → Rohan Chakane | 29-08-2026 08:00 | 30-08-2026 13:18 | 29.3
26-27SO128 | 61249396-01 | RUNNING | 4. VMC SECOND SIDE | VMC3 | Rupesh Pawar | 30-08-2026 08:00 | 30-08-2026 13:30 | 5.5
26-27SO128 | 61249396-01 | RUNNING | 5. CHAMFER | DTC2 | Sanjay | 30-08-2026 09:54 | 30-08-2026 14:54 | 5
26-27SO128 | 61249396-01 | RUNNING | 6. CMM | CMM | Kiran Mohite | 30-08-2026 10:24 | 30-08-2026 15:24 | 5
26-27SO128 | 61249396-01 | RUNNING | 7. WASHING | MW1 | HP2 | 30-08-2026 14:44 | 30-08-2026 15:24 | 0.67
26-27SO128 | 61249396-01 | RUNNING | 8. PACKING | MPK1 | HP1 | 30-08-2026 15:13 | 30-08-2026 15:53 | 0.67
26-27SO130 | 61249330-80 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO130 | 61249330-80 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO130 | 61249330-80 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO130 | 61249330-80 | RUNNING | 2. CNC SECOND SIDE | CNC6 | Sidhu Singe → Khansab Mulla | 09-08-2026 14:00 | 10-08-2026 00:00 | 10
26-27SO130 | 61249330-80 | WAITING (crew) |  |  |  | 10-08-2026 00:00 | 10-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO130 | 61249330-80 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO130 | 61249330-80 | WAITING (crew) |  |  |  | 10-08-2026 08:00 | 10-08-2026 18:54 | 10.9 | Machine free — waiting for a free qualified operator
26-27SO130 | 61249330-80 | WAITING (machine busy) |  | VMC3 |  | 10-08-2026 18:54 | 13-08-2026 00:24 | 53.5 | VMC3 busy with 26-27SO108 / 61240341-80 — VMC FIRST SIDE (higher priority)
26-27SO130 | 61249330-80 | WAITING (crew) |  |  |  | 13-08-2026 00:24 | 13-08-2026 05:00 | 4.6 | Machine free — waiting for a free qualified operator
26-27SO130 | 61249330-80 | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO130 | 61249330-80 | WAITING (machine busy) |  | VMC3 |  | 14-08-2026 08:00 | 16-08-2026 15:00 | 55 | VMC3 busy with 26-27SO108 / 61240341-80 — VMC SECOND SIDE (higher priority)
26-27SO130 | 61249330-80 | WAITING (machine busy) |  | VMC3 |  | 16-08-2026 15:00 | 16-08-2026 19:00 | 4 | VMC3 busy with 26-27SO104 / 61249522-01 — VMC SECOND SIDE (higher priority)
26-27SO130 | 61249330-80 | WAITING (crew) |  |  |  | 16-08-2026 19:00 | 17-08-2026 05:00 | 10 | Machine free — waiting for a free qualified operator
26-27SO130 | 61249330-80 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO130 | 61249330-80 | WAITING (crew) |  |  |  | 17-08-2026 08:00 | 17-08-2026 10:18 | 2.3 | Machine free — waiting for a free qualified operator
26-27SO130 | 61249330-80 | WAITING (machine busy) |  | VMC3 |  | 17-08-2026 10:18 | 18-08-2026 01:48 | 15.5 | VMC3 busy with 26-27SO118 / 61239614-01 — VMC FIRST SIDE (higher priority)
26-27SO130 | 61249330-80 | WAITING (crew) |  |  |  | 18-08-2026 01:48 | 18-08-2026 05:00 | 3.2 | Machine free — waiting for a free qualified operator
26-27SO130 | 61249330-80 | WAITING (off-hours) |  |  |  | 18-08-2026 05:00 | 18-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO130 | 61249330-80 | WAITING (machine busy) |  | VMC3 |  | 18-08-2026 08:00 | 18-08-2026 19:06 | 11.1 | VMC3 busy with 26-27SO132 / 61239819-81 — VMC SECOND SIDE (higher priority)
26-27SO130 | 61249330-80 | RUNNING | 3. VMC FIRST SIDE | VMC3 | Saif → Ankush Jadhav → Mahesh | 18-08-2026 19:06 | 22-08-2026 04:36 | 81.5
26-27SO130 | 61249330-80 | WAITING (crew) |  |  |  | 22-08-2026 04:36 | 22-08-2026 05:00 | 0.4 | Machine free — waiting for a free qualified operator
26-27SO130 | 61249330-80 | WAITING (off-hours) |  |  |  | 22-08-2026 05:00 | 22-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO130 | 61249330-80 | RUNNING | 4. VMC SECOND SIDE | VMC3 | Swapnil → Mahesh | 22-08-2026 08:00 | 23-08-2026 21:00 | 37
26-27SO130 | 61249330-80 | RUNNING | 5. CNC THIRD SIDE | CNC6 | Sidhu Singe | 23-08-2026 08:42 | 25-08-2026 09:02 | 48.33
26-27SO130 | 61249330-80 | RUNNING | 6. CNC FORTH SIDE | CNC6 | Sidhu Singe | 25-08-2026 09:02 | 26-08-2026 12:52 | 27.83
26-27SO130 | 61249330-80 | RUNNING | 7. CHAMFER | DTC2 | Anturam | 26-08-2026 09:32 | 26-08-2026 12:52 | 3.33
26-27SO130 | 61249330-80 | RUNNING | 8. INSPECTION | MI1 | Nitin Khade | 26-08-2026 09:52 | 26-08-2026 13:12 | 3.33
26-27SO130 | 61249330-80 | RUNNING | 9. CMM | CMM | Kiran Mohite | 26-08-2026 10:12 | 26-08-2026 15:12 | 5
26-27SO130 | 61249330-80 | RUNNING | 10. WASHING | MW1 | HP1 | 26-08-2026 14:47 | 26-08-2026 15:12 | 0.42
26-27SO69 | 8010009209 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO69 | 8010009209 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO69 | 8010009209 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO69 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 09-08-2026 14:00 | 10-08-2026 13:48 | 23.8 | CNC3 busy with 26-27SO126 / 971-571126-03 — CNC FORTH SIDE (higher priority)
26-27SO69 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 10-08-2026 13:48 | 12-08-2026 19:18 | 53.5 | CNC3 busy with 26-27SO108 / 61240341-80 — CNC SECOND SIDE (higher priority)
26-27SO69 | 8010009209 | RUNNING | 2. CNC SECOND SIDE | CNC3 | Khansab Mulla → Rohan Chakane | 12-08-2026 19:18 | 14-08-2026 17:48 | 46.5
26-27SO69 | 8010009209 | WAITING (machine busy) |  | VMC2 |  | 14-08-2026 17:48 | 14-08-2026 18:07 | 0.32 | VMC2 busy with 26-27SO113 / 9611416360 — VMC FIRST SIDE (higher priority)
26-27SO69 | 8010009209 | WAITING (machine busy) |  | VMC2 |  | 14-08-2026 18:07 | 15-08-2026 04:37 | 10.5 | VMC2 busy with 26-27SO68 / 61241992-01 — VMC FIRST SIDE (higher priority)
26-27SO69 | 8010009209 | WAITING (crew) |  |  |  | 15-08-2026 04:37 | 15-08-2026 05:00 | 0.38 | Machine free — waiting for a free qualified operator
26-27SO69 | 8010009209 | WAITING (off-hours) |  |  |  | 15-08-2026 05:00 | 15-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO69 | 8010009209 | WAITING (machine busy) |  | VMC2 |  | 15-08-2026 08:00 | 15-08-2026 14:00 | 6 | VMC2 busy with 26-27SO104 / 61249522-01 — VMC FIRST SIDE (higher priority)
26-27SO69 | 8010009209 | RUNNING | 3. VMC FIRST SIDE | VMC2 | Rupesh Pawar → Mahesh → Ankush Jadhav | 15-08-2026 14:00 | 16-08-2026 15:10 | 25.17
26-27SO69 | 8010009209 | RUNNING | 4. VMC SECOND SIDE | VMC2 | Ankush Jadhav → Saif | 16-08-2026 15:10 | 17-08-2026 04:40 | 13.5
26-27SO69 | 8010009209 | WAITING (machine busy) |  | CNC7 |  | 17-08-2026 04:40 | 17-08-2026 11:54 | 7.23 | CNC7 busy with 26-27SO117 / 61239857-01 — CNC THIRD SIDE
26-27SO69 | 8010009209 | RUNNING | 5. CNC THIRD SIDE | CNC7 | Rohan Chakane → Khansab Mulla | 17-08-2026 11:54 | 18-08-2026 12:24 | 24.5
26-27SO69 | 8010009209 | RUNNING | 6. DEBURING | MD1 | Anturam | 18-08-2026 11:04 | 18-08-2026 12:24 | 1.33
26-27SO69 | 8010009209 | RUNNING | 7. CMM | CMM | Kiran Mohite | 18-08-2026 11:12 | 18-08-2026 16:12 | 5
26-27SO69 | 8010009209 | RUNNING | 8. INSPECTION | MI1 | Nitin Khade | 18-08-2026 14:32 | 18-08-2026 16:12 | 1.67
26-27SO69 | 8010009209 | RUNNING | 9. WASHING | MW1 | HP2 | 18-08-2026 15:12 | 18-08-2026 16:12 | 1
26-27SO134 | 9612220708 P | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220708 P | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220708 P | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220708 P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220708 P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO134 | 9612220708 P | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220708 P | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220708 P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220708 P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74 | CNC1 busy with 26-27SO120 / 9611443240 — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220708 P | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220708 P | WAITING (machine busy) |  | CNC1 |  | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24 | CNC1 busy with 26-27SO134 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220708 P | WAITING (crew) |  |  |  | 13-08-2026 04:14 | 13-08-2026 05:00 | 0.76 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220708 P | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220708 P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 08:00 | 14-08-2026 17:46 | 9.78 | CNC1 busy with 26-27SO134 / 9612220710 P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220708 P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 17:46 | 16-08-2026 12:47 | 43.01 | CNC1 busy with 26-27SO105 / 9612220703-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220708 P | WAITING (machine busy) |  | CNC1 |  | 16-08-2026 12:47 | 17-08-2026 14:31 | 25.74 | CNC1 busy with 26-27SO134 / 9612220704-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220708 P | WAITING (machine busy) |  | CNC1 |  | 17-08-2026 14:31 | 20-08-2026 01:44 | 59.22 | CNC1 busy with 26-27SO120 / 9611443240 — CNC SECOND SIDE (higher priority)
26-27SO134 | 9612220708 P | WAITING (crew) |  |  |  | 20-08-2026 01:44 | 20-08-2026 05:00 | 3.25 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220708 P | WAITING (off-hours) |  |  |  | 20-08-2026 05:00 | 21-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220708 P | WAITING (machine busy) |  | CNC1 |  | 21-08-2026 08:00 | 22-08-2026 08:06 | 24.1 | CNC1 busy with 26-27SO134 / 9612220705-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220708 P | WAITING (machine busy) |  | CNC1 |  | 22-08-2026 08:06 | 23-08-2026 20:36 | 36.5 | CNC1 busy with 26-27SO139 / 9611443241 — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220708 P | WAITING (machine busy) |  | CNC1 |  | 23-08-2026 20:36 | 26-08-2026 04:26 | 55.83 | CNC1 busy with 26-27SO139 / 9611443241 — CNC SECOND SIDE (higher priority)
26-27SO134 | 9612220708 P | WAITING (crew) |  |  |  | 26-08-2026 04:26 | 26-08-2026 05:00 | 0.56 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220708 P | WAITING (off-hours) |  |  |  | 26-08-2026 05:00 | 26-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220708 P | WAITING (machine busy) |  | CNC1 |  | 26-08-2026 08:00 | 27-08-2026 00:52 | 16.88 | CNC1 busy with 26-27SO137 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220708 P | WAITING (crew) |  |  |  | 27-08-2026 00:52 | 27-08-2026 05:00 | 4.12 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220708 P | WAITING (off-hours) |  |  |  | 27-08-2026 05:00 | 28-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220708 P | WAITING (machine busy) |  | CNC1 |  | 28-08-2026 08:00 | 29-08-2026 12:19 | 28.33 | CNC1 busy with 26-27SO135 / 9612220704-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220708 P | RUNNING | 2. CNC FIRST SIDE | CNC1 | Sandeep Kumar → Anil Kumar | 29-08-2026 12:19 | 29-08-2026 20:15 | 7.93
26-27SO134 | 9612220708 P | WAITING (off-hours) |  |  |  | 29-08-2026 20:15 | 30-08-2026 08:00 | 11.74 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220708 P | WAITING (machine busy) |  | MLATHE |  | 30-08-2026 08:00 | 30-08-2026 15:03 | 7.05 | MLATHE busy with 26-27SO135 / 9612220704-P — DEBURING (higher priority)
26-27SO134 | 9612220708 P | RUNNING | 3. DEBURING | MLATHE | Anturam | 30-08-2026 15:03 | 30-08-2026 17:18 | 2.25
26-27SO134 | 9612220708 P | RUNNING | 4. INSPECTION | MI1 | Nitin Khade | 30-08-2026 16:44 | 30-08-2026 17:18 | 0.56
26-27SO134 | 9612220708 P | RUNNING | 5. PACKING | MPK1 | HP1 | 30-08-2026 16:47 | 30-08-2026 17:21 | 0.56
26-27SO135 | 9612220704-P | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO135 | 9612220704-P | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO135 | 9612220704-P | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO135 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO135 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO135 | 9612220704-P | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO135 | 9612220704-P | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO135 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE (higher priority)
26-27SO135 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74 | CNC1 busy with 26-27SO120 / 9611443240 — CNC FIRST SIDE (higher priority)
26-27SO135 | 9612220704-P | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO135 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24 | CNC1 busy with 26-27SO134 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO135 | 9612220704-P | WAITING (crew) |  |  |  | 13-08-2026 04:14 | 13-08-2026 05:00 | 0.76 | Machine free — waiting for a free qualified operator
26-27SO135 | 9612220704-P | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO135 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 08:00 | 14-08-2026 17:46 | 9.78 | CNC1 busy with 26-27SO134 / 9612220710 P — CNC FIRST SIDE (higher priority)
26-27SO135 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 17:46 | 16-08-2026 12:47 | 43.01 | CNC1 busy with 26-27SO105 / 9612220703-P — CNC FIRST SIDE (higher priority)
26-27SO135 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 16-08-2026 12:47 | 17-08-2026 14:31 | 25.74 | CNC1 busy with 26-27SO134 / 9612220704-P — CNC FIRST SIDE (higher priority)
26-27SO135 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 17-08-2026 14:31 | 20-08-2026 01:44 | 59.22 | CNC1 busy with 26-27SO120 / 9611443240 — CNC SECOND SIDE (higher priority)
26-27SO135 | 9612220704-P | WAITING (crew) |  |  |  | 20-08-2026 01:44 | 20-08-2026 05:00 | 3.25 | Machine free — waiting for a free qualified operator
26-27SO135 | 9612220704-P | WAITING (off-hours) |  |  |  | 20-08-2026 05:00 | 21-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO135 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 21-08-2026 08:00 | 22-08-2026 08:06 | 24.1 | CNC1 busy with 26-27SO134 / 9612220705-P — CNC FIRST SIDE (higher priority)
26-27SO135 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 22-08-2026 08:06 | 23-08-2026 20:36 | 36.5 | CNC1 busy with 26-27SO139 / 9611443241 — CNC FIRST SIDE (higher priority)
26-27SO135 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 23-08-2026 20:36 | 26-08-2026 04:26 | 55.83 | CNC1 busy with 26-27SO139 / 9611443241 — CNC SECOND SIDE (higher priority)
26-27SO135 | 9612220704-P | WAITING (crew) |  |  |  | 26-08-2026 04:26 | 26-08-2026 05:00 | 0.56 | Machine free — waiting for a free qualified operator
26-27SO135 | 9612220704-P | WAITING (off-hours) |  |  |  | 26-08-2026 05:00 | 26-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO135 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 26-08-2026 08:00 | 27-08-2026 00:52 | 16.88 | CNC1 busy with 26-27SO137 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO135 | 9612220704-P | WAITING (crew) |  |  |  | 27-08-2026 00:52 | 27-08-2026 05:00 | 4.12 | Machine free — waiting for a free qualified operator
26-27SO135 | 9612220704-P | WAITING (off-hours) |  |  |  | 27-08-2026 05:00 | 28-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO135 | 9612220704-P | RUNNING | 2. CNC FIRST SIDE | CNC1 | Sandeep Kumar → Anil Kumar | 28-08-2026 08:00 | 29-08-2026 12:19 | 28.33
26-27SO135 | 9612220704-P | WAITING (crew) |  |  |  | 29-08-2026 12:19 | 29-08-2026 19:00 | 6.67 | Machine free — waiting for a free qualified operator
26-27SO135 | 9612220704-P | WAITING (off-hours) |  |  |  | 29-08-2026 19:00 | 30-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO135 | 9612220704-P | RUNNING | 3. DEBURING | MLATHE | Anturam | 30-08-2026 08:00 | 30-08-2026 15:03 | 7.05
26-27SO135 | 9612220704-P | RUNNING | 4. INSPECTION | MI1 | Nitin Khade | 30-08-2026 13:17 | 30-08-2026 15:03 | 1.76
26-27SO135 | 9612220704-P | RUNNING | 5. PACKING | MPK1 | HP1 | 30-08-2026 13:27 | 30-08-2026 15:13 | 1.76
26-27SO136 | 9612220704-P | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO136 | 9612220704-P | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO136 | 9612220704-P | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO136 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO136 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO136 | 9612220704-P | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO136 | 9612220704-P | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO136 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE (higher priority)
26-27SO136 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74 | CNC1 busy with 26-27SO120 / 9611443240 — CNC FIRST SIDE (higher priority)
26-27SO136 | 9612220704-P | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO136 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24 | CNC1 busy with 26-27SO134 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO136 | 9612220704-P | WAITING (crew) |  |  |  | 13-08-2026 04:14 | 13-08-2026 05:00 | 0.76 | Machine free — waiting for a free qualified operator
26-27SO136 | 9612220704-P | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO136 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 08:00 | 14-08-2026 17:46 | 9.78 | CNC1 busy with 26-27SO134 / 9612220710 P — CNC FIRST SIDE (higher priority)
26-27SO136 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 17:46 | 16-08-2026 12:47 | 43.01 | CNC1 busy with 26-27SO105 / 9612220703-P — CNC FIRST SIDE (higher priority)
26-27SO136 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 16-08-2026 12:47 | 17-08-2026 14:31 | 25.74 | CNC1 busy with 26-27SO134 / 9612220704-P — CNC FIRST SIDE (higher priority)
26-27SO136 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 17-08-2026 14:31 | 20-08-2026 01:44 | 59.22 | CNC1 busy with 26-27SO120 / 9611443240 — CNC SECOND SIDE (higher priority)
26-27SO136 | 9612220704-P | WAITING (crew) |  |  |  | 20-08-2026 01:44 | 20-08-2026 05:00 | 3.25 | Machine free — waiting for a free qualified operator
26-27SO136 | 9612220704-P | WAITING (off-hours) |  |  |  | 20-08-2026 05:00 | 21-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO136 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 21-08-2026 08:00 | 22-08-2026 08:06 | 24.1 | CNC1 busy with 26-27SO134 / 9612220705-P — CNC FIRST SIDE (higher priority)
26-27SO136 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 22-08-2026 08:06 | 23-08-2026 20:36 | 36.5 | CNC1 busy with 26-27SO139 / 9611443241 — CNC FIRST SIDE (higher priority)
26-27SO136 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 23-08-2026 20:36 | 26-08-2026 04:26 | 55.83 | CNC1 busy with 26-27SO139 / 9611443241 — CNC SECOND SIDE (higher priority)
26-27SO136 | 9612220704-P | WAITING (crew) |  |  |  | 26-08-2026 04:26 | 26-08-2026 05:00 | 0.56 | Machine free — waiting for a free qualified operator
26-27SO136 | 9612220704-P | WAITING (off-hours) |  |  |  | 26-08-2026 05:00 | 26-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO136 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 26-08-2026 08:00 | 27-08-2026 00:52 | 16.88 | CNC1 busy with 26-27SO137 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO136 | 9612220704-P | WAITING (crew) |  |  |  | 27-08-2026 00:52 | 27-08-2026 05:00 | 4.12 | Machine free — waiting for a free qualified operator
26-27SO136 | 9612220704-P | WAITING (off-hours) |  |  |  | 27-08-2026 05:00 | 28-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO136 | 9612220704-P | RUNNING | 2. CNC FIRST SIDE | CNC1 | Sandeep Kumar → Anil Kumar | 28-08-2026 08:00 | 29-08-2026 12:19 | 28.33
26-27SO136 | 9612220704-P | WAITING (crew) |  |  |  | 29-08-2026 12:19 | 29-08-2026 19:00 | 6.67 | Machine free — waiting for a free qualified operator
26-27SO136 | 9612220704-P | WAITING (off-hours) |  |  |  | 29-08-2026 19:00 | 30-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO136 | 9612220704-P | RUNNING | 3. DEBURING | MLATHE | Anturam | 30-08-2026 08:00 | 30-08-2026 15:03 | 7.05
26-27SO136 | 9612220704-P | RUNNING | 4. INSPECTION | MI1 | Nitin Khade | 30-08-2026 13:17 | 30-08-2026 15:03 | 1.76
26-27SO136 | 9612220704-P | RUNNING | 5. PACKING | MPK1 | HP1 | 30-08-2026 13:27 | 30-08-2026 15:13 | 1.76
26-27SO95 | 8010009209 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO95 | 8010009209 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO95 | 8010009209 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO95 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 09-08-2026 14:00 | 10-08-2026 13:48 | 23.8 | CNC3 busy with 26-27SO126 / 971-571126-03 — CNC FORTH SIDE (higher priority)
26-27SO95 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 10-08-2026 13:48 | 12-08-2026 19:18 | 53.5 | CNC3 busy with 26-27SO108 / 61240341-80 — CNC SECOND SIDE (higher priority)
26-27SO95 | 8010009209 | RUNNING | 2. CNC SECOND SIDE | CNC3 | Khansab Mulla → Rohan Chakane | 12-08-2026 19:18 | 14-08-2026 17:48 | 46.5
26-27SO95 | 8010009209 | WAITING (machine busy) |  | VMC2 |  | 14-08-2026 17:48 | 14-08-2026 18:07 | 0.32 | VMC2 busy with 26-27SO113 / 9611416360 — VMC FIRST SIDE (higher priority)
26-27SO95 | 8010009209 | WAITING (machine busy) |  | VMC2 |  | 14-08-2026 18:07 | 15-08-2026 04:37 | 10.5 | VMC2 busy with 26-27SO68 / 61241992-01 — VMC FIRST SIDE (higher priority)
26-27SO95 | 8010009209 | WAITING (crew) |  |  |  | 15-08-2026 04:37 | 15-08-2026 05:00 | 0.38 | Machine free — waiting for a free qualified operator
26-27SO95 | 8010009209 | WAITING (off-hours) |  |  |  | 15-08-2026 05:00 | 15-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO95 | 8010009209 | WAITING (machine busy) |  | VMC2 |  | 15-08-2026 08:00 | 15-08-2026 14:00 | 6 | VMC2 busy with 26-27SO104 / 61249522-01 — VMC FIRST SIDE (higher priority)
26-27SO95 | 8010009209 | RUNNING | 3. VMC FIRST SIDE | VMC2 | Rupesh Pawar → Mahesh → Ankush Jadhav | 15-08-2026 14:00 | 16-08-2026 15:10 | 25.17
26-27SO95 | 8010009209 | RUNNING | 4. VMC SECOND SIDE | VMC2 | Ankush Jadhav → Saif | 16-08-2026 15:10 | 17-08-2026 04:40 | 13.5
26-27SO95 | 8010009209 | WAITING (machine busy) |  | CNC7 |  | 17-08-2026 04:40 | 17-08-2026 11:54 | 7.23 | CNC7 busy with 26-27SO117 / 61239857-01 — CNC THIRD SIDE
26-27SO95 | 8010009209 | RUNNING | 5. CNC THIRD SIDE | CNC7 | Rohan Chakane → Khansab Mulla | 17-08-2026 11:54 | 18-08-2026 12:24 | 24.5
26-27SO95 | 8010009209 | RUNNING | 6. DEBURING | MD1 | Anturam | 18-08-2026 11:04 | 18-08-2026 12:24 | 1.33
26-27SO95 | 8010009209 | RUNNING | 7. CMM | CMM | Kiran Mohite | 18-08-2026 11:12 | 18-08-2026 16:12 | 5
26-27SO95 | 8010009209 | RUNNING | 8. INSPECTION | MI1 | Nitin Khade | 18-08-2026 14:32 | 18-08-2026 16:12 | 1.67
26-27SO95 | 8010009209 | RUNNING | 9. WASHING | MW1 | HP2 | 18-08-2026 15:12 | 18-08-2026 16:12 | 1
26-27SO139 | 9611443241 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO139 | 9611443241 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO139 | 9611443241 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO139 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO139 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO139 | 9611443241 | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO139 | 9611443241 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO139 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE (higher priority)
26-27SO139 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74 | CNC1 busy with 26-27SO120 / 9611443240 — CNC FIRST SIDE (higher priority)
26-27SO139 | 9611443241 | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO139 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24 | CNC1 busy with 26-27SO134 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO139 | 9611443241 | WAITING (crew) |  |  |  | 13-08-2026 04:14 | 13-08-2026 05:00 | 0.76 | Machine free — waiting for a free qualified operator
26-27SO139 | 9611443241 | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO139 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 08:00 | 14-08-2026 17:46 | 9.78 | CNC1 busy with 26-27SO134 / 9612220710 P — CNC FIRST SIDE (higher priority)
26-27SO139 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 17:46 | 16-08-2026 12:47 | 43.01 | CNC1 busy with 26-27SO105 / 9612220703-P — CNC FIRST SIDE (higher priority)
26-27SO139 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 16-08-2026 12:47 | 17-08-2026 14:31 | 25.74 | CNC1 busy with 26-27SO134 / 9612220704-P — CNC FIRST SIDE (higher priority)
26-27SO139 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 17-08-2026 14:31 | 20-08-2026 01:44 | 59.22 | CNC1 busy with 26-27SO120 / 9611443240 — CNC SECOND SIDE (higher priority)
26-27SO139 | 9611443241 | WAITING (crew) |  |  |  | 20-08-2026 01:44 | 20-08-2026 05:00 | 3.25 | Machine free — waiting for a free qualified operator
26-27SO139 | 9611443241 | WAITING (off-hours) |  |  |  | 20-08-2026 05:00 | 21-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO139 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 21-08-2026 08:00 | 22-08-2026 08:06 | 24.1 | CNC1 busy with 26-27SO134 / 9612220705-P — CNC FIRST SIDE (higher priority)
26-27SO139 | 9611443241 | RUNNING | 1. CNC FIRST SIDE | CNC1 | Sandeep Kumar → Anil Kumar | 22-08-2026 08:06 | 23-08-2026 20:36 | 36.5
26-27SO139 | 9611443241 | RUNNING | 2. CNC SECOND SIDE | CNC1 | Anil Kumar → Sandeep Kumar | 23-08-2026 20:36 | 26-08-2026 04:26 | 55.83
26-27SO139 | 9611443241 | RUNNING | 3. VMC FIRST SIDE | VMC1 | Swapnil → Mahesh → Rupesh Pawar → Saif | 24-08-2026 08:00 | 29-08-2026 18:30 | 130.5
26-27SO139 | 9611443241 | RUNNING | 4. DEBURING | MD1 | Anturam | 28-08-2026 12:50 | 29-08-2026 18:30 | 29.67
26-27SO139 | 9611443241 | RUNNING | 5. CHAMFER | DTC2 | Sanjay | 29-08-2026 10:10 | 29-08-2026 18:30 | 8.33
26-27SO139 | 9611443241 | RUNNING | 6. INSPECTION | MI3 | Sidhanath | 29-08-2026 11:00 | 30-08-2026 08:20 | 21.33
26-27SO139 | 9611443241 | RUNNING | 7. PACKING | MPK1 | HP1 | 30-08-2026 08:00 | 30-08-2026 12:10 | 4.17
26-27SO140 | 9611443241 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO140 | 9611443241 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO140 | 9611443241 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO140 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO140 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO140 | 9611443241 | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO140 | 9611443241 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO140 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE (higher priority)
26-27SO140 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74 | CNC1 busy with 26-27SO120 / 9611443240 — CNC FIRST SIDE (higher priority)
26-27SO140 | 9611443241 | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO140 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24 | CNC1 busy with 26-27SO134 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO140 | 9611443241 | WAITING (crew) |  |  |  | 13-08-2026 04:14 | 13-08-2026 05:00 | 0.76 | Machine free — waiting for a free qualified operator
26-27SO140 | 9611443241 | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO140 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 08:00 | 14-08-2026 17:46 | 9.78 | CNC1 busy with 26-27SO134 / 9612220710 P — CNC FIRST SIDE (higher priority)
26-27SO140 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 17:46 | 16-08-2026 12:47 | 43.01 | CNC1 busy with 26-27SO105 / 9612220703-P — CNC FIRST SIDE (higher priority)
26-27SO140 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 16-08-2026 12:47 | 17-08-2026 14:31 | 25.74 | CNC1 busy with 26-27SO134 / 9612220704-P — CNC FIRST SIDE (higher priority)
26-27SO140 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 17-08-2026 14:31 | 20-08-2026 01:44 | 59.22 | CNC1 busy with 26-27SO120 / 9611443240 — CNC SECOND SIDE (higher priority)
26-27SO140 | 9611443241 | WAITING (crew) |  |  |  | 20-08-2026 01:44 | 20-08-2026 05:00 | 3.25 | Machine free — waiting for a free qualified operator
26-27SO140 | 9611443241 | WAITING (off-hours) |  |  |  | 20-08-2026 05:00 | 21-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO140 | 9611443241 | WAITING (machine busy) |  | CNC1 |  | 21-08-2026 08:00 | 22-08-2026 08:06 | 24.1 | CNC1 busy with 26-27SO134 / 9612220705-P — CNC FIRST SIDE (higher priority)
26-27SO140 | 9611443241 | RUNNING | 1. CNC FIRST SIDE | CNC1 | Sandeep Kumar → Anil Kumar | 22-08-2026 08:06 | 23-08-2026 20:36 | 36.5
26-27SO140 | 9611443241 | RUNNING | 2. CNC SECOND SIDE | CNC1 | Anil Kumar → Sandeep Kumar | 23-08-2026 20:36 | 26-08-2026 04:26 | 55.83
26-27SO140 | 9611443241 | RUNNING | 3. VMC FIRST SIDE | VMC1 | Swapnil → Mahesh → Rupesh Pawar → Saif | 24-08-2026 08:00 | 29-08-2026 18:30 | 130.5
26-27SO140 | 9611443241 | RUNNING | 4. DEBURING | MD1 | Anturam | 28-08-2026 12:50 | 29-08-2026 18:30 | 29.67
26-27SO140 | 9611443241 | RUNNING | 5. CHAMFER | DTC2 | Sanjay | 29-08-2026 10:10 | 29-08-2026 18:30 | 8.33
26-27SO140 | 9611443241 | RUNNING | 6. INSPECTION | MI3 | Sidhanath | 29-08-2026 11:00 | 30-08-2026 08:20 | 21.33
26-27SO140 | 9611443241 | RUNNING | 7. PACKING | MPK1 | HP1 | 30-08-2026 08:00 | 30-08-2026 12:10 | 4.17
26-27SO132 | 61239819-81 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO132 | 61239819-81 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO132 | 61239819-81 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO132 | 61239819-81 | WAITING (machine busy) |  | CNC3 |  | 09-08-2026 14:00 | 10-08-2026 13:48 | 23.8 | CNC3 busy with 26-27SO126 / 971-571126-03 — CNC FORTH SIDE (higher priority)
26-27SO132 | 61239819-81 | WAITING (machine busy) |  | CNC3 |  | 10-08-2026 13:48 | 12-08-2026 19:18 | 53.5 | CNC3 busy with 26-27SO108 / 61240341-80 — CNC SECOND SIDE (higher priority)
26-27SO132 | 61239819-81 | WAITING (machine busy) |  | CNC3 |  | 12-08-2026 19:18 | 14-08-2026 17:48 | 46.5 | CNC3 busy with 26-27SO69 / 8010009209 — CNC SECOND SIDE (higher priority)
26-27SO132 | 61239819-81 | RUNNING | 1. CNC FIRST SIDE | CNC3 | Rohan Chakane → Sidhu Singe → Khansab Mulla | 14-08-2026 17:48 | 16-08-2026 03:30 | 33.7
26-27SO132 | 61239819-81 | WAITING (crew) |  |  |  | 16-08-2026 03:30 | 16-08-2026 05:00 | 1.5 | Machine free — waiting for a free qualified operator
26-27SO132 | 61239819-81 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO132 | 61239819-81 | RUNNING | 2. CNC SECOND SIDE | CNC3 | Sidhu Singe → Khansab Mulla | 16-08-2026 08:00 | 16-08-2026 23:54 | 15.9
26-27SO132 | 61239819-81 | WAITING (machine busy) |  | VMC2 |  | 16-08-2026 23:54 | 17-08-2026 04:40 | 4.77 | VMC2 busy with 26-27SO69 / 8010009209 — VMC SECOND SIDE (higher priority)
26-27SO132 | 61239819-81 | WAITING (crew) |  |  |  | 17-08-2026 04:40 | 17-08-2026 05:00 | 0.33 | Machine free — waiting for a free qualified operator
26-27SO132 | 61239819-81 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO132 | 61239819-81 | RUNNING | 3. VMC FIRST SIDE | VMC2 | Ankush Jadhav → Mahesh | 17-08-2026 08:00 | 18-08-2026 04:42 | 20.7
26-27SO132 | 61239819-81 | WAITING (crew) |  |  |  | 18-08-2026 04:42 | 18-08-2026 05:00 | 0.3 | Machine free — waiting for a free qualified operator
26-27SO132 | 61239819-81 | WAITING (off-hours) |  |  |  | 18-08-2026 05:00 | 18-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO132 | 61239819-81 | RUNNING | 4. VMC SECOND SIDE | VMC3 | Rupesh Pawar → Saif | 18-08-2026 08:00 | 18-08-2026 19:06 | 11.1
26-27SO132 | 61239819-81 | RUNNING | 5. CNC THIRD SIDE | CNC3 | Sidhu Singe → Rohan Chakane | 18-08-2026 14:00 | 19-08-2026 11:42 | 21.7
26-27SO132 | 61239819-81 | WAITING (machine busy) |  | CNC6 |  | 19-08-2026 11:42 | 21-08-2026 09:30 | 45.8 | CNC6 busy with 26-27SO108 / 61240341-80 — CNC THIRD SIDE (higher priority)
26-27SO132 | 61239819-81 | RUNNING | 6. CNC FORTH SIDE | CNC6 | Rohan Chakane | 21-08-2026 09:30 | 21-08-2026 14:12 | 4.7
26-27SO132 | 61239819-81 | RUNNING | 7. INSPECTION | MI1 | Nitin Khade | 21-08-2026 11:19 | 21-08-2026 16:39 | 5.33
26-27SO132 | 61239819-81 | RUNNING | 8. CMM | CMM | Kiran Mohite | 21-08-2026 11:51 | 22-08-2026 08:51 | 21
26-27SO132 | 61239819-81 | RUNNING | 9. WASHING | MW1 | HP1 | 22-08-2026 08:11 | 22-08-2026 08:51 | 0.67
26-27SO132 | 61239819-81 | RUNNING | 10. PACKING | MPK1 | HP2 | 22-08-2026 08:15 | 22-08-2026 08:55 | 0.67
26-27SO104 | 61249522-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO104 | 61249522-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO104 | 61249522-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 10-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO104 | 61249522-01 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO104 | 61249522-01 | WAITING (machine busy) |  | CNC7 |  | 10-08-2026 08:00 | 10-08-2026 13:30 | 5.5 | CNC7 busy with 26-27SO95 / 61248811-01 — CNC FIRST SIDE (higher priority)
26-27SO104 | 61249522-01 | WAITING (machine busy) |  | CNC7 |  | 10-08-2026 13:30 | 11-08-2026 03:00 | 13.5 | CNC7 busy with 26-27SO95 / 61248811-01 — CNC SECOND SIDE (higher priority)
26-27SO104 | 61249522-01 | WAITING (crew) |  |  |  | 11-08-2026 03:00 | 11-08-2026 05:00 | 2 | Machine free — waiting for a free qualified operator
26-27SO104 | 61249522-01 | WAITING (off-hours) |  |  |  | 11-08-2026 05:00 | 11-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO104 | 61249522-01 | WAITING (machine busy) |  | CNC7 |  | 11-08-2026 08:00 | 12-08-2026 12:00 | 28 | CNC7 busy with 26-27SO68 / 61241992-01 — CNC FIRST SIDE (higher priority)
26-27SO104 | 61249522-01 | WAITING (machine busy) |  | CNC7 |  | 12-08-2026 12:00 | 12-08-2026 15:18 | 3.3 | CNC7 busy with 26-27SO111 / 61241989-01 — CNC FIRST SIDE (higher priority)
26-27SO104 | 61249522-01 | RUNNING | 2. CNC SECOND SIDE | CNC7 | Sidhu Singe | 12-08-2026 15:18 | 14-08-2026 11:48 | 44.5
26-27SO104 | 61249522-01 | WAITING (machine busy) |  | VMC2 |  | 14-08-2026 11:48 | 14-08-2026 18:07 | 6.32 | VMC2 busy with 26-27SO113 / 9611416360 — VMC FIRST SIDE (higher priority)
26-27SO104 | 61249522-01 | WAITING (machine busy) |  | VMC2 |  | 14-08-2026 18:07 | 15-08-2026 04:37 | 10.5 | VMC2 busy with 26-27SO68 / 61241992-01 — VMC FIRST SIDE (higher priority)
26-27SO104 | 61249522-01 | WAITING (crew) |  |  |  | 15-08-2026 04:37 | 15-08-2026 05:00 | 0.38 | Machine free — waiting for a free qualified operator
26-27SO104 | 61249522-01 | WAITING (off-hours) |  |  |  | 15-08-2026 05:00 | 15-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO104 | 61249522-01 | RUNNING | 3. VMC FIRST SIDE | VMC2 | Rupesh Pawar | 15-08-2026 08:00 | 15-08-2026 14:00 | 6
26-27SO104 | 61249522-01 | WAITING (machine busy) |  | VMC3 |  | 15-08-2026 14:00 | 16-08-2026 15:00 | 25 | VMC3 busy with 26-27SO108 / 61240341-80 — VMC SECOND SIDE (higher priority)
26-27SO104 | 61249522-01 | RUNNING | 4. VMC SECOND SIDE | VMC3 | Rupesh Pawar | 16-08-2026 15:00 | 16-08-2026 19:00 | 4
26-27SO104 | 61249522-01 | RUNNING | 5. CHAMFER | DTC2 | Sanjay → Anturam | 16-08-2026 16:45 | 17-08-2026 09:30 | 16.75
26-27SO104 | 61249522-01 | RUNNING | 6. CMM | CMM | Kiran Mohite | 16-08-2026 17:07 | 17-08-2026 09:52 | 16.75
26-27SO104 | 61249522-01 | WAITING (machine busy) |  | MI1 |  | 17-08-2026 09:52 | 17-08-2026 12:58 | 3.1 | MI1 busy with 26-27SO105 / 9612220703-P — INSPECTION
26-27SO104 | 61249522-01 | RUNNING | 7. INSPECTION | MI1 | Nitin Khade | 17-08-2026 12:58 | 17-08-2026 16:43 | 3.75
26-27SO104 | 61249522-01 | RUNNING | 8. WASHING | MW1 | HP1 | 17-08-2026 15:28 | 17-08-2026 16:43 | 1.25
26-27SO104 | 61249522-01 | RUNNING | 9. PACKING | MPK2 | HP2 | 17-08-2026 15:35 | 17-08-2026 16:50 | 1.25
26-27SO146 | 61240401-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO146 | 61240401-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO146 | 61240401-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO146 | 61240401-01 | WAITING (machine busy) |  | CNC6 |  | 09-08-2026 14:00 | 10-08-2026 00:00 | 10 | CNC6 busy with 26-27SO130 / 61249330-80 — CNC SECOND SIDE (higher priority)
26-27SO146 | 61240401-01 | WAITING (crew) |  |  |  | 10-08-2026 00:00 | 10-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO146 | 61240401-01 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO146 | 61240401-01 | WAITING (crew) |  |  |  | 10-08-2026 08:00 | 11-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO146 | 61240401-01 | WAITING (off-hours) |  |  |  | 11-08-2026 05:00 | 11-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO146 | 61240401-01 | WAITING (crew) |  |  |  | 11-08-2026 08:00 | 12-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO146 | 61240401-01 | WAITING (off-hours) |  |  |  | 12-08-2026 05:00 | 12-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO146 | 61240401-01 | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 13-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO146 | 61240401-01 | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO146 | 61240401-01 | WAITING (crew) |  |  |  | 14-08-2026 08:00 | 15-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO146 | 61240401-01 | WAITING (off-hours) |  |  |  | 15-08-2026 05:00 | 15-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO146 | 61240401-01 | WAITING (crew) |  |  |  | 15-08-2026 08:00 | 16-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO146 | 61240401-01 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO146 | 61240401-01 | WAITING (crew) |  |  |  | 16-08-2026 08:00 | 17-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO146 | 61240401-01 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO146 | 61240401-01 | WAITING (crew) |  |  |  | 17-08-2026 08:00 | 18-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO146 | 61240401-01 | WAITING (off-hours) |  |  |  | 18-08-2026 05:00 | 18-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO146 | 61240401-01 | WAITING (crew) |  |  |  | 18-08-2026 08:00 | 19-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO146 | 61240401-01 | WAITING (off-hours) |  |  |  | 19-08-2026 05:00 | 19-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO146 | 61240401-01 | WAITING (machine busy) |  | CNC6 |  | 19-08-2026 08:00 | 21-08-2026 09:30 | 49.5 | CNC6 busy with 26-27SO108 / 61240341-80 — CNC THIRD SIDE (higher priority)
26-27SO146 | 61240401-01 | WAITING (machine busy) |  | CNC6 |  | 21-08-2026 09:30 | 21-08-2026 14:12 | 4.7 | CNC6 busy with 26-27SO132 / 61239819-81 — CNC FORTH SIDE (higher priority)
26-27SO146 | 61240401-01 | WAITING (machine busy) |  | CNC6 |  | 21-08-2026 14:12 | 23-08-2026 08:42 | 42.5 | CNC6 busy with 26-27SO98 / 61239701-01 — CNC FIRST SIDE (higher priority)
26-27SO146 | 61240401-01 | WAITING (machine busy) |  | CNC6 |  | 23-08-2026 08:42 | 25-08-2026 09:02 | 48.33 | CNC6 busy with 26-27SO130 / 61249330-80 — CNC THIRD SIDE (higher priority)
26-27SO146 | 61240401-01 | WAITING (machine busy) |  | CNC6 |  | 25-08-2026 09:02 | 26-08-2026 12:52 | 27.83 | CNC6 busy with 26-27SO130 / 61249330-80 — CNC FORTH SIDE (higher priority)
26-27SO146 | 61240401-01 | WAITING (machine busy) |  | CNC6 |  | 26-08-2026 12:52 | 28-08-2026 20:52 | 56 | CNC6 busy with 26-27SO117 / 00531569-01 — CNC THIRD SIDE (higher priority)
26-27SO146 | 61240401-01 | WAITING (machine busy) |  | CNC6 |  | 28-08-2026 20:52 | 30-08-2026 04:22 | 31.5 | CNC6 busy with 26-27SO98 / 61239701-01 — CNC SECOND SIDE (higher priority)
26-27SO146 | 61240401-01 | WAITING (crew) |  |  |  | 30-08-2026 04:22 | 30-08-2026 05:00 | 0.63 | Machine free — waiting for a free qualified operator
26-27SO146 | 61240401-01 | WAITING (off-hours) |  |  |  | 30-08-2026 05:00 | 30-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO146 | 61240401-01 | WAITING (crew) |  |  |  | 30-08-2026 08:00 | 31-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO146 | 61240401-01 | WAITING (off-hours) |  |  |  | 31-08-2026 05:00 | 31-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO146 | 61240401-01 | WAITING (crew) |  |  |  | 31-08-2026 08:00 | 01-09-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO146 | 61240401-01 | WAITING (off-hours) |  |  |  | 01-09-2026 05:00 | 01-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO146 | 61240401-01 | WAITING (crew) |  |  |  | 01-09-2026 08:00 | 02-09-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO146 | 61240401-01 | WAITING (off-hours) |  |  |  | 02-09-2026 05:00 | 02-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO146 | 61240401-01 | RUNNING | 2. CNC FIRST SIDE | CNC6 | Sidhu Singe → Rohan Chakane → Khansab Mulla | 02-09-2026 08:00 | 05-09-2026 17:30 | 81.5
26-27SO146 | 61240401-01 | RUNNING | 3. VMC FIRST SIDE | VMC2 | Saif → Rupesh Pawar | 04-09-2026 22:00 | 05-09-2026 20:30 | 22.5
26-27SO146 | 61240401-01 | RUNNING | 4. CNC SECOND SIDE | CNC6 | Rohan Chakane → Sidhu Singe → Khansab Mulla | 05-09-2026 17:30 | 07-09-2026 23:00 | 53.5
26-27SO146 | 61240401-01 | RUNNING | 5. CHAMFER | DTC2 | Anturam | 07-09-2026 18:00 | 08-09-2026 12:00 | 18
26-27SO146 | 61240401-01 | RUNNING | 6. CMM | CMM | Kiran Mohite | 07-09-2026 18:30 | 08-09-2026 12:30 | 18
26-27SO146 | 61240401-01 | RUNNING | 7. INSPECTION | MI1 | Nitin Khade | 08-09-2026 08:00 | 08-09-2026 14:40 | 6.67
26-27SO146 | 61240401-01 | RUNNING | 8. PACKING | MPK1 | HP1 | 08-09-2026 13:00 | 08-09-2026 14:40 | 1.67
26-27SO126 | 971-571126-03 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO126 | 971-571126-03 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO126 | 971-571126-03 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO126 | 971-571126-03 | RUNNING | 5. CNC FORTH SIDE | CNC3 | Rohan Chakane | 09-08-2026 14:00 | 10-08-2026 13:48 | 23.8
26-27SO126 | 971-571126-03 | RUNNING | 6. CMM | CMM | Kiran Mohite → Nitin Khade | 09-08-2026 16:34 | 10-08-2026 15:34 | 23
26-27SO126 | 971-571126-03 | RUNNING | 7. INSPECTION | MI3 | Sidhanath | 09-08-2026 17:34 | 11-08-2026 18:04 | 48.5
26-27SO126 | 971-571126-03 | RUNNING | 8. WASHING | MW1 | HP1 | 11-08-2026 15:34 | 11-08-2026 18:04 | 2.5
26-27SO126 | 971-571126-03 | RUNNING | 9. PACKING | MPK1 | HP2 | 11-08-2026 15:49 | 11-08-2026 18:19 | 2.5
26-27SO137 | 9612220701-P | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO137 | 9612220701-P | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO137 | 9612220701-P | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO137 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO137 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO137 | 9612220701-P | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO137 | 9612220701-P | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO137 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE (higher priority)
26-27SO137 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74 | CNC1 busy with 26-27SO120 / 9611443240 — CNC FIRST SIDE (higher priority)
26-27SO137 | 9612220701-P | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO137 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24 | CNC1 busy with 26-27SO134 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO137 | 9612220701-P | WAITING (crew) |  |  |  | 13-08-2026 04:14 | 13-08-2026 05:00 | 0.76 | Machine free — waiting for a free qualified operator
26-27SO137 | 9612220701-P | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO137 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 08:00 | 14-08-2026 17:46 | 9.78 | CNC1 busy with 26-27SO134 / 9612220710 P — CNC FIRST SIDE (higher priority)
26-27SO137 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 17:46 | 16-08-2026 12:47 | 43.01 | CNC1 busy with 26-27SO105 / 9612220703-P — CNC FIRST SIDE (higher priority)
26-27SO137 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 16-08-2026 12:47 | 17-08-2026 14:31 | 25.74 | CNC1 busy with 26-27SO134 / 9612220704-P — CNC FIRST SIDE (higher priority)
26-27SO137 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 17-08-2026 14:31 | 20-08-2026 01:44 | 59.22 | CNC1 busy with 26-27SO120 / 9611443240 — CNC SECOND SIDE (higher priority)
26-27SO137 | 9612220701-P | WAITING (crew) |  |  |  | 20-08-2026 01:44 | 20-08-2026 05:00 | 3.25 | Machine free — waiting for a free qualified operator
26-27SO137 | 9612220701-P | WAITING (off-hours) |  |  |  | 20-08-2026 05:00 | 21-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO137 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 21-08-2026 08:00 | 22-08-2026 08:06 | 24.1 | CNC1 busy with 26-27SO134 / 9612220705-P — CNC FIRST SIDE (higher priority)
26-27SO137 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 22-08-2026 08:06 | 23-08-2026 20:36 | 36.5 | CNC1 busy with 26-27SO139 / 9611443241 — CNC FIRST SIDE (higher priority)
26-27SO137 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 23-08-2026 20:36 | 26-08-2026 04:26 | 55.83 | CNC1 busy with 26-27SO139 / 9611443241 — CNC SECOND SIDE (higher priority)
26-27SO137 | 9612220701-P | WAITING (crew) |  |  |  | 26-08-2026 04:26 | 26-08-2026 05:00 | 0.56 | Machine free — waiting for a free qualified operator
26-27SO137 | 9612220701-P | WAITING (off-hours) |  |  |  | 26-08-2026 05:00 | 26-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO137 | 9612220701-P | RUNNING | 2. CNC FIRST SIDE | CNC1 | Sandeep Kumar → Anil Kumar | 26-08-2026 08:00 | 27-08-2026 00:52 | 16.88
26-27SO137 | 9612220701-P | WAITING (off-hours) |  |  |  | 27-08-2026 00:52 | 28-08-2026 08:00 | 31.12 | Outside working hours (night / weekly off / holiday)
26-27SO137 | 9612220701-P | RUNNING | 3. DEBURING | MLATHE | Sanjay | 28-08-2026 08:00 | 28-08-2026 13:38 | 5.63
26-27SO137 | 9612220701-P | RUNNING | 4. INSPECTION | MI1 | Nitin Khade | 28-08-2026 12:13 | 28-08-2026 13:38 | 1.41
26-27SO137 | 9612220701-P | RUNNING | 5. PACKING | MPK1 | HP1 | 28-08-2026 12:21 | 28-08-2026 13:46 | 1.41
26-27SO138 | 9612220701-P | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO138 | 9612220701-P | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO138 | 9612220701-P | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO138 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO138 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO138 | 9612220701-P | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO138 | 9612220701-P | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO138 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE (higher priority)
26-27SO138 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74 | CNC1 busy with 26-27SO120 / 9611443240 — CNC FIRST SIDE (higher priority)
26-27SO138 | 9612220701-P | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO138 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24 | CNC1 busy with 26-27SO134 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO138 | 9612220701-P | WAITING (crew) |  |  |  | 13-08-2026 04:14 | 13-08-2026 05:00 | 0.76 | Machine free — waiting for a free qualified operator
26-27SO138 | 9612220701-P | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO138 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 08:00 | 14-08-2026 17:46 | 9.78 | CNC1 busy with 26-27SO134 / 9612220710 P — CNC FIRST SIDE (higher priority)
26-27SO138 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 17:46 | 16-08-2026 12:47 | 43.01 | CNC1 busy with 26-27SO105 / 9612220703-P — CNC FIRST SIDE (higher priority)
26-27SO138 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 16-08-2026 12:47 | 17-08-2026 14:31 | 25.74 | CNC1 busy with 26-27SO134 / 9612220704-P — CNC FIRST SIDE (higher priority)
26-27SO138 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 17-08-2026 14:31 | 20-08-2026 01:44 | 59.22 | CNC1 busy with 26-27SO120 / 9611443240 — CNC SECOND SIDE (higher priority)
26-27SO138 | 9612220701-P | WAITING (crew) |  |  |  | 20-08-2026 01:44 | 20-08-2026 05:00 | 3.25 | Machine free — waiting for a free qualified operator
26-27SO138 | 9612220701-P | WAITING (off-hours) |  |  |  | 20-08-2026 05:00 | 21-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO138 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 21-08-2026 08:00 | 22-08-2026 08:06 | 24.1 | CNC1 busy with 26-27SO134 / 9612220705-P — CNC FIRST SIDE (higher priority)
26-27SO138 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 22-08-2026 08:06 | 23-08-2026 20:36 | 36.5 | CNC1 busy with 26-27SO139 / 9611443241 — CNC FIRST SIDE (higher priority)
26-27SO138 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 23-08-2026 20:36 | 26-08-2026 04:26 | 55.83 | CNC1 busy with 26-27SO139 / 9611443241 — CNC SECOND SIDE (higher priority)
26-27SO138 | 9612220701-P | WAITING (crew) |  |  |  | 26-08-2026 04:26 | 26-08-2026 05:00 | 0.56 | Machine free — waiting for a free qualified operator
26-27SO138 | 9612220701-P | WAITING (off-hours) |  |  |  | 26-08-2026 05:00 | 26-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO138 | 9612220701-P | RUNNING | 2. CNC FIRST SIDE | CNC1 | Sandeep Kumar → Anil Kumar | 26-08-2026 08:00 | 27-08-2026 00:52 | 16.88
26-27SO138 | 9612220701-P | WAITING (off-hours) |  |  |  | 27-08-2026 00:52 | 28-08-2026 08:00 | 31.12 | Outside working hours (night / weekly off / holiday)
26-27SO138 | 9612220701-P | RUNNING | 3. DEBURING | MLATHE | Sanjay | 28-08-2026 08:00 | 28-08-2026 13:38 | 5.63
26-27SO138 | 9612220701-P | RUNNING | 4. INSPECTION | MI1 | Nitin Khade | 28-08-2026 12:13 | 28-08-2026 13:38 | 1.41
26-27SO138 | 9612220701-P | RUNNING | 5. PACKING | MPK1 | HP1 | 28-08-2026 12:21 | 28-08-2026 13:46 | 1.41
26-27SO120 | 9611443240 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO120 | 9611443240 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO120 | 9611443240 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO120 | 9611443240 | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO120 | 9611443240 | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO120 | 9611443240 | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO120 | 9611443240 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO120 | 9611443240 | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE (higher priority)
26-27SO120 | 9611443240 | RUNNING | 1. CNC FIRST SIDE | CNC1 | Rajiv Kumar → Narayan Fatak → Ankush Jadhav | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74
26-27SO120 | 9611443240 | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO120 | 9611443240 | WAITING (machine busy) |  | CNC1 |  | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24 | CNC1 busy with 26-27SO134 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO120 | 9611443240 | WAITING (crew) |  |  |  | 13-08-2026 04:14 | 13-08-2026 05:00 | 0.76 | Machine free — waiting for a free qualified operator
26-27SO120 | 9611443240 | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO120 | 9611443240 | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 08:00 | 14-08-2026 17:46 | 9.78 | CNC1 busy with 26-27SO134 / 9612220710 P — CNC FIRST SIDE (higher priority)
26-27SO120 | 9611443240 | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 17:46 | 16-08-2026 12:47 | 43.01 | CNC1 busy with 26-27SO105 / 9612220703-P — CNC FIRST SIDE (higher priority)
26-27SO120 | 9611443240 | WAITING (machine busy) |  | CNC1 |  | 16-08-2026 12:47 | 17-08-2026 14:31 | 25.74 | CNC1 busy with 26-27SO134 / 9612220704-P — CNC FIRST SIDE (higher priority)
26-27SO120 | 9611443240 | RUNNING | 2. CNC SECOND SIDE | CNC1 | Sandeep Kumar → Anil Kumar | 17-08-2026 14:31 | 20-08-2026 01:44 | 59.22
26-27SO120 | 9611443240 | RUNNING | 3. VMC FIRST SIDE | VMC1 | Ankush Jadhav → Mahesh → Rupesh Pawar → Saif | 18-08-2026 08:00 | 24-08-2026 01:00 | 137.01
26-27SO120 | 9611443240 | RUNNING | 4. DEBURING | MD1 | Anturam | 22-08-2026 18:10 | 24-08-2026 14:00 | 43.83
26-27SO120 | 9611443240 | RUNNING | 5. CHAMFER | DTC2 | Sanjay | 23-08-2026 16:05 | 24-08-2026 14:00 | 21.92
26-27SO120 | 9611443240 | RUNNING | 6. INSPECTION | MI1 | Nitin Khade | 23-08-2026 16:59 | 24-08-2026 14:54 | 21.92
26-27SO120 | 9611443240 | RUNNING | 7. PACKING | MPK1 | HP1 | 24-08-2026 10:26 | 24-08-2026 14:54 | 4.46
26-27SO122 | 9611443240 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO122 | 9611443240 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO122 | 9611443240 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO122 | 9611443240 | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO122 | 9611443240 | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO122 | 9611443240 | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO122 | 9611443240 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO122 | 9611443240 | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE (higher priority)
26-27SO122 | 9611443240 | RUNNING | 1. CNC FIRST SIDE | CNC1 | Rajiv Kumar → Narayan Fatak → Ankush Jadhav | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74
26-27SO122 | 9611443240 | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO122 | 9611443240 | WAITING (machine busy) |  | CNC1 |  | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24 | CNC1 busy with 26-27SO134 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO122 | 9611443240 | WAITING (crew) |  |  |  | 13-08-2026 04:14 | 13-08-2026 05:00 | 0.76 | Machine free — waiting for a free qualified operator
26-27SO122 | 9611443240 | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO122 | 9611443240 | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 08:00 | 14-08-2026 17:46 | 9.78 | CNC1 busy with 26-27SO134 / 9612220710 P — CNC FIRST SIDE (higher priority)
26-27SO122 | 9611443240 | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 17:46 | 16-08-2026 12:47 | 43.01 | CNC1 busy with 26-27SO105 / 9612220703-P — CNC FIRST SIDE (higher priority)
26-27SO122 | 9611443240 | WAITING (machine busy) |  | CNC1 |  | 16-08-2026 12:47 | 17-08-2026 14:31 | 25.74 | CNC1 busy with 26-27SO134 / 9612220704-P — CNC FIRST SIDE (higher priority)
26-27SO122 | 9611443240 | RUNNING | 2. CNC SECOND SIDE | CNC1 | Sandeep Kumar → Anil Kumar | 17-08-2026 14:31 | 20-08-2026 01:44 | 59.22
26-27SO122 | 9611443240 | RUNNING | 3. VMC FIRST SIDE | VMC1 | Ankush Jadhav → Mahesh → Rupesh Pawar → Saif | 18-08-2026 08:00 | 24-08-2026 01:00 | 137.01
26-27SO122 | 9611443240 | RUNNING | 4. DEBURING | MD1 | Anturam | 22-08-2026 18:10 | 24-08-2026 14:00 | 43.83
26-27SO122 | 9611443240 | RUNNING | 5. CHAMFER | DTC2 | Sanjay | 23-08-2026 16:05 | 24-08-2026 14:00 | 21.92
26-27SO122 | 9611443240 | RUNNING | 6. INSPECTION | MI1 | Nitin Khade | 23-08-2026 16:59 | 24-08-2026 14:54 | 21.92
26-27SO122 | 9611443240 | RUNNING | 7. PACKING | MPK1 | HP1 | 24-08-2026 10:26 | 24-08-2026 14:54 | 4.46
26-27SO111 | 61241989-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO111 | 61241989-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO111 | 61241989-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 10-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO111 | 61241989-01 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO111 | 61241989-01 | WAITING (machine busy) |  | CNC7 |  | 10-08-2026 08:00 | 10-08-2026 13:30 | 5.5 | CNC7 busy with 26-27SO95 / 61248811-01 — CNC FIRST SIDE (higher priority)
26-27SO111 | 61241989-01 | WAITING (machine busy) |  | CNC7 |  | 10-08-2026 13:30 | 11-08-2026 03:00 | 13.5 | CNC7 busy with 26-27SO95 / 61248811-01 — CNC SECOND SIDE (higher priority)
26-27SO111 | 61241989-01 | WAITING (crew) |  |  |  | 11-08-2026 03:00 | 11-08-2026 05:00 | 2 | Machine free — waiting for a free qualified operator
26-27SO111 | 61241989-01 | WAITING (off-hours) |  |  |  | 11-08-2026 05:00 | 11-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO111 | 61241989-01 | WAITING (machine busy) |  | CNC7 |  | 11-08-2026 08:00 | 12-08-2026 12:00 | 28 | CNC7 busy with 26-27SO68 / 61241992-01 — CNC FIRST SIDE (higher priority)
26-27SO111 | 61241989-01 | RUNNING | 1. CNC FIRST SIDE | CNC7 | Sidhu Singe | 12-08-2026 12:00 | 12-08-2026 15:18 | 3.3
26-27SO111 | 61241989-01 | WAITING (machine busy) |  | VMC1 |  | 12-08-2026 15:18 | 12-08-2026 15:26 | 0.14 | VMC1 busy with 26-27SO113 / 9612193501 — VMC FIRST SIDE (higher priority)
26-27SO111 | 61241989-01 | WAITING (machine busy) |  | VMC1 |  | 12-08-2026 15:26 | 12-08-2026 18:56 | 3.5 | VMC1 busy with 26-27SO95 / 61248811-01 — VMC FIRST SIDE (higher priority)
26-27SO111 | 61241989-01 | RUNNING | 2. VMC FIRST SIDE | VMC1 | Ankush Jadhav | 12-08-2026 18:56 | 14-08-2026 15:26 | 44.5
26-27SO111 | 61241989-01 | RUNNING | 3. CNC THIRD SIDE | CNC7 | Sidhu Singe | 14-08-2026 11:48 | 14-08-2026 16:54 | 5.1
26-27SO111 | 61241989-01 | RUNNING | 4. CHAMFER | DTC2 | Sanjay | 14-08-2026 14:24 | 14-08-2026 16:54 | 2.5
26-27SO111 | 61241989-01 | RUNNING | 5. CMM | CMM | Kiran Mohite | 14-08-2026 14:39 | 14-08-2026 18:24 | 3.75
26-27SO111 | 61241989-01 | WAITING (crew) |  |  |  | 14-08-2026 18:24 | 14-08-2026 19:00 | 0.6 | Machine free — waiting for a free qualified operator
26-27SO111 | 61241989-01 | WAITING (off-hours) |  |  |  | 14-08-2026 19:00 | 15-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO111 | 61241989-01 | WAITING (crew) |  |  |  | 15-08-2026 08:00 | 15-08-2026 09:16 | 1.27 | Machine free — waiting for a free qualified operator
26-27SO111 | 61241989-01 | WAITING (machine busy) |  | MI2 |  | 15-08-2026 09:16 | 15-08-2026 10:26 | 1.17 | MI2 busy with 26-27SO134 / 9612220701-P — INSPECTION
26-27SO111 | 61241989-01 | RUNNING | 6. INSPECTION | MI2 | Kiran Mohite | 15-08-2026 10:26 | 15-08-2026 14:11 | 3.75
26-27SO111 | 61241989-01 | RUNNING | 7. WASHING | MW1 | HP1 | 15-08-2026 13:56 | 15-08-2026 14:11 | 0.25
26-27SO111 | 61241989-01 | RUNNING | 8. PACKING | MPK3 | Sanjay | 15-08-2026 13:57 | 15-08-2026 14:12 | 0.25
26-27SO117 | 61239857-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO117 | 61239857-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO117 | 61239857-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 10-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO117 | 61239857-01 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO117 | 61239857-01 | WAITING (machine busy) |  | CNC7 |  | 10-08-2026 08:00 | 10-08-2026 13:30 | 5.5 | CNC7 busy with 26-27SO95 / 61248811-01 — CNC FIRST SIDE (higher priority)
26-27SO117 | 61239857-01 | WAITING (machine busy) |  | CNC7 |  | 10-08-2026 13:30 | 11-08-2026 03:00 | 13.5 | CNC7 busy with 26-27SO95 / 61248811-01 — CNC SECOND SIDE (higher priority)
26-27SO117 | 61239857-01 | WAITING (crew) |  |  |  | 11-08-2026 03:00 | 11-08-2026 05:00 | 2 | Machine free — waiting for a free qualified operator
26-27SO117 | 61239857-01 | WAITING (off-hours) |  |  |  | 11-08-2026 05:00 | 11-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO117 | 61239857-01 | WAITING (machine busy) |  | CNC7 |  | 11-08-2026 08:00 | 12-08-2026 12:00 | 28 | CNC7 busy with 26-27SO68 / 61241992-01 — CNC FIRST SIDE (higher priority)
26-27SO117 | 61239857-01 | WAITING (machine busy) |  | CNC7 |  | 12-08-2026 12:00 | 12-08-2026 15:18 | 3.3 | CNC7 busy with 26-27SO111 / 61241989-01 — CNC FIRST SIDE (higher priority)
26-27SO117 | 61239857-01 | WAITING (machine busy) |  | CNC7 |  | 12-08-2026 15:18 | 14-08-2026 11:48 | 44.5 | CNC7 busy with 26-27SO104 / 61249522-01 — CNC SECOND SIDE (higher priority)
26-27SO117 | 61239857-01 | WAITING (machine busy) |  | CNC7 |  | 14-08-2026 11:48 | 14-08-2026 16:54 | 5.1 | CNC7 busy with 26-27SO111 / 61241989-01 — CNC THIRD SIDE (higher priority)
26-27SO117 | 61239857-01 | WAITING (machine busy) |  | CNC7 |  | 14-08-2026 16:54 | 14-08-2026 21:36 | 4.7 | CNC7 busy with 26-27SO117 / 61240807-01 — CNC FIRST SIDE (higher priority)
26-27SO117 | 61239857-01 | WAITING (machine busy) |  | CNC7 |  | 14-08-2026 21:36 | 15-08-2026 15:00 | 17.4 | CNC7 busy with 26-27SO68 / 61241992-01 — CNC SECOND SIDE (higher priority)
26-27SO117 | 61239857-01 | RUNNING | 1. CNC FIRST SIDE | CNC7 | Rohan Chakane | 15-08-2026 15:00 | 16-08-2026 09:42 | 18.7
26-27SO117 | 61239857-01 | RUNNING | 2. CNC SECOND SIDE | CNC7 | Rohan Chakane | 16-08-2026 09:42 | 16-08-2026 14:12 | 4.5
26-27SO117 | 61239857-01 | RUNNING | 3. VMC FIRST SIDE | VMC1 | Swapnil | 16-08-2026 11:30 | 16-08-2026 19:00 | 7.5
26-27SO117 | 61239857-01 | RUNNING | 4. CNC THIRD SIDE | CNC7 | Rohan Chakane | 16-08-2026 14:12 | 17-08-2026 11:54 | 21.7
26-27SO117 | 61239857-01 | RUNNING | 5. CHAMFER | DTC2 | Anturam | 17-08-2026 09:30 | 17-08-2026 14:30 | 5
26-27SO117 | 61239857-01 | WAITING (crew) |  |  |  | 17-08-2026 14:30 | 17-08-2026 19:00 | 4.5 | Machine free — waiting for a free qualified operator
26-27SO117 | 61239857-01 | WAITING (off-hours) |  |  |  | 17-08-2026 19:00 | 18-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO117 | 61239857-01 | WAITING (crew) |  |  |  | 18-08-2026 08:00 | 18-08-2026 11:12 | 3.2 | Machine free — waiting for a free qualified operator
26-27SO117 | 61239857-01 | WAITING (machine busy) |  | CMM |  | 18-08-2026 11:12 | 18-08-2026 16:12 | 5 | CMM busy with 26-27SO69 / 8010009209 — CMM (higher priority)
26-27SO117 | 61239857-01 | WAITING (machine busy) |  | CMM |  | 18-08-2026 16:12 | 18-08-2026 18:42 | 2.5 | CMM busy with 26-27SO118 / 61239614-01 — CMM (higher priority)
26-27SO117 | 61239857-01 | RUNNING | 6. CMM | CMM | Kiran Mohite | 18-08-2026 18:42 | 19-08-2026 17:42 | 23
26-27SO117 | 61239857-01 | RUNNING | 7. INSPECTION | MI1 | Nitin Khade | 19-08-2026 10:12 | 19-08-2026 17:42 | 7.5
26-27SO117 | 61239857-01 | RUNNING | 8. WASHING | MW1 | HP1 | 19-08-2026 16:42 | 19-08-2026 17:42 | 1
26-27SO117 | 61239857-01 | RUNNING | 9. PACKING | MPK1 | HP2 → HP1 | 19-08-2026 16:48 | 21-08-2026 08:18 | 39.5
26-27SO118 | 61239614-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO118 | 61239614-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO118 | 61239614-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO118 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 09-08-2026 14:00 | 10-08-2026 13:48 | 23.8 | CNC3 busy with 26-27SO126 / 971-571126-03 — CNC FORTH SIDE (higher priority)
26-27SO118 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 10-08-2026 13:48 | 12-08-2026 19:18 | 53.5 | CNC3 busy with 26-27SO108 / 61240341-80 — CNC SECOND SIDE (higher priority)
26-27SO118 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 12-08-2026 19:18 | 14-08-2026 17:48 | 46.5 | CNC3 busy with 26-27SO69 / 8010009209 — CNC SECOND SIDE (higher priority)
26-27SO118 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 14-08-2026 17:48 | 16-08-2026 03:30 | 33.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC FIRST SIDE (higher priority)
26-27SO118 | 61239614-01 | WAITING (crew) |  |  |  | 16-08-2026 03:30 | 16-08-2026 05:00 | 1.5 | Machine free — waiting for a free qualified operator
26-27SO118 | 61239614-01 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO118 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 08:00 | 16-08-2026 23:54 | 15.9 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC SECOND SIDE (higher priority)
26-27SO118 | 61239614-01 | RUNNING | 1. CNC FIRST SIDE | CNC3 | Khansab Mulla | 16-08-2026 23:54 | 17-08-2026 05:00 | 5.1
26-27SO118 | 61239614-01 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO118 | 61239614-01 | RUNNING | 2. CNC SECOND SIDE | CNC3 | Sidhu Singe | 17-08-2026 08:00 | 17-08-2026 17:30 | 9.5
26-27SO118 | 61239614-01 | RUNNING | 3. VMC FIRST SIDE | VMC3 | Rupesh Pawar → Saif | 17-08-2026 10:18 | 18-08-2026 01:48 | 15.5
26-27SO118 | 61239614-01 | RUNNING | 4. CNC THIRD SIDE | CNC3 | Sidhu Singe | 17-08-2026 17:30 | 18-08-2026 14:00 | 20.5
26-27SO118 | 61239614-01 | RUNNING | 5. CHAMFER | DTC2 | Anturam | 18-08-2026 13:10 | 18-08-2026 14:00 | 0.83
26-27SO118 | 61239614-01 | WAITING (machine busy) |  | CMM |  | 18-08-2026 14:00 | 18-08-2026 16:12 | 2.2 | CMM busy with 26-27SO69 / 8010009209 — CMM (higher priority)
26-27SO118 | 61239614-01 | RUNNING | 6. CMM | CMM | Kiran Mohite | 18-08-2026 16:12 | 18-08-2026 18:42 | 2.5
26-27SO118 | 61239614-01 | RUNNING | 7. INSPECTION | MI1 | Nitin Khade | 18-08-2026 16:27 | 19-08-2026 08:47 | 16.33
26-27SO118 | 61239614-01 | WAITING (crew) |  |  |  | 19-08-2026 08:47 | 19-08-2026 16:48 | 8.02 | Machine free — waiting for a free qualified operator
26-27SO118 | 61239614-01 | WAITING (machine busy) |  | MPK1 |  | 19-08-2026 16:48 | 21-08-2026 08:18 | 39.5 | MPK1 busy with 26-27SO117 / 61239857-01 — PACKING
26-27SO118 | 61239614-01 | WAITING (crew) |  |  |  | 21-08-2026 08:18 | 21-08-2026 08:42 | 0.4 | Machine free — waiting for a free qualified operator
26-27SO118 | 61239614-01 | WAITING (machine busy) |  | MPK1 |  | 21-08-2026 08:42 | 21-08-2026 09:02 | 0.33 | MPK1 busy with 26-27SO94 / 6003009 — PACKING (higher priority)
26-27SO118 | 61239614-01 | WAITING (crew) |  |  |  | 21-08-2026 09:02 | 21-08-2026 19:00 | 9.97 | Machine free — waiting for a free qualified operator
26-27SO118 | 61239614-01 | WAITING (off-hours) |  |  |  | 21-08-2026 19:00 | 22-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO118 | 61239614-01 | WAITING (crew) |  |  |  | 22-08-2026 08:00 | 22-08-2026 08:15 | 0.25 | Machine free — waiting for a free qualified operator
26-27SO118 | 61239614-01 | WAITING (machine busy) |  | MPK1 |  | 22-08-2026 08:15 | 22-08-2026 08:55 | 0.67 | MPK1 busy with 26-27SO132 / 61239819-81 — PACKING (higher priority)
26-27SO118 | 61239614-01 | WAITING (crew) |  |  |  | 22-08-2026 08:55 | 22-08-2026 10:59 | 2.08 | Machine free — waiting for a free qualified operator
26-27SO118 | 61239614-01 | WAITING (machine busy) |  | MPK1 |  | 22-08-2026 10:59 | 22-08-2026 11:57 | 0.97 | MPK1 busy with 26-27SO134 / 9612220705-P — PACKING
26-27SO118 | 61239614-01 | WAITING (crew) |  |  |  | 22-08-2026 11:57 | 22-08-2026 19:00 | 7.04 | Machine free — waiting for a free qualified operator
26-27SO118 | 61239614-01 | WAITING (off-hours) |  |  |  | 22-08-2026 19:00 | 23-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO118 | 61239614-01 | WAITING (crew) |  |  |  | 23-08-2026 08:00 | 23-08-2026 13:37 | 5.62 | Machine free — waiting for a free qualified operator
26-27SO118 | 61239614-01 | WAITING (machine busy) |  | MPK1 |  | 23-08-2026 13:37 | 23-08-2026 14:52 | 1.25 | MPK1 busy with 26-27SO108 / 61240341-80 — PACKING (higher priority)
26-27SO118 | 61239614-01 | WAITING (crew) |  |  |  | 23-08-2026 14:52 | 23-08-2026 19:00 | 4.12 | Machine free — waiting for a free qualified operator
26-27SO118 | 61239614-01 | WAITING (off-hours) |  |  |  | 23-08-2026 19:00 | 24-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO118 | 61239614-01 | WAITING (crew) |  |  |  | 24-08-2026 08:00 | 24-08-2026 10:26 | 2.44 | Machine free — waiting for a free qualified operator
26-27SO118 | 61239614-01 | WAITING (machine busy) |  | MPK1 |  | 24-08-2026 10:26 | 24-08-2026 14:54 | 4.46 | MPK1 busy with 26-27SO120 / 9611443240 — PACKING
26-27SO118 | 61239614-01 | WAITING (crew) |  |  |  | 24-08-2026 14:54 | 24-08-2026 19:00 | 4.1 | Machine free — waiting for a free qualified operator
26-27SO118 | 61239614-01 | WAITING (off-hours) |  |  |  | 24-08-2026 19:00 | 25-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO118 | 61239614-01 | WAITING (crew) |  |  |  | 25-08-2026 08:00 | 25-08-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO118 | 61239614-01 | WAITING (off-hours) |  |  |  | 25-08-2026 19:00 | 26-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO118 | 61239614-01 | WAITING (crew) |  |  |  | 26-08-2026 08:00 | 26-08-2026 08:47 | 0.78 | Machine free — waiting for a free qualified operator
26-27SO118 | 61239614-01 | RUNNING | 9. PACKING | MPK1 | HP1 | 26-08-2026 08:47 | 26-08-2026 08:57 | 0.17
26-27SO134 | 9612220705-P | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220705-P | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220705-P | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO134 | 9612220705-P | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220705-P | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74 | CNC1 busy with 26-27SO120 / 9611443240 — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220705-P | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24 | CNC1 busy with 26-27SO134 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220705-P | WAITING (crew) |  |  |  | 13-08-2026 04:14 | 13-08-2026 05:00 | 0.76 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220705-P | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 08:00 | 14-08-2026 17:46 | 9.78 | CNC1 busy with 26-27SO134 / 9612220710 P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 17:46 | 16-08-2026 12:47 | 43.01 | CNC1 busy with 26-27SO105 / 9612220703-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 16-08-2026 12:47 | 17-08-2026 14:31 | 25.74 | CNC1 busy with 26-27SO134 / 9612220704-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 17-08-2026 14:31 | 20-08-2026 01:44 | 59.22 | CNC1 busy with 26-27SO120 / 9611443240 — CNC SECOND SIDE (higher priority)
26-27SO134 | 9612220705-P | WAITING (crew) |  |  |  | 20-08-2026 01:44 | 20-08-2026 05:00 | 3.25 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220705-P | WAITING (off-hours) |  |  |  | 20-08-2026 05:00 | 21-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220705-P | RUNNING | 2. CNC FIRST SIDE | CNC1 | Sandeep Kumar → Anil Kumar | 21-08-2026 08:00 | 22-08-2026 08:06 | 24.1
26-27SO134 | 9612220705-P | RUNNING | 3. DEBURING | MLATHE | Anturam | 22-08-2026 08:00 | 22-08-2026 11:52 | 3.87
26-27SO134 | 9612220705-P | RUNNING | 4. INSPECTION | MI1 | Nitin Khade | 22-08-2026 10:54 | 22-08-2026 11:52 | 0.97
26-27SO134 | 9612220705-P | RUNNING | 5. PACKING | MPK1 | HP2 | 22-08-2026 10:59 | 22-08-2026 11:57 | 0.97
26-27SO149 | 9611443651 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO149 | 9611443651 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO149 | 9611443651 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 18:50 | 10.84 | Machine free — waiting for a free qualified operator
26-27SO149 | 9611443651 | WAITING (machine busy) |  | CNC4 |  | 09-08-2026 18:50 | 11-08-2026 16:19 | 45.48 | CNC4 busy with 26-27SO113 / 9612193501 — CNC SECOND SIDE (higher priority)
26-27SO149 | 9611443651 | WAITING (machine busy) |  | CNC4 |  | 11-08-2026 16:19 | 12-08-2026 22:22 | 30.06 | CNC4 busy with 26-27SO113 / 9611416360 — CNC SECOND SIDE (higher priority)
26-27SO149 | 9611443651 | RUNNING | 1. CNC FIRST SIDE | CNC4 | Anil Kumar → Rajiv Kumar | 12-08-2026 22:22 | 14-08-2026 16:52 | 42.5
26-27SO149 | 9611443651 | WAITING (crew) |  |  |  | 14-08-2026 16:52 | 14-08-2026 21:07 | 4.24 | Machine free — waiting for a free qualified operator
26-27SO149 | 9611443651 | WAITING (machine busy) |  | CNC4 |  | 14-08-2026 21:07 | 15-08-2026 01:49 | 4.7 | CNC4 busy with 26-27SO117 / 61240807-01 — CNC SECOND SIDE (higher priority)
26-27SO149 | 9611443651 | WAITING (crew) |  |  |  | 15-08-2026 01:49 | 15-08-2026 05:00 | 3.18 | Machine free — waiting for a free qualified operator
26-27SO149 | 9611443651 | WAITING (off-hours) |  |  |  | 15-08-2026 05:00 | 15-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO149 | 9611443651 | RUNNING | 2. CNC SECOND SIDE | CNC4 | Swapnil → Narayan Fatak | 15-08-2026 08:00 | 16-08-2026 02:00 | 18
26-27SO149 | 9611443651 | WAITING (crew) |  |  |  | 16-08-2026 02:00 | 16-08-2026 05:00 | 3 | Machine free — waiting for a free qualified operator
26-27SO149 | 9611443651 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO149 | 9611443651 | WAITING (crew) |  |  |  | 16-08-2026 08:00 | 16-08-2026 11:30 | 3.5 | Machine free — waiting for a free qualified operator
26-27SO149 | 9611443651 | WAITING (machine busy) |  | VMC1 |  | 16-08-2026 11:30 | 16-08-2026 19:00 | 7.5 | VMC1 busy with 26-27SO117 / 61239857-01 — VMC FIRST SIDE (higher priority)
26-27SO149 | 9611443651 | WAITING (crew) |  |  |  | 16-08-2026 19:00 | 17-08-2026 05:00 | 10 | Machine free — waiting for a free qualified operator
26-27SO149 | 9611443651 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO149 | 9611443651 | WAITING (crew) |  |  |  | 17-08-2026 08:00 | 18-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO149 | 9611443651 | WAITING (off-hours) |  |  |  | 18-08-2026 05:00 | 18-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO149 | 9611443651 | WAITING (machine busy) |  | VMC1 |  | 18-08-2026 08:00 | 24-08-2026 01:00 | 137.01 | VMC1 busy with 26-27SO120 / 9611443240 — VMC FIRST SIDE (higher priority)
26-27SO149 | 9611443651 | WAITING (crew) |  |  |  | 24-08-2026 01:00 | 24-08-2026 05:00 | 3.99 | Machine free — waiting for a free qualified operator
26-27SO149 | 9611443651 | WAITING (off-hours) |  |  |  | 24-08-2026 05:00 | 24-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO149 | 9611443651 | WAITING (machine busy) |  | VMC1 |  | 24-08-2026 08:00 | 29-08-2026 18:30 | 130.5 | VMC1 busy with 26-27SO139 / 9611443241 — VMC FIRST SIDE (higher priority)
26-27SO149 | 9611443651 | RUNNING | 3. VMC FIRST SIDE | VMC1 | Rupesh Pawar → Saif → Ankush Jadhav → Mahesh | 29-08-2026 18:30 | 31-08-2026 09:00 | 38.5
26-27SO149 | 9611443651 | RUNNING | 4. DEBURING | MD1 | Sanjay | 31-08-2026 08:00 | 31-08-2026 13:00 | 5
26-27SO149 | 9611443651 | WAITING (crew) |  |  |  | 31-08-2026 13:00 | 31-08-2026 19:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO149 | 9611443651 | WAITING (off-hours) |  |  |  | 31-08-2026 19:00 | 01-09-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO149 | 9611443651 | WAITING (crew) |  |  |  | 01-09-2026 08:00 | 01-09-2026 11:27 | 3.45 | Machine free — waiting for a free qualified operator
26-27SO149 | 9611443651 | WAITING (machine busy) |  | DTC2 |  | 01-09-2026 11:27 | 01-09-2026 12:42 | 1.25 | DTC2 busy with 26-27SO98 / 61239701-01 — CHAMFER (higher priority)
26-27SO149 | 9611443651 | RUNNING | 5. CHAMFER | DTC2 | Anturam | 01-09-2026 12:42 | 01-09-2026 17:42 | 5
26-27SO149 | 9611443651 | RUNNING | 6. INSPECTION | MI3 | Sidhanath | 01-09-2026 13:12 | 01-09-2026 18:12 | 5
26-27SO149 | 9611443651 | RUNNING | 7. PACKING | MPK1 | HP1 | 01-09-2026 15:42 | 01-09-2026 18:12 | 2.5
26-27SO150 | 9611443651 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO150 | 9611443651 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO150 | 9611443651 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 18:50 | 10.84 | Machine free — waiting for a free qualified operator
26-27SO150 | 9611443651 | WAITING (machine busy) |  | CNC4 |  | 09-08-2026 18:50 | 11-08-2026 16:19 | 45.48 | CNC4 busy with 26-27SO113 / 9612193501 — CNC SECOND SIDE (higher priority)
26-27SO150 | 9611443651 | WAITING (machine busy) |  | CNC4 |  | 11-08-2026 16:19 | 12-08-2026 22:22 | 30.06 | CNC4 busy with 26-27SO113 / 9611416360 — CNC SECOND SIDE (higher priority)
26-27SO150 | 9611443651 | RUNNING | 1. CNC FIRST SIDE | CNC4 | Anil Kumar → Rajiv Kumar | 12-08-2026 22:22 | 14-08-2026 16:52 | 42.5
26-27SO150 | 9611443651 | WAITING (crew) |  |  |  | 14-08-2026 16:52 | 14-08-2026 21:07 | 4.24 | Machine free — waiting for a free qualified operator
26-27SO150 | 9611443651 | WAITING (machine busy) |  | CNC4 |  | 14-08-2026 21:07 | 15-08-2026 01:49 | 4.7 | CNC4 busy with 26-27SO117 / 61240807-01 — CNC SECOND SIDE (higher priority)
26-27SO150 | 9611443651 | WAITING (crew) |  |  |  | 15-08-2026 01:49 | 15-08-2026 05:00 | 3.18 | Machine free — waiting for a free qualified operator
26-27SO150 | 9611443651 | WAITING (off-hours) |  |  |  | 15-08-2026 05:00 | 15-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO150 | 9611443651 | RUNNING | 2. CNC SECOND SIDE | CNC4 | Swapnil → Narayan Fatak | 15-08-2026 08:00 | 16-08-2026 02:00 | 18
26-27SO150 | 9611443651 | WAITING (crew) |  |  |  | 16-08-2026 02:00 | 16-08-2026 05:00 | 3 | Machine free — waiting for a free qualified operator
26-27SO150 | 9611443651 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO150 | 9611443651 | WAITING (crew) |  |  |  | 16-08-2026 08:00 | 16-08-2026 11:30 | 3.5 | Machine free — waiting for a free qualified operator
26-27SO150 | 9611443651 | WAITING (machine busy) |  | VMC1 |  | 16-08-2026 11:30 | 16-08-2026 19:00 | 7.5 | VMC1 busy with 26-27SO117 / 61239857-01 — VMC FIRST SIDE (higher priority)
26-27SO150 | 9611443651 | WAITING (crew) |  |  |  | 16-08-2026 19:00 | 17-08-2026 05:00 | 10 | Machine free — waiting for a free qualified operator
26-27SO150 | 9611443651 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO150 | 9611443651 | WAITING (crew) |  |  |  | 17-08-2026 08:00 | 18-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO150 | 9611443651 | WAITING (off-hours) |  |  |  | 18-08-2026 05:00 | 18-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO150 | 9611443651 | WAITING (machine busy) |  | VMC1 |  | 18-08-2026 08:00 | 24-08-2026 01:00 | 137.01 | VMC1 busy with 26-27SO120 / 9611443240 — VMC FIRST SIDE (higher priority)
26-27SO150 | 9611443651 | WAITING (crew) |  |  |  | 24-08-2026 01:00 | 24-08-2026 05:00 | 3.99 | Machine free — waiting for a free qualified operator
26-27SO150 | 9611443651 | WAITING (off-hours) |  |  |  | 24-08-2026 05:00 | 24-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO150 | 9611443651 | WAITING (machine busy) |  | VMC1 |  | 24-08-2026 08:00 | 29-08-2026 18:30 | 130.5 | VMC1 busy with 26-27SO139 / 9611443241 — VMC FIRST SIDE (higher priority)
26-27SO150 | 9611443651 | RUNNING | 3. VMC FIRST SIDE | VMC1 | Rupesh Pawar → Saif → Ankush Jadhav → Mahesh | 29-08-2026 18:30 | 31-08-2026 09:00 | 38.5
26-27SO150 | 9611443651 | RUNNING | 4. DEBURING | MD1 | Sanjay | 31-08-2026 08:00 | 31-08-2026 13:00 | 5
26-27SO150 | 9611443651 | WAITING (crew) |  |  |  | 31-08-2026 13:00 | 31-08-2026 19:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO150 | 9611443651 | WAITING (off-hours) |  |  |  | 31-08-2026 19:00 | 01-09-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO150 | 9611443651 | WAITING (crew) |  |  |  | 01-09-2026 08:00 | 01-09-2026 11:27 | 3.45 | Machine free — waiting for a free qualified operator
26-27SO150 | 9611443651 | WAITING (machine busy) |  | DTC2 |  | 01-09-2026 11:27 | 01-09-2026 12:42 | 1.25 | DTC2 busy with 26-27SO98 / 61239701-01 — CHAMFER (higher priority)
26-27SO150 | 9611443651 | RUNNING | 5. CHAMFER | DTC2 | Anturam | 01-09-2026 12:42 | 01-09-2026 17:42 | 5
26-27SO150 | 9611443651 | RUNNING | 6. INSPECTION | MI3 | Sidhanath | 01-09-2026 13:12 | 01-09-2026 18:12 | 5
26-27SO150 | 9611443651 | RUNNING | 7. PACKING | MPK1 | HP1 | 01-09-2026 15:42 | 01-09-2026 18:12 | 2.5
26-27SO105 | 9612220703-P | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO105 | 9612220703-P | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO105 | 9612220703-P | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO105 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO105 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO105 | 9612220703-P | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO105 | 9612220703-P | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO105 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE (higher priority)
26-27SO105 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74 | CNC1 busy with 26-27SO120 / 9611443240 — CNC FIRST SIDE
26-27SO105 | 9612220703-P | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO105 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24 | CNC1 busy with 26-27SO134 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO105 | 9612220703-P | WAITING (crew) |  |  |  | 13-08-2026 04:14 | 13-08-2026 05:00 | 0.76 | Machine free — waiting for a free qualified operator
26-27SO105 | 9612220703-P | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO105 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 08:00 | 14-08-2026 17:46 | 9.78 | CNC1 busy with 26-27SO134 / 9612220710 P — CNC FIRST SIDE (higher priority)
26-27SO105 | 9612220703-P | RUNNING | 2. CNC FIRST SIDE | CNC1 | Sandeep Kumar → Anil Kumar | 14-08-2026 17:46 | 16-08-2026 12:47 | 43.01
26-27SO105 | 9612220703-P | RUNNING | 3. DEBURING | MLATHE | Anturam → Sanjay | 16-08-2026 10:27 | 17-08-2026 11:52 | 25.42
26-27SO105 | 9612220703-P | RUNNING | 4. INSPECTION | MI1 | Nitin Khade | 17-08-2026 09:52 | 17-08-2026 12:58 | 3.1
26-27SO105 | 9612220703-P | RUNNING | 5. PACKING | MPK2 | HP2 | 17-08-2026 10:10 | 17-08-2026 13:16 | 3.1
26-27SO134 | 9612220703-P | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220703-P | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220703-P | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO134 | 9612220703-P | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220703-P | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74 | CNC1 busy with 26-27SO120 / 9611443240 — CNC FIRST SIDE
26-27SO134 | 9612220703-P | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24 | CNC1 busy with 26-27SO134 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220703-P | WAITING (crew) |  |  |  | 13-08-2026 04:14 | 13-08-2026 05:00 | 0.76 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220703-P | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 08:00 | 14-08-2026 17:46 | 9.78 | CNC1 busy with 26-27SO134 / 9612220710 P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220703-P | RUNNING | 2. CNC FIRST SIDE | CNC1 | Sandeep Kumar → Anil Kumar | 14-08-2026 17:46 | 16-08-2026 12:47 | 43.01
26-27SO134 | 9612220703-P | RUNNING | 3. DEBURING | MLATHE | Anturam → Sanjay | 16-08-2026 10:27 | 17-08-2026 11:52 | 25.42
26-27SO134 | 9612220703-P | RUNNING | 4. INSPECTION | MI1 | Nitin Khade | 17-08-2026 09:52 | 17-08-2026 12:58 | 3.1
26-27SO134 | 9612220703-P | RUNNING | 5. PACKING | MPK2 | HP2 | 17-08-2026 10:10 | 17-08-2026 13:16 | 3.1
26-27SO134 | 9612220704-P | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220704-P | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220704-P | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO134 | 9612220704-P | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220704-P | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74 | CNC1 busy with 26-27SO120 / 9611443240 — CNC FIRST SIDE
26-27SO134 | 9612220704-P | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24 | CNC1 busy with 26-27SO134 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220704-P | WAITING (crew) |  |  |  | 13-08-2026 04:14 | 13-08-2026 05:00 | 0.76 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220704-P | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 08:00 | 14-08-2026 17:46 | 9.78 | CNC1 busy with 26-27SO134 / 9612220710 P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220704-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 17:46 | 16-08-2026 12:47 | 43.01 | CNC1 busy with 26-27SO105 / 9612220703-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220704-P | RUNNING | 2. CNC FIRST SIDE | CNC1 | Sandeep Kumar → Anil Kumar | 16-08-2026 12:47 | 17-08-2026 14:31 | 25.74
26-27SO134 | 9612220704-P | RUNNING | 3. DEBURING | MLATHE | Sanjay | 17-08-2026 11:52 | 17-08-2026 18:09 | 6.28
26-27SO134 | 9612220704-P | RUNNING | 4. INSPECTION | MI2 | Kiran Mohite | 17-08-2026 16:34 | 17-08-2026 18:09 | 1.57
26-27SO134 | 9612220704-P | RUNNING | 5. PACKING | MPK3 | HP1 | 17-08-2026 16:44 | 17-08-2026 18:18 | 1.57
26-27SO148 | 9612220703-P | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO148 | 9612220703-P | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO148 | 9612220703-P | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO148 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO148 | 9612220703-P | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO148 | 9612220703-P | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO148 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74 | CNC1 busy with 26-27SO120 / 9611443240 — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220703-P | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO148 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24 | CNC1 busy with 26-27SO134 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220703-P | WAITING (crew) |  |  |  | 13-08-2026 04:14 | 13-08-2026 05:00 | 0.76 | Machine free — waiting for a free qualified operator
26-27SO148 | 9612220703-P | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO148 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 08:00 | 14-08-2026 17:46 | 9.78 | CNC1 busy with 26-27SO134 / 9612220710 P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 17:46 | 16-08-2026 12:47 | 43.01 | CNC1 busy with 26-27SO105 / 9612220703-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 16-08-2026 12:47 | 17-08-2026 14:31 | 25.74 | CNC1 busy with 26-27SO134 / 9612220704-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 17-08-2026 14:31 | 20-08-2026 01:44 | 59.22 | CNC1 busy with 26-27SO120 / 9611443240 — CNC SECOND SIDE (higher priority)
26-27SO148 | 9612220703-P | WAITING (crew) |  |  |  | 20-08-2026 01:44 | 20-08-2026 05:00 | 3.25 | Machine free — waiting for a free qualified operator
26-27SO148 | 9612220703-P | WAITING (off-hours) |  |  |  | 20-08-2026 05:00 | 21-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO148 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 21-08-2026 08:00 | 22-08-2026 08:06 | 24.1 | CNC1 busy with 26-27SO134 / 9612220705-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 22-08-2026 08:06 | 23-08-2026 20:36 | 36.5 | CNC1 busy with 26-27SO139 / 9611443241 — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 23-08-2026 20:36 | 26-08-2026 04:26 | 55.83 | CNC1 busy with 26-27SO139 / 9611443241 — CNC SECOND SIDE (higher priority)
26-27SO148 | 9612220703-P | WAITING (crew) |  |  |  | 26-08-2026 04:26 | 26-08-2026 05:00 | 0.56 | Machine free — waiting for a free qualified operator
26-27SO148 | 9612220703-P | WAITING (off-hours) |  |  |  | 26-08-2026 05:00 | 26-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO148 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 26-08-2026 08:00 | 27-08-2026 00:52 | 16.88 | CNC1 busy with 26-27SO137 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220703-P | WAITING (crew) |  |  |  | 27-08-2026 00:52 | 27-08-2026 05:00 | 4.12 | Machine free — waiting for a free qualified operator
26-27SO148 | 9612220703-P | WAITING (off-hours) |  |  |  | 27-08-2026 05:00 | 28-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO148 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 28-08-2026 08:00 | 29-08-2026 12:19 | 28.33 | CNC1 busy with 26-27SO135 / 9612220704-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220703-P | WAITING (machine busy) |  | CNC1 |  | 29-08-2026 12:19 | 29-08-2026 20:15 | 7.93 | CNC1 busy with 26-27SO134 / 9612220708 P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220703-P | RUNNING | 2. CNC FIRST SIDE | CNC1 | Anil Kumar → Sandeep Kumar | 29-08-2026 20:15 | 30-08-2026 17:41 | 21.42
26-27SO148 | 9612220703-P | RUNNING | 3. DEBURING | MLATHE | Anturam | 30-08-2026 17:18 | 31-08-2026 12:13 | 18.92
26-27SO148 | 9612220703-P | RUNNING | 4. INSPECTION | MI1 | Nitin Khade | 31-08-2026 10:44 | 31-08-2026 12:13 | 1.48
26-27SO148 | 9612220703-P | RUNNING | 5. PACKING | MPK1 | HP1 | 31-08-2026 10:53 | 31-08-2026 12:21 | 1.48
26-27SO148 | 9612220705-P | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO148 | 9612220705-P | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO148 | 9612220705-P | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO148 | 9612220705-P | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO148 | 9612220705-P | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74 | CNC1 busy with 26-27SO120 / 9611443240 — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220705-P | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24 | CNC1 busy with 26-27SO134 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220705-P | WAITING (crew) |  |  |  | 13-08-2026 04:14 | 13-08-2026 05:00 | 0.76 | Machine free — waiting for a free qualified operator
26-27SO148 | 9612220705-P | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 08:00 | 14-08-2026 17:46 | 9.78 | CNC1 busy with 26-27SO134 / 9612220710 P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 14-08-2026 17:46 | 16-08-2026 12:47 | 43.01 | CNC1 busy with 26-27SO105 / 9612220703-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 16-08-2026 12:47 | 17-08-2026 14:31 | 25.74 | CNC1 busy with 26-27SO134 / 9612220704-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 17-08-2026 14:31 | 20-08-2026 01:44 | 59.22 | CNC1 busy with 26-27SO120 / 9611443240 — CNC SECOND SIDE (higher priority)
26-27SO148 | 9612220705-P | WAITING (crew) |  |  |  | 20-08-2026 01:44 | 20-08-2026 05:00 | 3.25 | Machine free — waiting for a free qualified operator
26-27SO148 | 9612220705-P | WAITING (off-hours) |  |  |  | 20-08-2026 05:00 | 21-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 21-08-2026 08:00 | 22-08-2026 08:06 | 24.1 | CNC1 busy with 26-27SO134 / 9612220705-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 22-08-2026 08:06 | 23-08-2026 20:36 | 36.5 | CNC1 busy with 26-27SO139 / 9611443241 — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 23-08-2026 20:36 | 26-08-2026 04:26 | 55.83 | CNC1 busy with 26-27SO139 / 9611443241 — CNC SECOND SIDE (higher priority)
26-27SO148 | 9612220705-P | WAITING (crew) |  |  |  | 26-08-2026 04:26 | 26-08-2026 05:00 | 0.56 | Machine free — waiting for a free qualified operator
26-27SO148 | 9612220705-P | WAITING (off-hours) |  |  |  | 26-08-2026 05:00 | 26-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 26-08-2026 08:00 | 27-08-2026 00:52 | 16.88 | CNC1 busy with 26-27SO137 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220705-P | WAITING (crew) |  |  |  | 27-08-2026 00:52 | 27-08-2026 05:00 | 4.12 | Machine free — waiting for a free qualified operator
26-27SO148 | 9612220705-P | WAITING (off-hours) |  |  |  | 27-08-2026 05:00 | 28-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 28-08-2026 08:00 | 29-08-2026 12:19 | 28.33 | CNC1 busy with 26-27SO135 / 9612220704-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 29-08-2026 12:19 | 29-08-2026 20:15 | 7.93 | CNC1 busy with 26-27SO134 / 9612220708 P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | CNC1 |  | 29-08-2026 20:15 | 30-08-2026 17:41 | 21.42 | CNC1 busy with 26-27SO148 / 9612220703-P — CNC FIRST SIDE (higher priority)
26-27SO148 | 9612220705-P | RUNNING | 2. CNC FIRST SIDE | CNC1 | Sandeep Kumar → Anil Kumar | 30-08-2026 17:41 | 31-08-2026 10:21 | 16.67
26-27SO148 | 9612220705-P | WAITING (machine busy) |  | MLATHE |  | 31-08-2026 10:21 | 31-08-2026 12:13 | 1.86 | MLATHE busy with 26-27SO148 / 9612220703-P — DEBURING (higher priority)
26-27SO148 | 9612220705-P | RUNNING | 3. DEBURING | MLATHE | Anturam | 31-08-2026 12:13 | 31-08-2026 14:37 | 2.4
26-27SO148 | 9612220705-P | RUNNING | 4. INSPECTION | MI1 | Nitin Khade | 31-08-2026 14:01 | 31-08-2026 14:37 | 0.6
26-27SO148 | 9612220705-P | RUNNING | 5. PACKING | MPK1 | HP1 | 31-08-2026 14:04 | 31-08-2026 14:40 | 0.6
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | WAITING (machine busy) |  | CNC5 |  | 09-08-2026 14:00 | 11-08-2026 02:22 | 36.38 | CNC5 busy with 26-27SO113 / 9612193501 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 11-08-2026 02:22 | 11-08-2026 05:00 | 2.62 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | WAITING (off-hours) |  |  |  | 11-08-2026 05:00 | 11-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240222-01 | WAITING (machine busy) |  | CNC5 |  | 11-08-2026 08:00 | 11-08-2026 20:56 | 12.94 | CNC5 busy with 26-27SO113 / 9611416360 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 11-08-2026 20:56 | 12-08-2026 05:00 | 8.06 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | WAITING (off-hours) |  |  |  | 12-08-2026 05:00 | 12-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 13-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 14-08-2026 08:00 | 15-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | WAITING (off-hours) |  |  |  | 15-08-2026 05:00 | 15-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 15-08-2026 08:00 | 15-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | RUNNING | 2. CNC FIRST SIDE | CNC5 | Rajiv Kumar → Murali | 15-08-2026 14:00 | 15-08-2026 21:30 | 7.5
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 15-08-2026 21:30 | 16-08-2026 05:00 | 7.5 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 16-08-2026 08:00 | 17-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 17-08-2026 08:00 | 18-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | WAITING (off-hours) |  |  |  | 18-08-2026 05:00 | 18-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 18-08-2026 08:00 | 19-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | WAITING (off-hours) |  |  |  | 19-08-2026 05:00 | 19-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240222-01 | WAITING (machine busy) |  | CNC6 |  | 19-08-2026 08:00 | 21-08-2026 09:30 | 49.5 | CNC6 busy with 26-27SO108 / 61240341-80 — CNC THIRD SIDE (higher priority)
26-27SO143 | 61240222-01 | WAITING (machine busy) |  | CNC6 |  | 21-08-2026 09:30 | 21-08-2026 14:12 | 4.7 | CNC6 busy with 26-27SO132 / 61239819-81 — CNC FORTH SIDE (higher priority)
26-27SO143 | 61240222-01 | WAITING (machine busy) |  | CNC6 |  | 21-08-2026 14:12 | 23-08-2026 08:42 | 42.5 | CNC6 busy with 26-27SO98 / 61239701-01 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61240222-01 | WAITING (machine busy) |  | CNC6 |  | 23-08-2026 08:42 | 25-08-2026 09:02 | 48.33 | CNC6 busy with 26-27SO130 / 61249330-80 — CNC THIRD SIDE (higher priority)
26-27SO143 | 61240222-01 | WAITING (machine busy) |  | CNC6 |  | 25-08-2026 09:02 | 26-08-2026 12:52 | 27.83 | CNC6 busy with 26-27SO130 / 61249330-80 — CNC FORTH SIDE (higher priority)
26-27SO143 | 61240222-01 | WAITING (machine busy) |  | CNC6 |  | 26-08-2026 12:52 | 28-08-2026 20:52 | 56 | CNC6 busy with 26-27SO117 / 00531569-01 — CNC THIRD SIDE (higher priority)
26-27SO143 | 61240222-01 | WAITING (machine busy) |  | CNC6 |  | 28-08-2026 20:52 | 30-08-2026 04:22 | 31.5 | CNC6 busy with 26-27SO98 / 61239701-01 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 30-08-2026 04:22 | 30-08-2026 05:00 | 0.63 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | WAITING (off-hours) |  |  |  | 30-08-2026 05:00 | 30-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 30-08-2026 08:00 | 31-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | WAITING (off-hours) |  |  |  | 31-08-2026 05:00 | 31-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 31-08-2026 08:00 | 01-09-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | WAITING (off-hours) |  |  |  | 01-09-2026 05:00 | 01-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 01-09-2026 08:00 | 02-09-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | WAITING (off-hours) |  |  |  | 02-09-2026 05:00 | 02-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240222-01 | WAITING (machine busy) |  | CNC6 |  | 02-09-2026 08:00 | 05-09-2026 17:30 | 81.5 | CNC6 busy with 26-27SO146 / 61240401-01 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61240222-01 | WAITING (machine busy) |  | CNC6 |  | 05-09-2026 17:30 | 07-09-2026 23:00 | 53.5 | CNC6 busy with 26-27SO146 / 61240401-01 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61240222-01 | WAITING (machine busy) |  | CNC6 |  | 07-09-2026 23:00 | 08-09-2026 22:30 | 23.5 | CNC6 busy with 26-27SO93 / 61249330-80 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 08-09-2026 22:30 | 08-09-2026 23:54 | 1.4 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | WAITING (machine busy) |  | CNC6 |  | 08-09-2026 23:54 | 09-09-2026 22:24 | 22.5 | CNC6 busy with 26-27SO131 / 8010005735 — CNC THIRD SIDE (higher priority)
26-27SO143 | 61240222-01 | WAITING (machine busy) |  | CNC6 |  | 09-09-2026 22:24 | 11-09-2026 20:54 | 46.5 | CNC6 busy with 26-27SO131 / 8010005735 — CNC FORTH SIDE (higher priority)
26-27SO143 | 61240222-01 | WAITING (machine busy) |  | CNC6 |  | 11-09-2026 20:54 | 13-09-2026 10:24 | 37.5 | CNC6 busy with 26-27SO93 / 61249330-80 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61240222-01 | RUNNING | 3. CNC SECOND SIDE | CNC6 | Rohan Chakane → Sidhu Singe | 13-09-2026 10:24 | 14-09-2026 12:54 | 26.5
26-27SO143 | 61240222-01 | RUNNING | 4. VMC FIRST SIDE | VMC2 | Rupesh Pawar | 14-09-2026 08:00 | 14-09-2026 15:54 | 7.9
26-27SO143 | 61240222-01 | RUNNING | 5. CNC THIRD SIDE | CNC6 | Sidhu Singe → Khansab Mulla | 14-09-2026 12:54 | 15-09-2026 02:24 | 13.5
26-27SO143 | 61240222-01 | WAITING (off-hours) |  |  |  | 15-09-2026 02:24 | 15-09-2026 08:00 | 5.6 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240222-01 | RUNNING | 6. CHAMFER | DTC2 | Anturam | 15-09-2026 08:00 | 15-09-2026 11:20 | 3.33
26-27SO143 | 61240222-01 | WAITING (crew) |  |  |  | 15-09-2026 11:20 | 15-09-2026 11:30 | 0.17 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240222-01 | WAITING (machine busy) |  | CMM |  | 15-09-2026 11:30 | 15-09-2026 16:30 | 5 | CMM busy with 26-27SO143 / 61240190-01 — CMM (higher priority)
26-27SO143 | 61240222-01 | RUNNING | 7. CMM | CMM | Kiran Mohite | 15-09-2026 16:30 | 16-09-2026 10:30 | 18
26-27SO143 | 61240222-01 | RUNNING | 8. INSPECTION | MI3 | Sidhanath | 15-09-2026 17:00 | 16-09-2026 12:40 | 19.67
26-27SO143 | 61240222-01 | RUNNING | 9. PACKING | MPK1 | HP1 | 16-09-2026 11:00 | 16-09-2026 12:40 | 1.67
26-27SO143 | 61240190-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240190-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240190-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 09-08-2026 14:00 | 10-08-2026 13:48 | 23.8 | CNC3 busy with 26-27SO126 / 971-571126-03 — CNC FORTH SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 10-08-2026 13:48 | 12-08-2026 19:18 | 53.5 | CNC3 busy with 26-27SO108 / 61240341-80 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 12-08-2026 19:18 | 14-08-2026 17:48 | 46.5 | CNC3 busy with 26-27SO69 / 8010009209 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 14-08-2026 17:48 | 16-08-2026 03:30 | 33.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (crew) |  |  |  | 16-08-2026 03:30 | 16-08-2026 05:00 | 1.5 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240190-01 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 08:00 | 16-08-2026 23:54 | 15.9 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 23:54 | 17-08-2026 05:00 | 5.1 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 17-08-2026 08:00 | 17-08-2026 17:30 | 9.5 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 17-08-2026 17:30 | 18-08-2026 14:00 | 20.5 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC THIRD SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 18-08-2026 14:00 | 19-08-2026 11:42 | 21.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC THIRD SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 19-08-2026 11:42 | 23-08-2026 10:12 | 94.5 | CNC3 busy with 26-27SO117 / 00531569-01 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 23-08-2026 10:12 | 25-08-2026 08:42 | 46.5 | CNC3 busy with 26-27SO131 / 8010005735 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 25-08-2026 08:42 | 28-08-2026 18:12 | 81.5 | CNC3 busy with 26-27SO117 / 00531569-01 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 28-08-2026 18:12 | 31-08-2026 11:42 | 65.5 | CNC3 busy with 26-27SO75 / 61235943-01 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 31-08-2026 11:42 | 01-09-2026 12:42 | 25 | CNC3 busy with 26-27SO98 / 61239701-01 — CNC THIRD SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 01-09-2026 12:42 | 03-09-2026 03:12 | 38.5 | CNC3 busy with 26-27SO75 / 61235943-01 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (crew) |  |  |  | 03-09-2026 03:12 | 03-09-2026 05:00 | 1.8 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240190-01 | WAITING (off-hours) |  |  |  | 03-09-2026 05:00 | 04-09-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 04-09-2026 08:00 | 06-09-2026 16:30 | 56.5 | CNC3 busy with 26-27SO131 / 8010005735 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 06-09-2026 16:30 | 08-09-2026 11:00 | 42.5 | CNC3 busy with 26-27SO143 / 61239701-01 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61240190-01 | RUNNING | 1. CNC FIRST SIDE | CNC3 | Rohan Chakane | 08-09-2026 11:00 | 09-09-2026 17:30 | 30.5
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 09-09-2026 17:30 | 13-09-2026 00:00 | 78.5 | CNC3 busy with 26-27SO143 / 61239701-01 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61240190-01 | WAITING (crew) |  |  |  | 13-09-2026 00:00 | 13-09-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO143 | 61240190-01 | WAITING (off-hours) |  |  |  | 13-09-2026 05:00 | 13-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | CNC3 |  | 13-09-2026 08:00 | 13-09-2026 20:00 | 12 | CNC3 busy with 26-27SO143 / 61239701-01 — CNC THIRD SIDE (higher priority)
26-27SO143 | 61240190-01 | RUNNING | 2. CNC SECOND SIDE | CNC3 | Khansab Mulla → Rohan Chakane | 13-09-2026 20:00 | 14-09-2026 16:30 | 20.5
26-27SO143 | 61240190-01 | RUNNING | 3. VMC FIRST SIDE | VMC2 | Rupesh Pawar → Saif | 14-09-2026 15:54 | 15-09-2026 01:24 | 9.5
26-27SO143 | 61240190-01 | WAITING (off-hours) |  |  |  | 15-09-2026 01:24 | 15-09-2026 08:00 | 6.6 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61240190-01 | WAITING (machine busy) |  | DTC2 |  | 15-09-2026 08:00 | 15-09-2026 11:20 | 3.33 | DTC2 busy with 26-27SO143 / 61240222-01 — CHAMFER
26-27SO143 | 61240190-01 | RUNNING | 4. CHAMFER | DTC2 | Anturam | 15-09-2026 11:20 | 15-09-2026 13:00 | 1.67
26-27SO143 | 61240190-01 | RUNNING | 5. CMM | CMM | Kiran Mohite | 15-09-2026 11:30 | 15-09-2026 16:30 | 5
26-27SO143 | 61240190-01 | RUNNING | 6. INSPECTION | MI1 | Nitin Khade | 15-09-2026 12:00 | 15-09-2026 18:40 | 6.67
26-27SO143 | 61240190-01 | RUNNING | 7. PACKING | MPK1 | HP1 | 15-09-2026 17:40 | 15-09-2026 18:40 | 1
26-27SO134 | 9612220701-P | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220701-P | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220701-P | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO134 | 9612220701-P | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220701-P | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE
26-27SO134 | 9612220701-P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74 | CNC1 busy with 26-27SO120 / 9611443240 — CNC FIRST SIDE
26-27SO134 | 9612220701-P | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220701-P | RUNNING | 2. CNC FIRST SIDE | CNC1 | Rajiv Kumar → Murali | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24
26-27SO134 | 9612220701-P | RUNNING | 3. DEBURING | MLATHE | Sanjay → Anturam | 12-08-2026 16:46 | 15-08-2026 10:26 | 65.67
26-27SO134 | 9612220701-P | RUNNING | 4. INSPECTION | MI2 | Kiran Mohite | 15-08-2026 09:16 | 15-08-2026 10:26 | 1.17
26-27SO134 | 9612220701-P | RUNNING | 5. PACKING | MPK2 | HP2 | 15-08-2026 09:23 | 15-08-2026 10:33 | 1.17
26-27SO117 | 61240807-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO117 | 61240807-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO117 | 61240807-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 10-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO117 | 61240807-01 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO117 | 61240807-01 | WAITING (machine busy) |  | CNC7 |  | 10-08-2026 08:00 | 10-08-2026 13:30 | 5.5 | CNC7 busy with 26-27SO95 / 61248811-01 — CNC FIRST SIDE (higher priority)
26-27SO117 | 61240807-01 | WAITING (machine busy) |  | CNC7 |  | 10-08-2026 13:30 | 11-08-2026 03:00 | 13.5 | CNC7 busy with 26-27SO95 / 61248811-01 — CNC SECOND SIDE (higher priority)
26-27SO117 | 61240807-01 | WAITING (crew) |  |  |  | 11-08-2026 03:00 | 11-08-2026 05:00 | 2 | Machine free — waiting for a free qualified operator
26-27SO117 | 61240807-01 | WAITING (off-hours) |  |  |  | 11-08-2026 05:00 | 11-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO117 | 61240807-01 | WAITING (machine busy) |  | CNC7 |  | 11-08-2026 08:00 | 12-08-2026 12:00 | 28 | CNC7 busy with 26-27SO68 / 61241992-01 — CNC FIRST SIDE (higher priority)
26-27SO117 | 61240807-01 | WAITING (machine busy) |  | CNC7 |  | 12-08-2026 12:00 | 12-08-2026 15:18 | 3.3 | CNC7 busy with 26-27SO111 / 61241989-01 — CNC FIRST SIDE (higher priority)
26-27SO117 | 61240807-01 | WAITING (machine busy) |  | CNC7 |  | 12-08-2026 15:18 | 14-08-2026 11:48 | 44.5 | CNC7 busy with 26-27SO104 / 61249522-01 — CNC SECOND SIDE (higher priority)
26-27SO117 | 61240807-01 | WAITING (machine busy) |  | CNC7 |  | 14-08-2026 11:48 | 14-08-2026 16:54 | 5.1 | CNC7 busy with 26-27SO111 / 61241989-01 — CNC THIRD SIDE (higher priority)
26-27SO117 | 61240807-01 | RUNNING | 1. CNC FIRST SIDE | CNC7 | Sidhu Singe → Khansab Mulla | 14-08-2026 16:54 | 14-08-2026 21:36 | 4.7
26-27SO117 | 61240807-01 | RUNNING | 2. VMC FIRST SIDE | VMC1 | Ankush Jadhav → Mahesh | 14-08-2026 18:43 | 15-08-2026 01:49 | 7.1
26-27SO117 | 61240807-01 | RUNNING | 3. CNC SECOND SIDE | CNC4 | Murali | 14-08-2026 21:07 | 15-08-2026 01:49 | 4.7
26-27SO117 | 61240807-01 | WAITING (off-hours) |  |  |  | 15-08-2026 01:49 | 15-08-2026 08:00 | 6.18 | Outside working hours (night / weekly off / holiday)
26-27SO117 | 61240807-01 | WAITING (crew) |  |  |  | 15-08-2026 08:00 | 15-08-2026 12:30 | 4.5 | Machine free — waiting for a free qualified operator
26-27SO117 | 61240807-01 | WAITING (machine busy) |  | DTC2 |  | 15-08-2026 12:30 | 15-08-2026 15:00 | 2.5 | DTC2 busy with 26-27SO68 / 61241992-01 — CHAMFER (higher priority)
26-27SO117 | 61240807-01 | RUNNING | 4. CHAMFER | DTC2 | Anturam | 15-08-2026 15:00 | 15-08-2026 18:20 | 3.33
26-27SO117 | 61240807-01 | RUNNING | 5. CMM | CMM | Kiran Mohite | 15-08-2026 15:20 | 15-08-2026 18:40 | 3.33
26-27SO117 | 61240807-01 | WAITING (crew) |  |  |  | 15-08-2026 18:40 | 15-08-2026 19:00 | 0.33 | Machine free — waiting for a free qualified operator
26-27SO117 | 61240807-01 | WAITING (off-hours) |  |  |  | 15-08-2026 19:00 | 16-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO117 | 61240807-01 | WAITING (crew) |  |  |  | 16-08-2026 08:00 | 16-08-2026 09:50 | 1.84 | Machine free — waiting for a free qualified operator
26-27SO117 | 61240807-01 | WAITING (machine busy) |  | MI1 |  | 16-08-2026 09:50 | 16-08-2026 10:27 | 0.61 | MI1 busy with 26-27SO134 / 9612220710 P — INSPECTION (higher priority)
26-27SO117 | 61240807-01 | WAITING (machine busy) |  | MI1 |  | 16-08-2026 10:27 | 16-08-2026 14:12 | 3.75 | MI1 busy with 26-27SO68 / 61241992-01 — INSPECTION (higher priority)
26-27SO117 | 61240807-01 | RUNNING | 6. INSPECTION | MI1 | Nitin Khade | 16-08-2026 14:12 | 17-08-2026 09:52 | 19.67
26-27SO117 | 61240807-01 | RUNNING | 7. WASHING | MW1 | HP1 | 17-08-2026 09:12 | 17-08-2026 09:52 | 0.67
26-27SO117 | 61240807-01 | RUNNING | 8. PACKING | MPK2 | HP2 | 17-08-2026 09:16 | 17-08-2026 09:56 | 0.67
26-27SO143 | 61239701-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO143 | 61239701-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61239701-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 09-08-2026 14:00 | 10-08-2026 13:48 | 23.8 | CNC3 busy with 26-27SO126 / 971-571126-03 — CNC FORTH SIDE (higher priority)
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 10-08-2026 13:48 | 12-08-2026 19:18 | 53.5 | CNC3 busy with 26-27SO108 / 61240341-80 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 12-08-2026 19:18 | 14-08-2026 17:48 | 46.5 | CNC3 busy with 26-27SO69 / 8010009209 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 14-08-2026 17:48 | 16-08-2026 03:30 | 33.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61239701-01 | WAITING (crew) |  |  |  | 16-08-2026 03:30 | 16-08-2026 05:00 | 1.5 | Machine free — waiting for a free qualified operator
26-27SO143 | 61239701-01 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 08:00 | 16-08-2026 23:54 | 15.9 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 23:54 | 17-08-2026 05:00 | 5.1 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61239701-01 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 17-08-2026 08:00 | 17-08-2026 17:30 | 9.5 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 17-08-2026 17:30 | 18-08-2026 14:00 | 20.5 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC THIRD SIDE (higher priority)
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 18-08-2026 14:00 | 19-08-2026 11:42 | 21.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC THIRD SIDE (higher priority)
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 19-08-2026 11:42 | 23-08-2026 10:12 | 94.5 | CNC3 busy with 26-27SO117 / 00531569-01 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 23-08-2026 10:12 | 25-08-2026 08:42 | 46.5 | CNC3 busy with 26-27SO131 / 8010005735 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 25-08-2026 08:42 | 28-08-2026 18:12 | 81.5 | CNC3 busy with 26-27SO117 / 00531569-01 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 28-08-2026 18:12 | 31-08-2026 11:42 | 65.5 | CNC3 busy with 26-27SO75 / 61235943-01 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 31-08-2026 11:42 | 01-09-2026 12:42 | 25 | CNC3 busy with 26-27SO98 / 61239701-01 — CNC THIRD SIDE (higher priority)
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 01-09-2026 12:42 | 03-09-2026 03:12 | 38.5 | CNC3 busy with 26-27SO75 / 61235943-01 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61239701-01 | WAITING (crew) |  |  |  | 03-09-2026 03:12 | 03-09-2026 05:00 | 1.8 | Machine free — waiting for a free qualified operator
26-27SO143 | 61239701-01 | WAITING (off-hours) |  |  |  | 03-09-2026 05:00 | 04-09-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 04-09-2026 08:00 | 06-09-2026 16:30 | 56.5 | CNC3 busy with 26-27SO131 / 8010005735 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61239701-01 | RUNNING | 2. CNC FIRST SIDE | CNC3 | Rohan Chakane → Sidhu Singe | 06-09-2026 16:30 | 08-09-2026 11:00 | 42.5
26-27SO143 | 61239701-01 | RUNNING | 3. VMC FIRST SIDE | VMC2 | Saif → Rupesh Pawar | 07-09-2026 20:00 | 08-09-2026 11:00 | 15
26-27SO143 | 61239701-01 | RUNNING | 4. VMC SECOND SIDE | VMC2 | Rupesh Pawar | 08-09-2026 11:00 | 08-09-2026 18:30 | 7.5
26-27SO143 | 61239701-01 | WAITING (machine busy) |  | CNC3 |  | 08-09-2026 18:30 | 09-09-2026 17:30 | 23 | CNC3 busy with 26-27SO143 / 61240190-01 — CNC FIRST SIDE
26-27SO143 | 61239701-01 | RUNNING | 5. CNC SECOND SIDE | CNC3 | Rohan Chakane → Sidhu Singe → Khansab Mulla | 09-09-2026 17:30 | 13-09-2026 00:00 | 78.5
26-27SO143 | 61239701-01 | WAITING (crew) |  |  |  | 13-09-2026 00:00 | 13-09-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO143 | 61239701-01 | WAITING (off-hours) |  |  |  | 13-09-2026 05:00 | 13-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61239701-01 | RUNNING | 6. CNC THIRD SIDE | CNC3 | Sidhu Singe → Khansab Mulla | 13-09-2026 08:00 | 13-09-2026 20:00 | 12
26-27SO143 | 61239701-01 | RUNNING | 7. CHAMFER | DTC2 | Anturam | 13-09-2026 18:45 | 14-09-2026 09:00 | 14.25
26-27SO143 | 61239701-01 | RUNNING | 8. CMM | CMM | Kiran Mohite | 13-09-2026 18:52 | 14-09-2026 11:37 | 16.75
26-27SO143 | 61239701-01 | RUNNING | 9. INSPECTION | MI1 | Nitin Khade | 14-09-2026 08:00 | 14-09-2026 11:45 | 3.75
26-27SO143 | 61239701-01 | RUNNING | 10. PACKING | MPK1 | HP1 | 14-09-2026 10:30 | 14-09-2026 11:45 | 1.25
26-27SO133 | 9611443650 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO133 | 9611443650 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO133 | 9611443650 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO133 | 9611443650 | RUNNING | 3. VMC FIRST SIDE | VMC1 | Rupesh Pawar → Saif | 09-08-2026 14:00 | 10-08-2026 15:56 | 25.94
26-27SO133 | 9611443650 | RUNNING | 4. DEBURING | MD2 | Anturam → Sanjay | 09-08-2026 18:46 | 10-08-2026 15:56 | 21.17
26-27SO133 | 9611443650 | WAITING (crew) |  |  |  | 10-08-2026 15:56 | 10-08-2026 19:00 | 3.06 | Machine free — waiting for a free qualified operator
26-27SO133 | 9611443650 | WAITING (off-hours) |  |  |  | 10-08-2026 19:00 | 11-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO133 | 9611443650 | WAITING (crew) |  |  |  | 11-08-2026 08:00 | 11-08-2026 09:46 | 1.77 | Machine free — waiting for a free qualified operator
26-27SO133 | 9611443650 | WAITING (machine busy) |  | DTC2 |  | 11-08-2026 09:46 | 12-08-2026 15:26 | 29.67 | DTC2 busy with 26-27SO113 / 9612193501 — CHAMFER (higher priority)
26-27SO133 | 9611443650 | WAITING (machine busy) |  | DTC2 |  | 12-08-2026 15:26 | 14-08-2026 08:36 | 41.17 | DTC2 busy with 26-27SO113 / 9612193501 — RETAPP (higher priority)
26-27SO133 | 9611443650 | WAITING (machine busy) |  | DTC2 |  | 14-08-2026 08:36 | 14-08-2026 10:16 | 1.67 | DTC2 busy with 26-27SO95 / 61248811-01 — CHAMFER (higher priority)
26-27SO133 | 9611443650 | WAITING (crew) |  |  |  | 14-08-2026 10:16 | 14-08-2026 14:24 | 4.13 | Machine free — waiting for a free qualified operator
26-27SO133 | 9611443650 | WAITING (machine busy) |  | DTC2 |  | 14-08-2026 14:24 | 14-08-2026 16:54 | 2.5 | DTC2 busy with 26-27SO111 / 61241989-01 — CHAMFER (higher priority)
26-27SO133 | 9611443650 | WAITING (crew) |  |  |  | 14-08-2026 16:54 | 14-08-2026 19:00 | 2.1 | Machine free — waiting for a free qualified operator
26-27SO133 | 9611443650 | WAITING (off-hours) |  |  |  | 14-08-2026 19:00 | 15-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO133 | 9611443650 | WAITING (crew) |  |  |  | 15-08-2026 08:00 | 15-08-2026 12:30 | 4.5 | Machine free — waiting for a free qualified operator
26-27SO133 | 9611443650 | WAITING (machine busy) |  | DTC2 |  | 15-08-2026 12:30 | 15-08-2026 15:00 | 2.5 | DTC2 busy with 26-27SO68 / 61241992-01 — CHAMFER (higher priority)
26-27SO133 | 9611443650 | WAITING (machine busy) |  | DTC2 |  | 15-08-2026 15:00 | 15-08-2026 18:20 | 3.33 | DTC2 busy with 26-27SO117 / 61240807-01 — CHAMFER (higher priority)
26-27SO133 | 9611443650 | RUNNING | 5. CHAMFER | DTC2 | Anturam → Sanjay | 15-08-2026 18:20 | 16-08-2026 15:30 | 21.17
26-27SO133 | 9611443650 | WAITING (machine busy) |  | MI1 |  | 16-08-2026 15:30 | 17-08-2026 09:52 | 18.37 | MI1 busy with 26-27SO117 / 61240807-01 — INSPECTION (higher priority)
26-27SO133 | 9611443650 | WAITING (machine busy) |  | MI1 |  | 17-08-2026 09:52 | 17-08-2026 12:58 | 3.1 | MI1 busy with 26-27SO105 / 9612220703-P — INSPECTION (higher priority)
26-27SO133 | 9611443650 | WAITING (machine busy) |  | MI1 |  | 17-08-2026 12:58 | 17-08-2026 16:43 | 3.75 | MI1 busy with 26-27SO104 / 61249522-01 — INSPECTION (higher priority)
26-27SO133 | 9611443650 | RUNNING | 6. INSPECTION | MI1 | Nitin Khade | 17-08-2026 16:43 | 18-08-2026 13:53 | 21.17
26-27SO133 | 9611443650 | RUNNING | 7. PACKING | MPK2 | HP2 | 18-08-2026 09:48 | 18-08-2026 13:53 | 4.08
26-27SO108 | 61240341-80 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO108 | 61240341-80 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO108 | 61240341-80 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO108 | 61240341-80 | WAITING (machine busy) |  | CNC3 |  | 09-08-2026 14:00 | 10-08-2026 13:48 | 23.8 | CNC3 busy with 26-27SO126 / 971-571126-03 — CNC FORTH SIDE
26-27SO108 | 61240341-80 | RUNNING | 2. CNC SECOND SIDE | CNC3 | Rohan Chakane → Khansab Mulla | 10-08-2026 13:48 | 12-08-2026 19:18 | 53.5
26-27SO108 | 61240341-80 | RUNNING | 3. VMC FIRST SIDE | VMC3 | Ankush Jadhav → Mahesh → Swapnil | 10-08-2026 18:54 | 13-08-2026 00:24 | 53.5
26-27SO108 | 61240341-80 | WAITING (crew) |  |  |  | 13-08-2026 00:24 | 13-08-2026 05:00 | 4.6 | Machine free — waiting for a free qualified operator
26-27SO108 | 61240341-80 | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO108 | 61240341-80 | RUNNING | 4. VMC SECOND SIDE | VMC3 | Swapnil → Ankush Jadhav → Saif → Rupesh Pawar | 14-08-2026 08:00 | 16-08-2026 15:00 | 55
26-27SO108 | 61240341-80 | WAITING (crew) |  |  |  | 16-08-2026 15:00 | 17-08-2026 05:00 | 14 | Machine free — waiting for a free qualified operator
26-27SO108 | 61240341-80 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO108 | 61240341-80 | WAITING (crew) |  |  |  | 17-08-2026 08:00 | 18-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO108 | 61240341-80 | WAITING (off-hours) |  |  |  | 18-08-2026 05:00 | 18-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO108 | 61240341-80 | WAITING (crew) |  |  |  | 18-08-2026 08:00 | 19-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO108 | 61240341-80 | WAITING (off-hours) |  |  |  | 19-08-2026 05:00 | 19-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO108 | 61240341-80 | RUNNING | 5. CNC THIRD SIDE | CNC6 | Sidhu Singe → Khansab Mulla → Rohan Chakane | 19-08-2026 08:00 | 21-08-2026 09:30 | 49.5
26-27SO108 | 61240341-80 | RUNNING | 6. CNC FORTH SIDE | DTC2 | Anturam | 21-08-2026 08:00 | 21-08-2026 14:15 | 6.25
26-27SO108 | 61240341-80 | RUNNING | 7. CHAMFER | DTC2 | Anturam → Sanjay | 21-08-2026 14:15 | 23-08-2026 14:45 | 48.5
26-27SO108 | 61240341-80 | RUNNING | 8. CMM | CMM | Kiran Mohite | 22-08-2026 10:45 | 23-08-2026 14:45 | 28
26-27SO108 | 61240341-80 | RUNNING | 9. WASHING | MW1 | HP1 | 23-08-2026 13:30 | 23-08-2026 14:45 | 1.25
26-27SO108 | 61240341-80 | RUNNING | 10. PACKING | MPK1 | HP2 | 23-08-2026 13:37 | 23-08-2026 14:52 | 1.25
26-27SO137 | 9611340324-P | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO137 | 9611340324-P | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO137 | 9611340324-P | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO137 | 9611340324-P | RUNNING | 1. CNC FIRST SIDE | CNC1 | Rajiv Kumar → Narayan Fatak | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45
26-27SO137 | 9611340324-P | RUNNING | 2. CNC SECOND SIDE | CNC1 | Narayan Fatak | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3
26-27SO137 | 9611340324-P | WAITING (off-hours) |  |  |  | 10-08-2026 02:45 | 10-08-2026 08:00 | 5.25 | Outside working hours (night / weekly off / holiday)
26-27SO137 | 9611340324-P | RUNNING | 3. INSPECTION | MI2 | Kiran Mohite | 10-08-2026 08:00 | 10-08-2026 09:40 | 1.67
26-27SO137 | 9611340324-P | RUNNING | 4. PACKING | MPK1 | HP1 | 10-08-2026 08:10 | 10-08-2026 09:50 | 1.67
26-27SO144 | 9612358901 | WAITING (off-hours) |  |  |  | 09-08-2026 00:00 | 09-08-2026 08:00 | 8 | Outside working hours (night / weekly off / holiday)
26-27SO144 | 9612358901 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO144 | 9612358901 | WAITING (off-hours) |  |  |  | 09-08-2026 19:00 | 10-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO144 | 9612358901 | WAITING (crew) |  |  |  | 10-08-2026 08:00 | 10-08-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO144 | 9612358901 | WAITING (off-hours) |  |  |  | 10-08-2026 19:00 | 11-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO144 | 9612358901 | WAITING (crew) |  |  |  | 11-08-2026 08:00 | 11-08-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO144 | 9612358901 | WAITING (off-hours) |  |  |  | 11-08-2026 19:00 | 12-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO144 | 9612358901 | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO144 | 9612358901 | WAITING (off-hours) |  |  |  | 12-08-2026 19:00 | 14-08-2026 08:00 | 37 | Outside working hours (night / weekly off / holiday)
26-27SO144 | 9612358901 | WAITING (crew) |  |  |  | 14-08-2026 08:00 | 14-08-2026 13:10 | 5.17 | Machine free — waiting for a free qualified operator
26-27SO144 | 9612358901 | WAITING (machine busy) |  | MI1 |  | 14-08-2026 13:10 | 15-08-2026 13:10 | 24 | MI1 busy with 26-27SO113 / 9611416360 — INSP (higher priority)
26-27SO144 | 9612358901 | RUNNING | 4. INSPECTION | MI1 | Nitin Khade | 15-08-2026 13:10 | 15-08-2026 17:20 | 4.17
26-27SO144 | 9612358901 | RUNNING | 5. WASHING | MW1 | HP1 | 15-08-2026 15:15 | 15-08-2026 17:20 | 2.08
26-27SO144 | 9612358901 | RUNNING | 6. PACKING | MPK2 | HP2 → HP1 | 15-08-2026 15:27 | 16-08-2026 08:37 | 17.17
26-27SO147 | 8010009209 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO147 | 8010009209 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO147 | 8010009209 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 09-08-2026 14:00 | 10-08-2026 13:48 | 23.8 | CNC3 busy with 26-27SO126 / 971-571126-03 — CNC FORTH SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 10-08-2026 13:48 | 12-08-2026 19:18 | 53.5 | CNC3 busy with 26-27SO108 / 61240341-80 — CNC SECOND SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 12-08-2026 19:18 | 14-08-2026 17:48 | 46.5 | CNC3 busy with 26-27SO69 / 8010009209 — CNC SECOND SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 14-08-2026 17:48 | 16-08-2026 03:30 | 33.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC FIRST SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (crew) |  |  |  | 16-08-2026 03:30 | 16-08-2026 05:00 | 1.5 | Machine free — waiting for a free qualified operator
26-27SO147 | 8010009209 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 08:00 | 16-08-2026 23:54 | 15.9 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC SECOND SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 23:54 | 17-08-2026 05:00 | 5.1 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC FIRST SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 17-08-2026 08:00 | 17-08-2026 17:30 | 9.5 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC SECOND SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 17-08-2026 17:30 | 18-08-2026 14:00 | 20.5 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC THIRD SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 18-08-2026 14:00 | 19-08-2026 11:42 | 21.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC THIRD SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 19-08-2026 11:42 | 23-08-2026 10:12 | 94.5 | CNC3 busy with 26-27SO117 / 00531569-01 — CNC FIRST SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 23-08-2026 10:12 | 25-08-2026 08:42 | 46.5 | CNC3 busy with 26-27SO131 / 8010005735 — CNC FIRST SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 25-08-2026 08:42 | 28-08-2026 18:12 | 81.5 | CNC3 busy with 26-27SO117 / 00531569-01 — CNC SECOND SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 28-08-2026 18:12 | 31-08-2026 11:42 | 65.5 | CNC3 busy with 26-27SO75 / 61235943-01 — CNC FIRST SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 31-08-2026 11:42 | 01-09-2026 12:42 | 25 | CNC3 busy with 26-27SO98 / 61239701-01 — CNC THIRD SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 01-09-2026 12:42 | 03-09-2026 03:12 | 38.5 | CNC3 busy with 26-27SO75 / 61235943-01 — CNC SECOND SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (crew) |  |  |  | 03-09-2026 03:12 | 03-09-2026 05:00 | 1.8 | Machine free — waiting for a free qualified operator
26-27SO147 | 8010009209 | WAITING (off-hours) |  |  |  | 03-09-2026 05:00 | 04-09-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 04-09-2026 08:00 | 06-09-2026 16:30 | 56.5 | CNC3 busy with 26-27SO131 / 8010005735 — CNC SECOND SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 06-09-2026 16:30 | 08-09-2026 11:00 | 42.5 | CNC3 busy with 26-27SO143 / 61239701-01 — CNC FIRST SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 08-09-2026 11:00 | 09-09-2026 17:30 | 30.5 | CNC3 busy with 26-27SO143 / 61240190-01 — CNC FIRST SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 09-09-2026 17:30 | 13-09-2026 00:00 | 78.5 | CNC3 busy with 26-27SO143 / 61239701-01 — CNC SECOND SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (crew) |  |  |  | 13-09-2026 00:00 | 13-09-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO147 | 8010009209 | WAITING (off-hours) |  |  |  | 13-09-2026 05:00 | 13-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 13-09-2026 08:00 | 13-09-2026 20:00 | 12 | CNC3 busy with 26-27SO143 / 61239701-01 — CNC THIRD SIDE (higher priority)
26-27SO147 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 13-09-2026 20:00 | 14-09-2026 16:30 | 20.5 | CNC3 busy with 26-27SO143 / 61240190-01 — CNC SECOND SIDE (higher priority)
26-27SO147 | 8010009209 | RUNNING | 1. CNC FIRST SIDE | CNC3 | Rohan Chakane | 14-09-2026 16:30 | 15-09-2026 15:00 | 22.5
26-27SO147 | 8010009209 | RUNNING | 2. CNC SECOND SIDE | CNC6 | Sidhu Singe | 15-09-2026 08:00 | 15-09-2026 18:30 | 10.5
26-27SO147 | 8010009209 | RUNNING | 3. VMC FIRST SIDE | VMC2 | Rupesh Pawar → Saif | 15-09-2026 10:24 | 15-09-2026 22:14 | 11.83
26-27SO147 | 8010009209 | RUNNING | 4. VMC SECOND SIDE | VMC2 | Saif → Ankush Jadhav | 15-09-2026 22:14 | 16-09-2026 08:44 | 10.5
26-27SO147 | 8010009209 | WAITING (crew) |  |  |  | 16-09-2026 08:44 | 17-09-2026 05:00 | 20.27 | Machine free — waiting for a free qualified operator
26-27SO147 | 8010009209 | WAITING (off-hours) |  |  |  | 17-09-2026 05:00 | 18-09-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO147 | 8010009209 | WAITING (crew) |  |  |  | 18-09-2026 08:00 | 18-09-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO147 | 8010009209 | RUNNING | 5. CNC THIRD SIDE | CNC7 | Khansab Mulla → Rohan Chakane | 18-09-2026 19:00 | 19-09-2026 09:30 | 14.5
26-27SO147 | 8010009209 | RUNNING | 6. DEBURING | MD1 | Anturam | 19-09-2026 08:50 | 19-09-2026 09:30 | 0.67
26-27SO147 | 8010009209 | RUNNING | 7. CMM | CMM | Kiran Mohite | 19-09-2026 08:54 | 19-09-2026 11:24 | 2.5
26-27SO147 | 8010009209 | RUNNING | 8. INSPECTION | MI1 | Nitin Khade | 19-09-2026 10:34 | 19-09-2026 11:24 | 0.83
26-27SO147 | 8010009209 | RUNNING | 9. WASHING | MW1 | HP1 | 19-09-2026 10:54 | 19-09-2026 11:24 | 0.5
26-27SO105 | 9612220702-P | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO105 | 9612220702-P | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO105 | 9612220702-P | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO105 | 9612220702-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO105 | 9612220702-P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO105 | 9612220702-P | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO105 | 9612220702-P | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO105 | 9612220702-P | RUNNING | 2. CNC FIRST SIDE | CNC1 | Rajiv Kumar | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27
26-27SO105 | 9612220702-P | RUNNING | 3. DEBURING | MLATHE | Anturam | 10-08-2026 12:36 | 10-08-2026 14:16 | 1.67
26-27SO105 | 9612220702-P | RUNNING | 4. INSPECTION | MI2 | Kiran Mohite | 10-08-2026 13:51 | 10-08-2026 14:16 | 0.42
26-27SO105 | 9612220702-P | RUNNING | 5. PACKING | MPK1 | HP1 | 10-08-2026 13:53 | 10-08-2026 14:18 | 0.42
26-27SO142 | 8010009209 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO142 | 8010009209 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO142 | 8010009209 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 09-08-2026 14:00 | 10-08-2026 13:48 | 23.8 | CNC3 busy with 26-27SO126 / 971-571126-03 — CNC FORTH SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 10-08-2026 13:48 | 12-08-2026 19:18 | 53.5 | CNC3 busy with 26-27SO108 / 61240341-80 — CNC SECOND SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 12-08-2026 19:18 | 14-08-2026 17:48 | 46.5 | CNC3 busy with 26-27SO69 / 8010009209 — CNC SECOND SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 14-08-2026 17:48 | 16-08-2026 03:30 | 33.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC FIRST SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (crew) |  |  |  | 16-08-2026 03:30 | 16-08-2026 05:00 | 1.5 | Machine free — waiting for a free qualified operator
26-27SO142 | 8010009209 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 08:00 | 16-08-2026 23:54 | 15.9 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC SECOND SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 23:54 | 17-08-2026 05:00 | 5.1 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC FIRST SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 17-08-2026 08:00 | 17-08-2026 17:30 | 9.5 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC SECOND SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 17-08-2026 17:30 | 18-08-2026 14:00 | 20.5 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC THIRD SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 18-08-2026 14:00 | 19-08-2026 11:42 | 21.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC THIRD SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 19-08-2026 11:42 | 23-08-2026 10:12 | 94.5 | CNC3 busy with 26-27SO117 / 00531569-01 — CNC FIRST SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 23-08-2026 10:12 | 25-08-2026 08:42 | 46.5 | CNC3 busy with 26-27SO131 / 8010005735 — CNC FIRST SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 25-08-2026 08:42 | 28-08-2026 18:12 | 81.5 | CNC3 busy with 26-27SO117 / 00531569-01 — CNC SECOND SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 28-08-2026 18:12 | 31-08-2026 11:42 | 65.5 | CNC3 busy with 26-27SO75 / 61235943-01 — CNC FIRST SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 31-08-2026 11:42 | 01-09-2026 12:42 | 25 | CNC3 busy with 26-27SO98 / 61239701-01 — CNC THIRD SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 01-09-2026 12:42 | 03-09-2026 03:12 | 38.5 | CNC3 busy with 26-27SO75 / 61235943-01 — CNC SECOND SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (crew) |  |  |  | 03-09-2026 03:12 | 03-09-2026 05:00 | 1.8 | Machine free — waiting for a free qualified operator
26-27SO142 | 8010009209 | WAITING (off-hours) |  |  |  | 03-09-2026 05:00 | 04-09-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 04-09-2026 08:00 | 06-09-2026 16:30 | 56.5 | CNC3 busy with 26-27SO131 / 8010005735 — CNC SECOND SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 06-09-2026 16:30 | 08-09-2026 11:00 | 42.5 | CNC3 busy with 26-27SO143 / 61239701-01 — CNC FIRST SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 08-09-2026 11:00 | 09-09-2026 17:30 | 30.5 | CNC3 busy with 26-27SO143 / 61240190-01 — CNC FIRST SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 09-09-2026 17:30 | 13-09-2026 00:00 | 78.5 | CNC3 busy with 26-27SO143 / 61239701-01 — CNC SECOND SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (crew) |  |  |  | 13-09-2026 00:00 | 13-09-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO142 | 8010009209 | WAITING (off-hours) |  |  |  | 13-09-2026 05:00 | 13-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 13-09-2026 08:00 | 13-09-2026 20:00 | 12 | CNC3 busy with 26-27SO143 / 61239701-01 — CNC THIRD SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 13-09-2026 20:00 | 14-09-2026 16:30 | 20.5 | CNC3 busy with 26-27SO143 / 61240190-01 — CNC SECOND SIDE (higher priority)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 14-09-2026 16:30 | 15-09-2026 15:00 | 22.5 | CNC3 busy with 26-27SO147 / 8010009209 — CNC FIRST SIDE (higher priority)
26-27SO142 | 8010009209 | RUNNING | 1. CNC FIRST SIDE | CNC3 | Rohan Chakane → Khansab Mulla | 15-09-2026 15:00 | 16-09-2026 00:30 | 9.5
26-27SO142 | 8010009209 | WAITING (crew) |  |  |  | 16-09-2026 00:30 | 16-09-2026 05:00 | 4.5 | Machine free — waiting for a free qualified operator
26-27SO142 | 8010009209 | WAITING (off-hours) |  |  |  | 16-09-2026 05:00 | 16-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC3 |  | 16-09-2026 08:00 | 16-09-2026 15:58 | 7.98 | CNC3 busy with 26-27SO98 / 61239614-01 — CNC FIRST SIDE
26-27SO142 | 8010009209 | RUNNING | 2. CNC SECOND SIDE | CNC3 | Rohan Chakane → Sidhu Singe | 16-09-2026 15:58 | 18-09-2026 15:28 | 47.5
26-27SO142 | 8010009209 | RUNNING | 3. VMC FIRST SIDE | VMC2 | Rupesh Pawar → Saif | 18-09-2026 08:00 | 18-09-2026 19:50 | 11.83
26-27SO142 | 8010009209 | RUNNING | 4. VMC SECOND SIDE | VMC3 | Ankush Jadhav → Mahesh | 18-09-2026 12:20 | 18-09-2026 19:50 | 7.5
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CNC7 |  | 18-09-2026 19:50 | 19-09-2026 09:30 | 13.67 | CNC7 busy with 26-27SO147 / 8010009209 — CNC THIRD SIDE (higher priority)
26-27SO142 | 8010009209 | RUNNING | 5. CNC THIRD SIDE | CNC7 | Rohan Chakane | 19-09-2026 09:30 | 20-09-2026 10:00 | 24.5
26-27SO142 | 8010009209 | RUNNING | 6. DEBURING | MD1 | Anturam | 20-09-2026 09:20 | 20-09-2026 10:00 | 0.67
26-27SO142 | 8010009209 | WAITING (machine busy) |  | CMM |  | 20-09-2026 10:00 | 20-09-2026 11:18 | 1.3 | CMM busy with 26-27SO93 / 61249330-80 — CMM (higher priority)
26-27SO142 | 8010009209 | RUNNING | 7. CMM | CMM | Kiran Mohite | 20-09-2026 11:18 | 20-09-2026 13:48 | 2.5
26-27SO142 | 8010009209 | RUNNING | 8. INSPECTION | MI1 | Nitin Khade | 20-09-2026 12:58 | 20-09-2026 13:48 | 0.83
26-27SO142 | 8010009209 | RUNNING | 9. WASHING | MW1 | HP1 | 20-09-2026 13:18 | 20-09-2026 13:48 | 0.5
26-27SO134 | 9612220710 P | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220710 P | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220710 P | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220710 P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 14:00 | 09-08-2026 20:27 | 6.45 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220710 P | WAITING (machine busy) |  | CNC1 |  | 09-08-2026 20:27 | 10-08-2026 02:45 | 6.3 | CNC1 busy with 26-27SO137 / 9611340324-P — CNC SECOND SIDE (higher priority)
26-27SO134 | 9612220710 P | WAITING (crew) |  |  |  | 10-08-2026 02:45 | 10-08-2026 05:00 | 2.25 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220710 P | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220710 P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 08:00 | 10-08-2026 14:16 | 6.27 | CNC1 busy with 26-27SO105 / 9612220702-P — CNC FIRST SIDE
26-27SO134 | 9612220710 P | WAITING (machine busy) |  | CNC1 |  | 10-08-2026 14:16 | 12-08-2026 08:00 | 41.74 | CNC1 busy with 26-27SO120 / 9611443240 — CNC FIRST SIDE
26-27SO134 | 9612220710 P | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 12-08-2026 14:00 | 5.99 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220710 P | WAITING (machine busy) |  | CNC1 |  | 12-08-2026 14:00 | 13-08-2026 04:14 | 14.24 | CNC1 busy with 26-27SO134 / 9612220701-P — CNC FIRST SIDE (higher priority)
26-27SO134 | 9612220710 P | WAITING (crew) |  |  |  | 13-08-2026 04:14 | 13-08-2026 05:00 | 0.76 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220710 P | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220710 P | RUNNING | 2. CNC FIRST SIDE | CNC1 | Sandeep Kumar | 14-08-2026 08:00 | 14-08-2026 17:46 | 9.78
26-27SO134 | 9612220710 P | WAITING (machine busy) |  | MLATHE |  | 14-08-2026 17:46 | 15-08-2026 10:26 | 16.66 | MLATHE busy with 26-27SO134 / 9612220701-P — DEBURING (higher priority)
26-27SO134 | 9612220710 P | WAITING (crew) |  |  |  | 15-08-2026 10:26 | 15-08-2026 19:00 | 8.56 | Machine free — waiting for a free qualified operator
26-27SO134 | 9612220710 P | WAITING (off-hours) |  |  |  | 15-08-2026 19:00 | 16-08-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO134 | 9612220710 P | RUNNING | 3. DEBURING | MLATHE | Anturam | 16-08-2026 08:00 | 16-08-2026 10:27 | 2.45
26-27SO134 | 9612220710 P | RUNNING | 4. INSPECTION | MI1 | Nitin Khade | 16-08-2026 09:50 | 16-08-2026 10:27 | 0.61
26-27SO134 | 9612220710 P | RUNNING | 5. PACKING | MPK2 | HP1 | 16-08-2026 09:53 | 16-08-2026 10:30 | 0.61
26-27SO98 | 61239614-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239614-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239614-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 09-08-2026 14:00 | 10-08-2026 13:48 | 23.8 | CNC3 busy with 26-27SO126 / 971-571126-03 — CNC FORTH SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 10-08-2026 13:48 | 12-08-2026 19:18 | 53.5 | CNC3 busy with 26-27SO108 / 61240341-80 — CNC SECOND SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 12-08-2026 19:18 | 14-08-2026 17:48 | 46.5 | CNC3 busy with 26-27SO69 / 8010009209 — CNC SECOND SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 14-08-2026 17:48 | 16-08-2026 03:30 | 33.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC FIRST SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (crew) |  |  |  | 16-08-2026 03:30 | 16-08-2026 05:00 | 1.5 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239614-01 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 08:00 | 16-08-2026 23:54 | 15.9 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC SECOND SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 16-08-2026 23:54 | 17-08-2026 05:00 | 5.1 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC FIRST SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 17-08-2026 08:00 | 17-08-2026 17:30 | 9.5 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC SECOND SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 17-08-2026 17:30 | 18-08-2026 14:00 | 20.5 | CNC3 busy with 26-27SO118 / 61239614-01 — CNC THIRD SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 18-08-2026 14:00 | 19-08-2026 11:42 | 21.7 | CNC3 busy with 26-27SO132 / 61239819-81 — CNC THIRD SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 19-08-2026 11:42 | 23-08-2026 10:12 | 94.5 | CNC3 busy with 26-27SO117 / 00531569-01 — CNC FIRST SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 23-08-2026 10:12 | 25-08-2026 08:42 | 46.5 | CNC3 busy with 26-27SO131 / 8010005735 — CNC FIRST SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 25-08-2026 08:42 | 28-08-2026 18:12 | 81.5 | CNC3 busy with 26-27SO117 / 00531569-01 — CNC SECOND SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 28-08-2026 18:12 | 31-08-2026 11:42 | 65.5 | CNC3 busy with 26-27SO75 / 61235943-01 — CNC FIRST SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 31-08-2026 11:42 | 01-09-2026 12:42 | 25 | CNC3 busy with 26-27SO98 / 61239701-01 — CNC THIRD SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 01-09-2026 12:42 | 03-09-2026 03:12 | 38.5 | CNC3 busy with 26-27SO75 / 61235943-01 — CNC SECOND SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (crew) |  |  |  | 03-09-2026 03:12 | 03-09-2026 05:00 | 1.8 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239614-01 | WAITING (off-hours) |  |  |  | 03-09-2026 05:00 | 04-09-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 04-09-2026 08:00 | 06-09-2026 16:30 | 56.5 | CNC3 busy with 26-27SO131 / 8010005735 — CNC SECOND SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 06-09-2026 16:30 | 08-09-2026 11:00 | 42.5 | CNC3 busy with 26-27SO143 / 61239701-01 — CNC FIRST SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 08-09-2026 11:00 | 09-09-2026 17:30 | 30.5 | CNC3 busy with 26-27SO143 / 61240190-01 — CNC FIRST SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 09-09-2026 17:30 | 13-09-2026 00:00 | 78.5 | CNC3 busy with 26-27SO143 / 61239701-01 — CNC SECOND SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (crew) |  |  |  | 13-09-2026 00:00 | 13-09-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239614-01 | WAITING (off-hours) |  |  |  | 13-09-2026 05:00 | 13-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 13-09-2026 08:00 | 13-09-2026 20:00 | 12 | CNC3 busy with 26-27SO143 / 61239701-01 — CNC THIRD SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 13-09-2026 20:00 | 14-09-2026 16:30 | 20.5 | CNC3 busy with 26-27SO143 / 61240190-01 — CNC SECOND SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 14-09-2026 16:30 | 15-09-2026 15:00 | 22.5 | CNC3 busy with 26-27SO147 / 8010009209 — CNC FIRST SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 15-09-2026 15:00 | 16-09-2026 00:30 | 9.5 | CNC3 busy with 26-27SO142 / 8010009209 — CNC FIRST SIDE (higher priority)
26-27SO98 | 61239614-01 | WAITING (crew) |  |  |  | 16-09-2026 00:30 | 16-09-2026 05:00 | 4.5 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239614-01 | WAITING (off-hours) |  |  |  | 16-09-2026 05:00 | 16-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239614-01 | RUNNING | 1. CNC FIRST SIDE | CNC3 | Rohan Chakane | 16-09-2026 08:00 | 16-09-2026 15:58 | 7.98
26-27SO98 | 61239614-01 | WAITING (machine busy) |  | CNC3 |  | 16-09-2026 15:58 | 18-09-2026 15:28 | 47.5 | CNC3 busy with 26-27SO142 / 8010009209 — CNC SECOND SIDE (higher priority)
26-27SO98 | 61239614-01 | RUNNING | 2. CNC SECOND SIDE | CNC3 | Sidhu Singe → Khansab Mulla → Rohan Chakane | 18-09-2026 15:28 | 21-09-2026 10:22 | 66.9
26-27SO98 | 61239614-01 | RUNNING | 3. VMC FIRST SIDE | VMC3 | Rupesh Pawar → Saif | 20-09-2026 08:00 | 21-09-2026 13:42 | 29.7
26-27SO98 | 61239614-01 | RUNNING | 4. CNC THIRD SIDE | CNC3 | Rohan Chakane → Khansab Mulla | 21-09-2026 10:22 | 21-09-2026 22:40 | 12.3
26-27SO98 | 61239614-01 | WAITING (off-hours) |  |  |  | 21-09-2026 22:40 | 22-09-2026 08:00 | 9.32 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239614-01 | RUNNING | 5. CHAMFER | DTC2 | Anturam | 22-09-2026 08:00 | 22-09-2026 09:30 | 1.5
26-27SO98 | 61239614-01 | RUNNING | 6. CMM | CMM | Kiran Mohite | 22-09-2026 08:09 | 22-09-2026 12:39 | 4.5
26-27SO98 | 61239614-01 | RUNNING | 7. INSPECTION | MI1 | Nitin Khade | 22-09-2026 08:36 | 22-09-2026 14:36 | 6
26-27SO98 | 61239614-01 | WAITING (crew) |  |  |  | 22-09-2026 14:36 | 22-09-2026 19:00 | 4.4 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239614-01 | WAITING (off-hours) |  |  |  | 22-09-2026 19:00 | 23-09-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239614-01 | WAITING (crew) |  |  |  | 23-09-2026 08:00 | 23-09-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239614-01 | WAITING (off-hours) |  |  |  | 23-09-2026 19:00 | 25-09-2026 08:00 | 37 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239614-01 | WAITING (crew) |  |  |  | 25-09-2026 08:00 | 25-09-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239614-01 | WAITING (off-hours) |  |  |  | 25-09-2026 19:00 | 26-09-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239614-01 | WAITING (crew) |  |  |  | 26-09-2026 08:00 | 26-09-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239614-01 | WAITING (off-hours) |  |  |  | 26-09-2026 19:00 | 27-09-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239614-01 | WAITING (crew) |  |  |  | 27-09-2026 08:00 | 27-09-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239614-01 | WAITING (off-hours) |  |  |  | 27-09-2026 19:00 | 28-09-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239614-01 | WAITING (crew) |  |  |  | 28-09-2026 08:00 | 28-09-2026 19:00 | 11 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239614-01 | WAITING (off-hours) |  |  |  | 28-09-2026 19:00 | 29-09-2026 08:00 | 13 | Outside working hours (night / weekly off / holiday)
26-27SO98 | 61239614-01 | WAITING (crew) |  |  |  | 29-09-2026 08:00 | 29-09-2026 14:36 | 6.6 | Machine free — waiting for a free qualified operator
26-27SO98 | 61239614-01 | RUNNING | 9. PACKING | MPK1 | HP1 | 29-09-2026 14:36 | 29-09-2026 14:54 | 0.3
26-27SO145 | 61249396-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO145 | 61249396-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO145 | 61249396-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 10-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO145 | 61249396-01 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO145 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 10-08-2026 08:00 | 10-08-2026 13:30 | 5.5 | CNC7 busy with 26-27SO95 / 61248811-01 — CNC FIRST SIDE (higher priority)
26-27SO145 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 10-08-2026 13:30 | 11-08-2026 03:00 | 13.5 | CNC7 busy with 26-27SO95 / 61248811-01 — CNC SECOND SIDE (higher priority)
26-27SO145 | 61249396-01 | WAITING (crew) |  |  |  | 11-08-2026 03:00 | 11-08-2026 05:00 | 2 | Machine free — waiting for a free qualified operator
26-27SO145 | 61249396-01 | WAITING (off-hours) |  |  |  | 11-08-2026 05:00 | 11-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO145 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 11-08-2026 08:00 | 12-08-2026 12:00 | 28 | CNC7 busy with 26-27SO68 / 61241992-01 — CNC FIRST SIDE (higher priority)
26-27SO145 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 12-08-2026 12:00 | 12-08-2026 15:18 | 3.3 | CNC7 busy with 26-27SO111 / 61241989-01 — CNC FIRST SIDE (higher priority)
26-27SO145 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 12-08-2026 15:18 | 14-08-2026 11:48 | 44.5 | CNC7 busy with 26-27SO104 / 61249522-01 — CNC SECOND SIDE (higher priority)
26-27SO145 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 14-08-2026 11:48 | 14-08-2026 16:54 | 5.1 | CNC7 busy with 26-27SO111 / 61241989-01 — CNC THIRD SIDE (higher priority)
26-27SO145 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 14-08-2026 16:54 | 14-08-2026 21:36 | 4.7 | CNC7 busy with 26-27SO117 / 61240807-01 — CNC FIRST SIDE (higher priority)
26-27SO145 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 14-08-2026 21:36 | 15-08-2026 15:00 | 17.4 | CNC7 busy with 26-27SO68 / 61241992-01 — CNC SECOND SIDE (higher priority)
26-27SO145 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 15-08-2026 15:00 | 16-08-2026 09:42 | 18.7 | CNC7 busy with 26-27SO117 / 61239857-01 — CNC FIRST SIDE (higher priority)
26-27SO145 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 16-08-2026 09:42 | 16-08-2026 14:12 | 4.5 | CNC7 busy with 26-27SO117 / 61239857-01 — CNC SECOND SIDE (higher priority)
26-27SO145 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 16-08-2026 14:12 | 17-08-2026 11:54 | 21.7 | CNC7 busy with 26-27SO117 / 61239857-01 — CNC THIRD SIDE (higher priority)
26-27SO145 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 17-08-2026 11:54 | 18-08-2026 12:24 | 24.5 | CNC7 busy with 26-27SO69 / 8010009209 — CNC THIRD SIDE (higher priority)
26-27SO145 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 18-08-2026 12:24 | 19-08-2026 04:42 | 16.3 | CNC7 busy with 26-27SO128 / 61249396-01 — CNC FIRST SIDE (higher priority)
26-27SO145 | 61249396-01 | WAITING (crew) |  |  |  | 19-08-2026 04:42 | 19-08-2026 05:00 | 0.3 | Machine free — waiting for a free qualified operator
26-27SO145 | 61249396-01 | WAITING (off-hours) |  |  |  | 19-08-2026 05:00 | 19-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO145 | 61249396-01 | WAITING (crew) |  |  |  | 19-08-2026 08:00 | 20-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO145 | 61249396-01 | WAITING (off-hours) |  |  |  | 20-08-2026 05:00 | 21-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO145 | 61249396-01 | WAITING (crew) |  |  |  | 21-08-2026 08:00 | 22-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO145 | 61249396-01 | WAITING (off-hours) |  |  |  | 22-08-2026 05:00 | 22-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO145 | 61249396-01 | WAITING (crew) |  |  |  | 22-08-2026 08:00 | 23-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO145 | 61249396-01 | WAITING (off-hours) |  |  |  | 23-08-2026 05:00 | 23-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO145 | 61249396-01 | WAITING (crew) |  |  |  | 23-08-2026 08:00 | 24-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO145 | 61249396-01 | WAITING (off-hours) |  |  |  | 24-08-2026 05:00 | 24-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO145 | 61249396-01 | WAITING (crew) |  |  |  | 24-08-2026 08:00 | 25-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO145 | 61249396-01 | WAITING (off-hours) |  |  |  | 25-08-2026 05:00 | 25-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO145 | 61249396-01 | WAITING (crew) |  |  |  | 25-08-2026 08:00 | 26-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO145 | 61249396-01 | WAITING (off-hours) |  |  |  | 26-08-2026 05:00 | 26-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO145 | 61249396-01 | WAITING (crew) |  |  |  | 26-08-2026 08:00 | 27-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO145 | 61249396-01 | WAITING (off-hours) |  |  |  | 27-08-2026 05:00 | 28-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO145 | 61249396-01 | WAITING (crew) |  |  |  | 28-08-2026 08:00 | 29-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO145 | 61249396-01 | WAITING (off-hours) |  |  |  | 29-08-2026 05:00 | 29-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO145 | 61249396-01 | WAITING (machine busy) |  | CNC7 |  | 29-08-2026 08:00 | 30-08-2026 13:18 | 29.3 | CNC7 busy with 26-27SO128 / 61249396-01 — CNC SECOND SIDE (higher priority)
26-27SO145 | 61249396-01 | RUNNING | 1. CNC FIRST SIDE | CNC7 | Rohan Chakane → Sidhu Singe → Khansab Mulla | 30-08-2026 13:18 | 31-08-2026 21:33 | 32.26
26-27SO145 | 61249396-01 | RUNNING | 2. VMC FIRST SIDE | VMC3 | Rupesh Pawar → Swapnil → Saif | 30-08-2026 17:37 | 31-08-2026 21:33 | 27.94
26-27SO145 | 61249396-01 | RUNNING | 3. CNC SECOND SIDE | CNC7 | Khansab Mulla → Rohan Chakane | 31-08-2026 21:33 | 01-09-2026 19:49 | 22.26
26-27SO145 | 61249396-01 | RUNNING | 4. VMC SECOND SIDE | VMC3 | Rupesh Pawar → Saif | 01-09-2026 13:31 | 01-09-2026 19:49 | 6.3
26-27SO145 | 61249396-01 | RUNNING | 5. CHAMFER | DTC2 | Anturam | 01-09-2026 17:42 | 02-09-2026 12:42 | 19
26-27SO145 | 61249396-01 | RUNNING | 6. CMM | CMM | Kiran Mohite | 01-09-2026 18:18 | 02-09-2026 13:18 | 19
26-27SO145 | 61249396-01 | RUNNING | 7. WASHING | MW1 | HP1 | 02-09-2026 12:30 | 02-09-2026 13:18 | 0.8
26-27SO145 | 61249396-01 | RUNNING | 8. PACKING | MPK1 | HP2 | 02-09-2026 12:34 | 02-09-2026 13:22 | 0.8
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 09-08-2026 14:00 | 6 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 09-08-2026 14:00 | 10-08-2026 00:00 | 10 | CNC6 busy with 26-27SO130 / 61249330-80 — CNC SECOND SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 10-08-2026 00:00 | 10-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 10-08-2026 08:00 | 11-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (off-hours) |  |  |  | 11-08-2026 05:00 | 11-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 11-08-2026 08:00 | 12-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (off-hours) |  |  |  | 12-08-2026 05:00 | 12-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 12-08-2026 08:00 | 13-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (off-hours) |  |  |  | 13-08-2026 05:00 | 14-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 14-08-2026 08:00 | 15-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (off-hours) |  |  |  | 15-08-2026 05:00 | 15-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 15-08-2026 08:00 | 16-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (off-hours) |  |  |  | 16-08-2026 05:00 | 16-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 16-08-2026 08:00 | 17-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (off-hours) |  |  |  | 17-08-2026 05:00 | 17-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 17-08-2026 08:00 | 18-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (off-hours) |  |  |  | 18-08-2026 05:00 | 18-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 18-08-2026 08:00 | 19-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (off-hours) |  |  |  | 19-08-2026 05:00 | 19-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 19-08-2026 08:00 | 21-08-2026 09:30 | 49.5 | CNC6 busy with 26-27SO108 / 61240341-80 — CNC THIRD SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 21-08-2026 09:30 | 21-08-2026 14:12 | 4.7 | CNC6 busy with 26-27SO132 / 61239819-81 — CNC FORTH SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 21-08-2026 14:12 | 23-08-2026 08:42 | 42.5 | CNC6 busy with 26-27SO98 / 61239701-01 — CNC FIRST SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 23-08-2026 08:42 | 25-08-2026 09:02 | 48.33 | CNC6 busy with 26-27SO130 / 61249330-80 — CNC THIRD SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 25-08-2026 09:02 | 26-08-2026 12:52 | 27.83 | CNC6 busy with 26-27SO130 / 61249330-80 — CNC FORTH SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 26-08-2026 12:52 | 28-08-2026 20:52 | 56 | CNC6 busy with 26-27SO117 / 00531569-01 — CNC THIRD SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 28-08-2026 20:52 | 30-08-2026 04:22 | 31.5 | CNC6 busy with 26-27SO98 / 61239701-01 — CNC SECOND SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 30-08-2026 04:22 | 30-08-2026 05:00 | 0.63 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (off-hours) |  |  |  | 30-08-2026 05:00 | 30-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 30-08-2026 08:00 | 31-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (off-hours) |  |  |  | 31-08-2026 05:00 | 31-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 31-08-2026 08:00 | 01-09-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (off-hours) |  |  |  | 01-09-2026 05:00 | 01-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 01-09-2026 08:00 | 02-09-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (off-hours) |  |  |  | 02-09-2026 05:00 | 02-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 02-09-2026 08:00 | 05-09-2026 17:30 | 81.5 | CNC6 busy with 26-27SO146 / 61240401-01 — CNC FIRST SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 05-09-2026 17:30 | 07-09-2026 23:00 | 53.5 | CNC6 busy with 26-27SO146 / 61240401-01 — CNC SECOND SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 07-09-2026 23:00 | 08-09-2026 22:30 | 23.5 | CNC6 busy with 26-27SO93 / 61249330-80 — CNC FIRST SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 08-09-2026 22:30 | 08-09-2026 23:54 | 1.4 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 08-09-2026 23:54 | 09-09-2026 22:24 | 22.5 | CNC6 busy with 26-27SO131 / 8010005735 — CNC THIRD SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 09-09-2026 22:24 | 11-09-2026 20:54 | 46.5 | CNC6 busy with 26-27SO131 / 8010005735 — CNC FORTH SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 11-09-2026 20:54 | 13-09-2026 10:24 | 37.5 | CNC6 busy with 26-27SO93 / 61249330-80 — CNC SECOND SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 13-09-2026 10:24 | 14-09-2026 12:54 | 26.5 | CNC6 busy with 26-27SO143 / 61240222-01 — CNC SECOND SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 14-09-2026 12:54 | 15-09-2026 02:24 | 13.5 | CNC6 busy with 26-27SO143 / 61240222-01 — CNC THIRD SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 15-09-2026 02:24 | 15-09-2026 05:00 | 2.6 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (off-hours) |  |  |  | 15-09-2026 05:00 | 15-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 15-09-2026 08:00 | 15-09-2026 18:30 | 10.5 | CNC6 busy with 26-27SO147 / 8010009209 — CNC SECOND SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 15-09-2026 18:30 | 18-09-2026 13:00 | 66.5 | CNC6 busy with 26-27SO93 / 61249330-80 — CNC THIRD SIDE (higher priority)
26-27SO88 | 61249330-80 | WAITING (machine busy) |  | CNC6 |  | 18-09-2026 13:00 | 19-09-2026 19:30 | 30.5 | CNC6 busy with 26-27SO93 / 61249330-80 — CNC FORTH SIDE (higher priority)
26-27SO88 | 61249330-80 | RUNNING | 1. CNC FIRST SIDE | CNC6 | Khansab Mulla → Sidhu Singe | 19-09-2026 19:30 | 20-09-2026 19:00 | 23.5
26-27SO88 | 61249330-80 | WAITING (crew) |  |  |  | 20-09-2026 19:00 | 21-09-2026 05:00 | 10 | Machine free — waiting for a free qualified operator
26-27SO88 | 61249330-80 | WAITING (off-hours) |  |  |  | 21-09-2026 05:00 | 21-09-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO88 | 61249330-80 | RUNNING | 2. CNC SECOND SIDE | CNC6 | Sidhu Singe → Rohan Chakane | 21-09-2026 08:00 | 22-09-2026 18:30 | 34.5
26-27SO88 | 61249330-80 | RUNNING | 3. VMC FIRST SIDE | VMC3 | Rupesh Pawar → Saif | 21-09-2026 13:42 | 25-09-2026 12:12 | 94.5
26-27SO88 | 61249330-80 | RUNNING | 4. VMC SECOND SIDE | VMC3 | Rupesh Pawar → Saif | 25-09-2026 12:12 | 26-09-2026 19:42 | 31.5
26-27SO88 | 61249330-80 | RUNNING | 5. CNC THIRD SIDE | CNC6 | Rohan Chakane → Khansab Mulla | 25-09-2026 16:24 | 26-09-2026 21:54 | 29.5
26-27SO88 | 61249330-80 | RUNNING | 6. CNC FORTH SIDE | CNC6 | Khansab Mulla → Rohan Chakane | 26-09-2026 21:54 | 27-09-2026 18:24 | 20.5
26-27SO88 | 61249330-80 | RUNNING | 7. CHAMFER | DTC2 | Anturam | 27-09-2026 14:24 | 27-09-2026 18:24 | 4
26-27SO88 | 61249330-80 | RUNNING | 8. INSPECTION | MI1 | Nitin Khade | 27-09-2026 14:48 | 27-09-2026 18:48 | 4
26-27SO88 | 61249330-80 | RUNNING | 9. CMM | CMM | Kiran Mohite | 27-09-2026 15:12 | 28-09-2026 10:12 | 19
26-27SO88 | 61249330-80 | RUNNING | 10. WASHING | MW1 | HP1 | 28-09-2026 09:42 | 28-09-2026 10:12 | 0.5
26-27SO143 | 61249291-01 | WAITING (crew) |  |  |  | 09-08-2026 00:00 | 09-08-2026 05:00 | 5 | Machine free — waiting for a free qualified operator
26-27SO143 | 61249291-01 | WAITING (off-hours) |  |  |  | 09-08-2026 05:00 | 09-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61249291-01 | WAITING (crew) |  |  |  | 09-08-2026 08:00 | 10-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61249291-01 | WAITING (off-hours) |  |  |  | 10-08-2026 05:00 | 10-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CNC7 |  | 10-08-2026 08:00 | 10-08-2026 13:30 | 5.5 | CNC7 busy with 26-27SO95 / 61248811-01 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CNC7 |  | 10-08-2026 13:30 | 11-08-2026 03:00 | 13.5 | CNC7 busy with 26-27SO95 / 61248811-01 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61249291-01 | WAITING (crew) |  |  |  | 11-08-2026 03:00 | 11-08-2026 05:00 | 2 | Machine free — waiting for a free qualified operator
26-27SO143 | 61249291-01 | WAITING (off-hours) |  |  |  | 11-08-2026 05:00 | 11-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CNC7 |  | 11-08-2026 08:00 | 12-08-2026 12:00 | 28 | CNC7 busy with 26-27SO68 / 61241992-01 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CNC7 |  | 12-08-2026 12:00 | 12-08-2026 15:18 | 3.3 | CNC7 busy with 26-27SO111 / 61241989-01 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CNC7 |  | 12-08-2026 15:18 | 14-08-2026 11:48 | 44.5 | CNC7 busy with 26-27SO104 / 61249522-01 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CNC7 |  | 14-08-2026 11:48 | 14-08-2026 16:54 | 5.1 | CNC7 busy with 26-27SO111 / 61241989-01 — CNC THIRD SIDE (higher priority)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CNC7 |  | 14-08-2026 16:54 | 14-08-2026 21:36 | 4.7 | CNC7 busy with 26-27SO117 / 61240807-01 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CNC7 |  | 14-08-2026 21:36 | 15-08-2026 15:00 | 17.4 | CNC7 busy with 26-27SO68 / 61241992-01 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CNC7 |  | 15-08-2026 15:00 | 16-08-2026 09:42 | 18.7 | CNC7 busy with 26-27SO117 / 61239857-01 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CNC7 |  | 16-08-2026 09:42 | 16-08-2026 14:12 | 4.5 | CNC7 busy with 26-27SO117 / 61239857-01 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CNC7 |  | 16-08-2026 14:12 | 17-08-2026 11:54 | 21.7 | CNC7 busy with 26-27SO117 / 61239857-01 — CNC THIRD SIDE (higher priority)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CNC7 |  | 17-08-2026 11:54 | 18-08-2026 12:24 | 24.5 | CNC7 busy with 26-27SO69 / 8010009209 — CNC THIRD SIDE (higher priority)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CNC7 |  | 18-08-2026 12:24 | 19-08-2026 04:42 | 16.3 | CNC7 busy with 26-27SO128 / 61249396-01 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61249291-01 | WAITING (crew) |  |  |  | 19-08-2026 04:42 | 19-08-2026 05:00 | 0.3 | Machine free — waiting for a free qualified operator
26-27SO143 | 61249291-01 | WAITING (off-hours) |  |  |  | 19-08-2026 05:00 | 19-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61249291-01 | WAITING (crew) |  |  |  | 19-08-2026 08:00 | 20-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61249291-01 | WAITING (off-hours) |  |  |  | 20-08-2026 05:00 | 21-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61249291-01 | WAITING (crew) |  |  |  | 21-08-2026 08:00 | 22-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61249291-01 | WAITING (off-hours) |  |  |  | 22-08-2026 05:00 | 22-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61249291-01 | WAITING (crew) |  |  |  | 22-08-2026 08:00 | 23-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61249291-01 | WAITING (off-hours) |  |  |  | 23-08-2026 05:00 | 23-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61249291-01 | WAITING (crew) |  |  |  | 23-08-2026 08:00 | 24-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61249291-01 | WAITING (off-hours) |  |  |  | 24-08-2026 05:00 | 24-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61249291-01 | WAITING (crew) |  |  |  | 24-08-2026 08:00 | 25-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61249291-01 | WAITING (off-hours) |  |  |  | 25-08-2026 05:00 | 25-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61249291-01 | WAITING (crew) |  |  |  | 25-08-2026 08:00 | 26-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61249291-01 | WAITING (off-hours) |  |  |  | 26-08-2026 05:00 | 26-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61249291-01 | WAITING (crew) |  |  |  | 26-08-2026 08:00 | 27-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61249291-01 | WAITING (off-hours) |  |  |  | 27-08-2026 05:00 | 28-08-2026 08:00 | 27 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61249291-01 | WAITING (crew) |  |  |  | 28-08-2026 08:00 | 29-08-2026 05:00 | 21 | Machine free — waiting for a free qualified operator
26-27SO143 | 61249291-01 | WAITING (off-hours) |  |  |  | 29-08-2026 05:00 | 29-08-2026 08:00 | 3 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CNC7 |  | 29-08-2026 08:00 | 30-08-2026 13:18 | 29.3 | CNC7 busy with 26-27SO128 / 61249396-01 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CNC7 |  | 30-08-2026 13:18 | 31-08-2026 21:33 | 32.26 | CNC7 busy with 26-27SO145 / 61249396-01 — CNC FIRST SIDE (higher priority)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CNC7 |  | 31-08-2026 21:33 | 01-09-2026 19:49 | 22.26 | CNC7 busy with 26-27SO145 / 61249396-01 — CNC SECOND SIDE (higher priority)
26-27SO143 | 61249291-01 | RUNNING | 3. CNC SECOND SIDE | CNC7 | Khansab Mulla | 01-09-2026 19:49 | 02-09-2026 00:37 | 4.8
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | DTC2 |  | 02-09-2026 00:37 | 02-09-2026 12:42 | 12.08 | DTC2 busy with 26-27SO145 / 61249396-01 — CHAMFER (higher priority)
26-27SO143 | 61249291-01 | WAITING (crew) |  |  |  | 02-09-2026 12:42 | 02-09-2026 19:00 | 6.3 | Machine free — waiting for a free qualified operator
26-27SO143 | 61249291-01 | WAITING (off-hours) |  |  |  | 02-09-2026 19:00 | 04-09-2026 08:00 | 37 | Outside working hours (night / weekly off / holiday)
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | DTC2 |  | 04-09-2026 08:00 | 04-09-2026 08:50 | 0.83 | DTC2 busy with 26-27SO75 / 61235943-01 — CHAMFER (higher priority)
26-27SO143 | 61249291-01 | RUNNING | 4. CHAMFER | DTC2 | Anturam | 04-09-2026 08:50 | 04-09-2026 09:45 | 0.92
26-27SO143 | 61249291-01 | WAITING (machine busy) |  | CMM |  | 04-09-2026 09:45 | 04-09-2026 10:35 | 0.83 | CMM busy with 26-27SO75 / 61235943-01 — CMM (higher priority)
26-27SO143 | 61249291-01 | RUNNING | 5. CMM | CMM | Kiran Mohite | 04-09-2026 10:35 | 04-09-2026 13:20 | 2.75
26-27SO143 | 61249291-01 | RUNNING | 6. WASHING | MW1 | HP1 | 04-09-2026 13:09 | 04-09-2026 13:20 | 0.18
26-27SO143 | 61249291-01 | RUNNING | 7. PACKING | MPK1 | HP2 | 04-09-2026 13:10 | 04-09-2026 13:21 | 0.18